## MTS WorkProgramme status
Current status of MTS active Work Items (as of 5th October 2004)
When a “current version available” number in shown the document can be found in the MTS “07-Drafts” area : http://portal.etsi.org/docbox/mts/MTS/07-Drafts/
WI nb | WI Ref | Type | Class | ETSInb | Current Status | Current Version | STF nb | Rapporteur | NEXT Milestone | TARGET DATE
075 | DTR/MTS-00075 TTCN-3 Training Material | D | TR |  | draft available | 0.1.1 |  | Rethy | TB approval | 2004-10-21
085 | DTS/MTS-00085 UML 2.0 profile for communication systems | D | TS |  | 1st draft | 0.1.0 |  | Bjorkander | Draft available | 2004-10-31
086 | DTS/MTS-00086 MTS-IPT Conformance Test Specifications: SIGTRAN SCTP | D | TS |  | draft available | 0.0.4 |  | Vassiliou-Gioles | TB approval | 2004-10-21
087 | DTS/MTS-00087 MTS-IPT Conformance Test Specifications: SIGTRAN M3UA | D | TS |  | draft available | 0.0.3 |  | Vassiliou-Gioles | TB approval | 2004-10-21
088 | DTS/MTS-00088 XML to TTCN-3 mapping | D | TS |  | 1st draft |  |  | Schieferdecker | Draft available | 2004-10-14
090-1 ttcn3 core | RES/MTS-00090-1 ttcn3 core TTCN-3 Core Language Edition 3 | R | ES | 201 873-1 | start |  | 253 | Rethy | Draft available | 2004-11-19
090-2 ttcn3 tft | RES/MTS-00090-2 ttcn3 tft TTCN-3 TFT Edition 3 | R | ES | 201 873-2 | start |  | 253 | Rethy | Draft available | 2004-11-19
090-3 ttcn3 gft | RES/MTS-00090-3 ttcn3 gft TTCN-3 GFT Edition 3 | R | ES | 201 873-3 | start |  | 253 | Schieferdecker | Draft available | 2004-11-19
090-4 ttcn3 os | RES/MTS-00090-4 ttcn3 os TTCN-3 OS Edition 3 | R | ES | 201 873-4 | start |  | 253 | Grabowski | Draft available | 2004-11-19
090-5 ttcn3 tri | RES/MTS-00090-5 ttcn3 tri TTCN-3 TRI edition 3. | R | ES | 201 873-5 | start |  | 253 | Schieferdecker | Draft available | 2004-11-19
| RES/MTS-00090-6 ttcn3 tci TTCN-3 TCI Edition 3. | R | ES | 202 873-6 | start |  | 253 | Schieferdecker | Draft available | 2004-11-19
090-7 ttcn3 & asn.1 | DES/MTS-00090-7 ttcn3 & asn.1 TTCN-3 and the Use of ASN.1 | D | ES | 201 873-7 | start |  | 253 | Rethy | Draft available | 2004-11-19
090mi | MI/MTS-00090mi TTCN 3 maintenance; |  | MI |  | 0 |  |  | wiles | Start of work | 2004-02-01
091 | DTR/MTS-00091 Generation Methodology for Conformance and Interoperability Test Specs: PTD | D | TR |  | 1st draft | 1.1.1 |  | Frey | Draft available | 2004-10-14
093 | DTS/MTS-00093 SIGTRAN M2UA (SPAN subset) | D | TS |  | draft available | 0.0.6 | 269 | Schmitting | TB approval | 2004-10-21
095-1 | RTS/MTS-00095-1 H.225. PICS | R | TS | 101 804-1 | draft available | 2.1.1 | 270 | Fischer | End of pre-processing | 2004-09-21
095-1[2] | RTS/MTS-00095-1[2] H.225. PICS | R | TS | 101 804-1 | start |  |  | Fischer | Table of Contents and Scope | 2004-06-15
095-2 | RTS/MTS-00095-2 H.225 TSS & TPs | R | TS | 101 804-2 | draft available | 1.1.1 | 270 | Fischer | End of pre-processing | 2004-09-22
095-2[2] | RTS/MTS-00095-2[2] H.225 TSS & TPs | R | TS | 101 804-2 | 0 |  |  | Fischer | Start of work | 2004-04-15
095-3 | RTS/MTS-00095-3 H.225. ATS & PIXIT | R | TS | 101 804-3 | draft available | 2.1.1 | 270 | Fischer | End of pre-processing | 2004-09-22
095-3[2] | RTS/MTS-00095-3[2] H.225. ATS & PIXIT | R | TS | 101 804-3 | 0 |  |  | Fischer | Start of work | 2004-04-15
096-1 | DTS/MTS-00096-1 H.248 PICS | D | TS |  | draft available | 1.1.0 | 270 | Fischer | TB approval | 2004-10-21
096-1[2] | RTS/MTS-00096-1[2] H.248 PICS | R | TS |  | 0 |  |  | Fischer | Start of work | 2004-04-15
096-2 | DTS/MTS-00096-2 H.248 TSS & TPs | D | TS |  | draft available | 1.1.0 | 270 | Fischer | TB approval | 2004-10-21
096-2[2] | RTS/MTS-00096-2[2] H.248 TSS & TPs | R | TS |  | 0 |  |  | Fischer | Start of work | 2004-04-14
096-3 | DTS/MTS-00096-3 H.248 ATS & PIXIT | D | TS |  | draft available | 1.0.0 | 270 | Fischer | Start of TB approval process | 2004-11-08
096-3[2] | RTS/MTS-00096-3[2] H.248 ATS & PIXIT | R | TS |  | 0 |  |  | Fischer | Start of work | 2004-04-15
097-1 | DTS/MTS-00097-1 SIP PICS | D | TS | 102 002-1 | draft available | 1.1.0 | 270 | Fischer | TB approval | 2004-10-21
097-1[2] | RTS/MTS-00097-1[2] SIP PICS | R | TS | 102 002-1 | 0 |  |  | Fischer | Start of work | 2004-04-15
097-2 | DTS/MTS-00097-2 SIP TSS & TPs | D | TS | 102 002-2 | draft available | 1.1.0 | 270 | Fischer | TB approval | 2004-10-21
097-2[2] | RTS/MTS-00097-2[2] SIP TSS & TPs | R | TS | 102 002-2 | 0 |  |  | Fischer | Start of work | 2004-04-15
097-3 | DTS/MTS-00097-3 SIP ATS & PIXIT | D | TS | 102 002-3 | draft available | 1.0.0 | 270 | Fischer | TB approval | 2004-10-21
097-3[2] | RTS/MTS-00097-3[2] SIP ATS & PIXIT | R | TS | 102 002-3 | 0 |  |  | Fischer | Start of work | 2004-04-15
098-1 | DTS/MTS-00098-1 H.245 PICS | D | TS | 101 890-1 | start |  |  | wiles | Table of Contents and Scope | 2003-09-26
098-2 | DTS/MTS-00098-2 H.245 Test Suite Structure and Test Purposes | D | TS | 101 890-2 | start |  |  | wiles | Table of Contents and Scope | 2003-09-26
098-3 | DTS/MTS-00098-3 H.245 Abstract Test Suite and PIXIT Specification | D | TS | 101 890-3 | start |  |  | wiles | Table of Contents and Scope | 2003-09-26
01-IPv6-Fwk | DTS/MTS-IPT-01-IPv6-Fwk IPv6 Testing: Methodology and Framework | D | TS |  | 0 |  | 276 | wiles | Start of work | 2004-10-04
02-IPv6-BaseT3Lib | MI/MTS-IPT-02-IPv6-BaseT3Lib IPv6 Baseline: TTCN-3 Library |  | MI |  | 0 |  | 276 | wiles | Start of work | 2004-10-04
03-IPv6-CoreReqCat | DTS/MTS-IPT-03-IPv6-CoreReqCat IPv6 Core :Requirements Catalogue | D | TS |  | 0 |  | 276 | wiles | Start of work | 2004-10-04
04-IPv6-CoreT3Lib | MI/MTS-IPT-04-IPv6-CoreT3Lib IPv6 Core: TTCN-3 Library |  | MI |  | 0 |  | 276 | wiles | Start of work | 2005-01-03
05-IPv6-CoreTSS_TP | DTS/MTS-IPT-05-IPv6-CoreTSS_TP IPv6 Core: Conformance TSS & TP | D | TS |  | 0 |  | 276 | wiles | Start of work | 2005-01-03
06-IPv6-CoreATS | DTS/MTS-IPT-06-IPv6-CoreATS IPv6 Core: ATS | D | TS |  | 0 |  | 276 | wiles | Start of work | 2005-04-04
07-IPv6-CoreITS | DTS/MTS-IPT-07-IPv6-CoreITS IPv6 Core: Interoperability Test Suite | D | TS |  | 0 |  | 276 | wiles | Start of work | 2004-11-29