| Title*: | First Progress Report from STF417 (Validation Methods) |
| --- | --- |
| from Source*: | PQM Consultants |
| Contact: | Steve Randall |
| input for Committee*: | MTS |
| Contribution For*: | Decision | X |  |
|  | Discussion |  |  |
|  | Information |  |  |
| Submission date*: | 2011-03-16 |
| Meeting & Allocation: | MTS#53 - |
| Relevant WI(s), or deliverable(s): |  |

Decision/action requested:	 TC-MTS is invited to approve this first progress report from STF417

|  | Milestone: A |
| --- | --- |
|  | Date: 05 April 2011 |
|  | Author: Steve Randall |
|  | Page 1 of 3 |

STF	417

Title: 	Standards Validation Methods

STF Leader: 	Steve Randall 	steve.randall@pqmconsultants.com

TB	MTS

TB Chair:	Stephan Schulz 	stephan.schulz@conformiq.com

Milestone:	A

Milestone description:
Progress Report#1 approved by MTS#53 (12-13 April 2011) plenary and initial draft available for discussion.

To be approved by: ETSI Director-General and TB Chair

### 1	Executive summary

- STF Experts selected February 2011

- First session in March 2011

- Initial draft (Scope & ToC) available as MTS(11)0017

- Concerns raised over whether the deliverable should replace or complement the existing EG 201 015. Discussion and decision at MTS#53.

### 2	Introduction

This is the first progress report from STF417. The STF was established on 23rd February 2011 to produce a new guide to the use of practical validation methods within the standardization process. The experts selected were:

- Ina Schieferdecker FOKUS

- Steve Randall PQM Consultants (STF Leader)

Sessions have been planned throughout 2011 with the finished deliverable to be available for final approval at MTS#54 in October.

### 3	Contractual milestone

The approval of this progress report and the presence of the first draft (Scope and ToC) of the project deliverable (REG/MTS-00122) as MTS(11)0017 at MTS#53 constitute achievement of Milestone A.

### 4	Progress of the work

It has been possible to plan only a few session days during the first few weeks of the project and so limited progress was expected during this period. The initial goal was to produce a first draft of the deliverable containing the Scope and the Table of Contents and this has been achieved. Progress is planned to accelerate over the next two months.

### 5	Assessment of technical risk, difficulties encountered/expected, unresolved issues

Some concern has been raised from within the ETSI Secretariat regarding the status of the STF417 deliverable, REG/MTS-00122. It is felt that revising (and, thus, replacing the existing Validation Handbook, EG 201 015) might be detrimental as some useful guidance on model-based validation techniques could be lost. This issue is raised for discussion within MTS in MTS(11)0016.

### 6	Proposed changes in the STF work plan

None.

### 7	Resources requirements

No changes required.

### 8	Changes in the STF Team

None.

### 9	Meetings attended on behalf of the STF with the reference TB and other ETSI TBs

The STF leader attended MTS#53 on 12th-13th April in Sophia Antipolis to present and discuss the initial progress of the STF.

### 10	STF communications, presentations, promotion, inside and outside ETSI, WEB pages etc

The STF has produced a summary of the goals and constitution of STF417 as a web page within the ETSI portal at:

http://portal.etsi.org/STFs/STF_HomePages/STF417/STF417.asp

### 11	Technical advice required from the reference Technical Body

See clause 5 of this report.

### 12	Status of the deliverables

An initial draft of REG/MTS-00122 containing only Scope and ToC has been uploaded as MTS(11)0017 to MTS#53.

### 13	Next report

The next report is scheduled for: 15th June 2011

### 14	Any other business

None