## Work Programme before MTS#57
MTS
[6 empty] | Found: 26 WI(s) |  |  |  |  | Adoption | Current |  | NEXT |  | Approval & PUB
WKI_ID | STF | DELIV_TYPE | DELIV_CLASS | wkiSerialNumber | WKI_REFERENCE | WKI_Long_Reference | ETSInb | Full_Title | WORKING_TITLE | Rapporteur | AdoptionDate | Current_Status | Current_Achieve_Date | Next Status | planned | Approval | Pub_Plan | Pub_As_Version | Hyperlink to WPM
38240 | 442 | D | TR | 141 MBT_CaseStudies | DTR/MTS-141 MBT_CaseStudies | () DTR/MTS-141 MBT_CaseStudies MBT Case Studies in ETSI |  | Methods for Testing and Specification (MTS); Model-Based Testing (MBT); Application of MBT in ETSI case studies | MBT Case Studies in ETSI | Schulz | 2011-10-05 | Early draft | 2012-05-13 | Stable draft | 2012-10-15 | 2012-11-15 | 2012-12-27 | 1.1.1 | DTR/MTS-141 MBT_CaseStudies - MBT Case Studies in ETSI
38241 | 442 | D | EG | 142 MBT_methodology | DEG/MTS-00142 MBT_methodology | () DEG/MTS-00142 MBT_methodology MBT methodology |  | Methods for Testing and Specification (MTS); Model-Based Testing (MBT); Methodology for standardized test specification development | MBT methodology | Schulz | 2011-10-05 | TB adoption of WI | 2011-10-05 | Early draft | 2012-05-15 | 2012-11-15 | 2013-02-25 | 1.1.1 | DEG/MTS-00142 MBT_methodology - MBT methodology
38242 |  | R | ES | 128ed121 MBTmodConce | RES/MTS-00128ed121 MBTmodConce | (202 951) RES/MTS-00128ed121 MBTmodConce MBT Rqmts for Modeling Notations | 202 951 | Methods for Testing and Specification (MTS); Model-Based Testing (MBT); Requirements for Modelling Notations | MBT Rqmts for Modeling Notations | Schulz | 2011-10-05 | TB adoption of WI | 2011-10-05 | Early draft | 2012-05-15 | 2013-01-03 | 2013-04-15 | 1.2.1 | RES/MTS-00128ed121 MBTmodConce - MBT Rqmts for Modeling Notations
38296 | 446 | R | ES | 201873-1 T3ed451 cor | RES/MTS-201873-1 T3ed451 cor | (201 873-1) RES/MTS-201873-1 T3ed451 cor TTCN-3 Edition 4.5.1: Core Language | 201 873-1 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; Part 1: TTCN-3 Core Language | TTCN-3 Edition 4.5.1: Core Language | Schieferdecker | 2011-10-26 | TB adoption of WI | 2011-10-26 | Early draft | 2012-06-30 | 2013-01-31 |  | 4.5.1 | RES/MTS-201873-1 T3ed451 cor - TTCN-3 Edition 4.5.1: Core Language
38301 | 446 | R | ES | 201873-10 T3ed451DOC | RES/MTS-201873-10 T3ed451DOC | (201 873-10) RES/MTS-201873-10 T3ed451DOC TTCN-3 Edition 4.5.1: T3Doc | 201 873-10 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; Part 10: TTCN-3 Documentation Comment Specification | TTCN-3 Edition 4.5.1: T3Doc | Rethy | 2011-10-26 | TB adoption of WI | 2011-10-26 | Early draft | 2012-06-30 | 2013-01-31 | 2013-05-13 | 4.5.1 | RES/MTS-201873-10 T3ed451DOC - TTCN-3 Edition 4.5.1: T3Doc
38295 | 446 | R | ES | 201873-4 T3 ed451 OS | RES/MTS-201873-4 T3 ed451 OS | (201 873-4) RES/MTS-201873-4 T3 ed451 OS TTCN-3 Edition 4.5.1: OS | 201 873-4 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; Part 4: TTCN-3 Operational Semantics | TTCN-3 Edition 4.5.1: OS | Schieferdecker | 2011-10-26 | TB adoption of WI | 2011-10-26 | Early draft | 2012-06-30 | 2013-01-31 | 2013-05-13 | 4.5.1 | RES/MTS-201873-4 T3 ed451 OS - TTCN-3 Edition 4.5.1: OS
38294 | 446 | R | ES | 201873-5 T3ed451 TRI | RES/MTS-201873-5 T3ed451 TRI | (201 873-5) RES/MTS-201873-5 T3ed451 TRI TTCN-3 Edition 4.5.1: TRI | 201 873-5 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; Part 5: TTCN-3 Runtime Interface (TRI) | TTCN-3 Edition 4.5.1: TRI | Schieferdecker | 2011-10-26 | TB adoption of WI | 2011-10-26 | Early draft | 2012-06-30 | 2013-01-31 | 2013-05-13 | 4.5.1 | RES/MTS-201873-5 T3ed451 TRI - TTCN-3 Edition 4.5.1: TRI
38297 | 446 | R | ES | 201873-6 T3ed451 TCI | RES/MTS-201873-6 T3ed451 TCI | (201 873-6) RES/MTS-201873-6 T3ed451 TCI TTCN-3 Edition 4.5.1: TCI | 201 873-6 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; Part 6: TTCN-3 Control Interface (TCI) | TTCN-3 Edition 4.5.1: TCI | Schieferdecker | 2011-10-26 | TB adoption of WI | 2011-10-26 | Early draft | 2012-06-30 | 2013-01-31 | 2013-05-13 | 4.5.1 | RES/MTS-201873-6 T3ed451 TCI - TTCN-3 Edition 4.5.1: TCI
38298 | 446 | R | ES | 201873-7 T3ed451ASN1 | RES/MTS-201873-7 T3ed451ASN1 | (201 873-7) RES/MTS-201873-7 T3ed451ASN1 TTCN-3 Edition 4.5.1: the use of ASN.1 | 201 873-7 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; Part 7: Using ASN.1 with TTCN-3 | TTCN-3 Edition 4.5.1: the use of ASN.1 | Rethy | 2011-10-26 | TB adoption of WI | 2011-10-26 | Early draft | 2012-06-30 | 2013-03-21 | 2013-07-01 | 4.5.1 | RES/MTS-201873-7 T3ed451ASN1 - TTCN-3 Edition 4.5.1: the use of ASN.1
38299 | 446 | R | ES | 201873-8 T3ed451IDL | RES/MTS-201873-8 T3ed451IDL | (201 873-8) RES/MTS-201873-8 T3ed451IDL TTCN-3 Edition 4.5.1: IDL | 201 873-8 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; Part 8: The IDL to TTCN-3 Mapping | TTCN-3 Edition 4.5.1: IDL | Rethy | 2011-10-26 | TB adoption of WI | 2011-10-26 | Early draft | 2012-06-30 | 2013-03-21 | 2013-07-01 | 4.5.1 | RES/MTS-201873-8 T3ed451IDL - TTCN-3 Edition 4.5.1: IDL
38300 | 446 | R | ES | 201873-9 T3ed451XML | RES/MTS-201873-9 T3ed451XML | (201 873-9) RES/MTS-201873-9 T3ed451XML TTCN-3 Edition 4.5.1: the Use of XML | 201 873-9 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; Part 9: Using XML schema with TTCN-3 | TTCN-3 Edition 4.5.1: the Use of XML | Rethy | 2011-10-26 | TB adoption of WI | 2011-10-26 | Early draft | 2012-06-30 | 2013-01-31 | 2013-05-13 | 4.5.1 | RES/MTS-201873-9 T3ed451XML - TTCN-3 Edition 4.5.1: the Use of XML
31900 | 446 | R | ES | 112ed121 T3Ext_Conf | RES/MTS-112ed121 T3Ext_Conf | (202 781) RES/MTS-112ed121 T3Ext_Conf TTCN-3 extension: Configuration & Deployment support | 202 781 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; TTCN-3 Language Extensions: Configuration and Deployment Support | TTCN-3 extension: Configuration & Deployment support | Grabowski | 2009-10-31 | Start of work | 2009-10-31 | Final draft for approval | 2012-12-31 | 2013-01-31 | 2013-05-13 | 1.2.1 | RES/MTS-112ed121 T3Ext_Conf - TTCN-3 extension: Configuration & Deployment support
31899 | 446 | R | ES | 113ed121 T3Ext_Perf | RES/MTS-113ed121 T3Ext_Perf | (202 782) RES/MTS-113ed121 T3Ext_Perf TTCN-3 extension: Performance and Real Time Testing | 202 782 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; TTCN-3 Language Extensions: TTCN-3 Performance and Real Time Testing | TTCN-3 extension: Performance and Real Time Testing | Grabowski | 2009-10-31 | Start of work | 2009-10-31 | Final draft for approval | 2012-12-31 | 2013-01-31 | 2013-05-13 | 1.2.1 | RES/MTS-113ed121 T3Ext_Perf - TTCN-3 extension: Performance and Real Time Testing
35106 | 446 | R | ES | 123ed131 T3Ext_AdvP | RES/MTS-123ed131 T3Ext_AdvP | (202 784) RES/MTS-123ed131 T3Ext_AdvP TTCN-3 extension: Advanced Parameterization | 202 784 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; TTCN-3 Language Extensions: Advanced Parameterization | TTCN-3 extension: Advanced Parameterization | Rethy | 2010-10-13 | TB adoption of WI | 2010-10-13 | Final draft for approval | 2012-12-31 | 2013-01-31 | 2013-05-13 | 1.3.1 | RES/MTS-123ed131 T3Ext_AdvP - TTCN-3 extension: Advanced Parameterization
35107 | 446 | R | ES | 124ed131 T3Ext_Behav | RES/MTS-124ed131 T3Ext_Behav | (202 785) RES/MTS-124ed131 T3Ext_Behav TTCN-3 extension: Behaviour Types | 202 785 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; TTCN-3 Language Extensions: Behaviour Types | TTCN-3 extension: Behaviour Types | Rethy | 2010-10-13 | TB adoption of WI | 2010-10-13 | Final draft for approval | 2012-12-31 | 2013-01-31 | 2013-05-13 | 1.3.1 | RES/MTS-124ed131 T3Ext_Behav - TTCN-3 extension: Behaviour Types
38302 | 446 | R | ES | 137ed121 T3ExtCntSig | RES/MTS-137ed121 T3ExtCntSig | (202 786) RES/MTS-137ed121 T3ExtCntSig TTCN-3 extension: Continuous Signal support | 202 786 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; TTCN-3 Language Extensions: Support of interfaces with continuous signals | TTCN-3 extension: Continuous Signal support | Grabowski | 2011-10-04 | TB adoption of WI | 2011-10-04 | Stable draft | 2012-10-31 | 2013-01-31 | 2013-05-13 | 1.2.1 | RES/MTS-137ed121 T3ExtCntSig - TTCN-3 extension: Continuous Signal support
38305 | 446 | R | ES | 138ed121 T3ExtExtTRI | RES/MTS-138ed121 T3ExtExtTRI | (202 789) RES/MTS-138ed121 T3ExtExtTRI TTCN-3 extension: Extended TRI | 202 789 | Methods for Testing and Specification (MTS); The Testing and Test Control Notation version 3; Extension Package: Extended TRI | TTCN-3 extension: Extended TRI | Schieferdecker | 2011-10-04 | TB adoption of WI | 2011-10-04 | Stable draft | 2012-10-31 | 2013-01-31 | 2013-05-13 | 1.2.1 | RES/MTS-138ed121 T3ExtExtTRI - TTCN-3 extension: Extended TRI
39406 | XC | R | TS | 102950-1ed131 T3Conf | RTS/MTS-102950-1ed131 T3Conf | (102 950-1) RTS/MTS-102950-1ed131 T3Conf TTCN-3 tool conformance: ICS | 102 950-1 | Methods for Testing and Specification (MTS); TTCN-3 Conformance Test Suite; Part 1: Implementation Conformance Statement (ICS) | TTCN-3 tool conformance: ICS | Tepelmann | 2012-05-16 | TB adoption of WI | 2012-05-16 | Start of work | 2012-05-16 | 2013-07-19 | 2013-08-30 | 1.3.1 | RTS/MTS-102950-1ed131 T3Conf - TTCN-3 tool conformance: ICS
39407 | XC | R | TS | 102950-2ed131 T3Conf | RTS/MTS-102950-2ed131 T3Conf | (102 950-2) RTS/MTS-102950-2ed131 T3Conf TTCN-3 tool conformance: TSS & TPs | 102 950-2 | Methods for Testing and Specification (MTS); TTCN-3 Conformance Test Suite; Part 2: Test Suite Structure and Test Purposes (TSS&TP) | TTCN-3 tool conformance: TSS & TPs | Tepelmann | 2012-05-16 | TB adoption of WI | 2012-05-16 | Start of work | 2012-05-16 | 2013-07-19 | 2013-08-30 | 1.3.1 | RTS/MTS-102950-2ed131 T3Conf - TTCN-3 tool conformance: TSS & TPs
39408 | XC | R | TS | 102950-3ed131 T3Conf | RTS/MTS-102950-3ed131 T3Conf | (102 950-3) RTS/MTS-102950-3ed131 T3Conf TTCN-3 tool conformance: ATS & IXIT | 102 950-3 | Methods for Testing and Specification (MTS); TTCN-3 Conformance Test Suite; Part 3: Abstract Test Suite (ATS) and Implementation eXtra Information for Testing (IXIT) | TTCN-3 tool conformance: ATS & IXIT | Tepelmann | 2012-05-16 | TB adoption of WI | 2012-05-16 | Start of work | 2012-05-16 | 2013-07-19 | 2013-08-30 | 1.3.1 | RTS/MTS-102950-3ed131 T3Conf - TTCN-3 tool conformance: ATS & IXIT
38239 |  | D | ES | 140_TDL | DES/MTS-140_TDL | () DES/MTS-140_TDL Test Description Language |  | Methods for Testing and Specification (MTS); Model-Based Testing (MBT); Test Description Language | Test Description Language | Ulrich | 2011-10-05 | TB adoption of WI | 2011-10-05 | Stable draft | 2012-05-15 | 2012-10-25 | 2013-02-04 | 1.1.1 | DES/MTS-140_TDL - Test Description Language
38805 |  | D | TR | 101582 SecTestCase | DTR/MTS-101582 SecTestCase | (101 582) DTR/MTS-101582 SecTestCase Security Case Studies | 101 582 | Methods for Testing and Specification (MTS) Security Testing Case Study Experiences | Security Case Studies | Takanen | 2012-01-20 | TB adoption of WI | 2012-01-20 | Start of work | 2012-01-20 | 2013-03-21 | 2013-05-02 | 1.1.1 | DTR/MTS-101582 SecTestCase - Security Case Studies
38804 |  | D | TS | 101583 SecTest_Terms | DTS/MTS-101583 SecTest_Terms | (101 583) DTS/MTS-101583 SecTest_Terms Security Testing Terminology | 101 583 | Methods for Testing and Specification (MTS) Security Testing Basic Terminology | Security Testing Terminology | Takanen | 2012-01-20 | TB adoption of WI | 2012-01-20 | Early draft | 2012-01-25 | 2012-11-18 | 2012-12-30 | 1.1.1 | DTS/MTS-101583 SecTest_Terms - Security Testing Terminology
34139 |  | D | EG | 130 T3SecAssTestMeth | DEG/MTS-00130 T3SecAssTestMeth | () DEG/MTS-00130 T3SecAssTestMeth Security Testing Methodology |  | Methods for Testing and Specification (MTS); Security Testing; A TTCN-3 Based Methodology for Security Assurance Testing | Security Testing Methodology | Cadzow | 2010-05-31 | TB adoption of WI | 2010-05-31 | Early draft | 2012-01-25 | 2012-10-01 | 2013-01-11 | 1.1.1 | DEG/MTS-00130 T3SecAssTestMeth - Security Testing Methodology
38806 |  | D | EG | 201581 SecDesGuideVV | DEG/MTS-201581 SecDesGuideVV | (201 581) DEG/MTS-201581 SecDesGuideVV Security design guide (+ V&V) | 201 581 | Methods for Testing and Specification (MTS) Security design guide enabling test and assurance (V&V) | Security design guide (+ V&V) | Cadzow | 2012-01-20 | Early draft | 2012-03-12 | Stable draft | 2012-12-31 | 2013-03-31 | 2013-07-11 | 1.1.1 | DEG/MTS-201581 SecDesGuideVV - Security design guide (+ V&V)
38837 |  | R | ES | 202553ed211_ExTRA | RES/MTS-202553ed211_ExTRA | (202 553) RES/MTS-202553ed211_ExTRA ExTRA | 202 553 | Methods for Testing and Specification (MTS); Extensible notation for expressing Test Purposes, Requirements and Assertions (ExTRA). | ExTRA | Randall | 2012-01-25 | Early draft | 2012-05-15 | Stable draft | 2012-12-04 | 2013-03-25 | 2013-07-05 | 2.1.1 | RES/MTS-202553ed211_ExTRA - ExTRA
TTCN-3
Ed 4.5.1 8 WIs Approval Jan 2013
TTCN-3
Extensions 6 WIs Approval Jan 2013
MBT 3 WIs
Security 4 WIs
ExTRA (TPLan ) Approval March 2013
TDL Approval End Oct 2012
TTCN-3 tool conformance 3 WIs Approval Jully 2013