|  | ToR STF XG (TC MTS) |
| --- | --- |
|  | Version: 0.3 |
|  | Author: dr. György Réthy – Date:19 October 2012 |
|  | Last updated by: Laurent Vreck- Date: 05 Novemberber 2012 |
|  | page 1 of 10 |

Terms of Reference - Specialist Task Force

STF XG (TC MTS)

TTCN-3 Evolution 2013

Summary information

| Approval status | This is a preliminary proposal from a TC MTS delegate, that must be reviewed and approved by TC MTS, before being submitted for approval by Board#90 (15-Nov-2012) |
| --- | --- |
| Funding | 50 400 € voluntary contribution 20% of total manpower |
| Time scale | Mar 2013 to Dec 2013 |
| Work Items | Deliverables to be produced according to clause 6.3 (WI set to be created) |
| Funding criteria B(12)88_030 | 2, 3 Innovation, applicable in mature domains and new areas 5 Horizontal activities (methodology, quality) |
| Notes from Secretariat | TTCN-3 language is one of the success stories of ETSI but requires a continuous maintenance and extension process to be aligned with the evolution of the technologies on which it is applied. This activity requires very specific competence and cannot be effectively completed without the support of an STF. |

Part I – Reason for proposing the STF

# Rationale

The third generation of the standardised testing language, known as TTCN-3, has intensively been developed by ETSI during the last decade and by today it consists of 14 ETSI standards, altogether around 1300 pages. The language is also endorsed by ITU-T as the Z.16x and Z.17x Recommendation series. By now TTCN-3 is used exceptionally as the formal specification language of standardized test suites and has also become a significantly important testing technology with high deployment at various ETSI member companies or even the major testing technology at some ETSI industrial members. TTCN-3 is also well established and used in other industries like the automotive, medical equipment manufacturing, finance, power transmission and railway systems.

TTCN-3 has an important role in standardization, it is an enabler technology in many areas. Several conformance test standards have been developed and being developed by 3GPP, ETSI TBs INT, ERM, and ITS. 3GPP is using TTCN-3 for UE conformance tests from Rel. 8 and onward to LTE and VoLTE, for IMS call control and supplementary services. Furthermore TB ITS runs projects under the umbrella of the EC ICT Standardisation Work Programme 2010 – 2013. TC ITS test specification projects are going to use TTCN-3 as their choice for the testing language.

Also OMA, the WiMAX Forum and the TETRA Association are using TTCN-3 as the basic specification language for testing.

TTCN-3 fulfills a very important role in the industry The customers of ETSI industrial members require low time to market of the new capabilities and features developed. Due to this, vendors have had introduced new, agile ways of working (WoW). One of the essential technologies required by the agile WoW is automated regression testing and continuous integration (CI). Both technologies rely on the languages and tools enabling automated testing and TTCN-3 is heavily used in agile development at ETSI member companies.

Performance and robustness testing are also of increasing importance. TTCN-3 is also used - in fact, at some ETSI member companies TTCN-3 has a major role - in these areas.

TB MTS is committed to keep the language powerful, up-to-date, well maintained and easy-to-use. A change request (CR) procedure is in place and exploited by the users’ community. 3GPP requires short response times to their TTCN-3 language requirements and defect reports and an updated version of the standards per half year periods. Along with this, a number of extension and maintenance requests arise.

At industrial users, development of new products raises new TTCN-3 language issues and requests for new features. Resolve these requests with short response time are important for user satisfaction and to keep low time-to-market for new capabilities and features being developed.

During the last years several change requests from 3GPP, industrial users and TTCN-3 tool vendors could be resolved and closed in a few-week time period due to the fact that a TTCN-3 language evolution STF was available. In case the STF is delayed, no such timely reaction to user needs can be provided. This would cause user dissatisfaction, and could lead to tool vendor-specific solutions of unresolved issues that over time would lead to backward compatibility problems in the language, in tool implementations and in user test suites.

TTCN-3 language evolution STFs in the last years enabled continuous maintenance and extension of the TTCN-3 standards in the ES 201 873 series and to develop 6 new language extensions for specific use cases and domains. The use of TTCN-3 is increasing today -among others - in model based testing (MBT) area that may need new language extensions.

# Objective

The TTCN-3 language evolution work will comprise the following tasks:

Review and resolve change requests reporting technical defects, or requesting clarifications and new language features for all existing TTCN-3 language standards.

Develop proposals for language extensions requested by 3GPP, OMA, ETSI members and the TTCN-3 community and consent the solution with the contributor(s).

Implement agreed solutions.

Manage the change request (CR) process.

Manage the interim versions of the standard, according to 3GPP needs, and the versions for approval.

Present the TTCN-3 standards’ status and the work of the STF at the conference(s) associated with ETSI TB MTS and at ETSI TB MTS meetings.

# Relation with ETSI strategy and priorities

The TTCN-3 language is a standard enabler as it is THE standard programming language used by all ETSI TBs producing conformance test suites. It is also used for benchmarking test suites, interoperability test suites and interworking test suites. At the same time, TTCN-3 is also fundamentally embedded in the software product development processes at ETSI industrial members, therefore it is also an important instrument for the emerging domains.

ETSI is known and is recognized for its high quality testing standards. Continuous maintenance and evolution of the TTCN-3 standard keep ETSI effective, efficient and recognised as such.

TTCN-3 is being used in other industry sectors besides telecoms (see details at http://www.ttcn-3.org/ApplicationAreas.htm). Maintaining the high quality of the TTCN-3 language standards and securing short response time to user requests helps ETSI to engage in other industry sectors.

# Context of the proposal

## ETSI Members support

The following ETSI Members support the request for this STF (to be confirmed):

| ETSI Member | Supporting delegate | Motivation |
| --- | --- | --- |
| Telefon AB LM Ericsson | Dr. Gyorgy Rethy | TTCN-3 has a major role in our product development, in both the functional and the performance test phases. It is essential for us that new language requirements, requests for clarification and user complaints arising during software development are handled in a short timeframe. |
| Telecom Italia | Giulio Carmelo Maggiore | TTCN-3 promotion and use for increasing the quality of standards and implementations in the network. |
| Institut fur Informatik, Universitaet Goettingen | Dieter Hogrefe | The University of Gottingen is interested in the further development of TTCN-3, because we are involved in several research and development projects where testing with TTCN-3 plays a central role. TTCN-3 can only keep such a central role, if TTCN-3 is continuously maintained and adapted to the new challenges of testing. |
| Fraunhofer FOKUS | Ina Schieferdecker | TTCN-3 plays a central role in our R&D projects and in our training programs. We run e.g. an automotive IOP test stand for Car2X communication based on TTCN-3 and a reference test system for IHE/HL7-based solutions likewise based on TTCN-3. In addition, our automated test generation methods and tools use TTCN-3 as target test specification so that in various respects a continuously maintained and evolving TTCN-3 is essential for our work |
| Testing Technologies | Theofanis Vassiliou-Gioles | For Testing Tech, being one of the main TTCN-3 tool provider the maintenance is crucial for it's success and TTCN-3's success at it's customers and users. Continuous development and enhancement of the language is one of its main USPs |
| OU Elvior | Dr. Andres Kull | Elvior as TTCN-3 tool provider is interested in continues maintenance and development of TTCN-3 standard. Resolving CRs raised by users is essential for our customers and important for spreading the standard over different user domains. |

## Market impact

The user basis of the TTCN-3 language is estimated well above 10 000 users. However, it is a language for automated testing and thus it is widely used in unattended continuous build-and-test software development systems. Therefore its market impact exceeds the above number.

Delay in the language maintenance and development would cause user dissatisfaction, and would lead to tool vendor-specific solutions of unresolved issues that over time would lead to backward compatibility problems in the language, in tool implementations and in user test suites.

## Tasks that cannot be done within the TB and for which the STF support is necessary

The STF support is needed for several reasons:

- Users need short response times to be confident in using the language and to avoid unnecessary delays in SW product development. The meeting schedule of the ETSI technical body does not makes it possible to respond in short time frames. See further information in clause 4.6.

- TTCN-3 is a test-specific programming language; program language development knowledge is not available at users in standardization bodies or industrial members; such knowledge is available at research institutes and universities that are not in the position of financing voluntary contribution to the language maintenance and development.

## Related voluntary activities in the TB

The ETSI Members supporting the creation of the STF are prepared to provide the following voluntary contribution:

Telefon AB LM Ericsson: input in form of TTCN-3 CRs, providing voluntary resource in addition to MWP STF resources, consultation in cases when the STF requests that for CR resolution, participation in Steering Committee, review of documents.

Telecom Italia: participation in Steering Committee.

Institut fuer Informatik, Universitaet Goettingen: input in form of TTCN-3 CRs, providing voluntary resources in addition to MWP STF resources for reviewing the draft documents, participation in TTCN-3 Steering Committee

Fraunhofer FOKUS: Input in form of TTCN-3 CRs, providing voluntary resources in addition to MWP STF resources for reviewing the draft documents, participation in TTCN-3 Steering Committee

Testing Technologies: Input in form of TTCN-3 CRs, providing expert for STF work, consultation in cases when the STF requests that for CR resolution, participation in TTCN-3 Steering Committee

Elvior: Consultation in cases when the STF requests that for CR resolution and participation in TTCN-3 Steering Committee.

## Outcome from previous funded activities in the same domain

TTCN-3 language evolution STFs supporting TB MTS reached the numerical results below during the last 5 years.

| STF | year | total resources days | Including voluntary resources days | No. of revised versions of existing stand’s (core version) | No. of new language extensions | No. of CRs handled |
| --- | --- | --- | --- | --- | --- | --- |
| 430 | 2011 | 94 | 16 | 8 (4.4.1) | 2 (continouos, extTRI) | 106 |
| 393 | 2010 | 78 | 16 | 9 (4.2.1+4.3.1) | 3 (real time & perform., conf. & depl., ATS profor.) | 119 |
| 380 | 2009 | 118 | 24 | 8 (4.2.1) | 2 (advan. param., behav. types ) | 100 |
| 349 | 2008 | 82 | 16 | 10 (3.4.1+4.1.1) | n/a | 135 |
| 337+337V | 2007 | 47 | 26 | 6 (3.4.1) | n/a | 56 |

## Consequences if not agreed

Clause 4.5 contains the numerical results of past TTCN-3 language STFs. However, TB MTS thinks that the existence of the language teams and the communication with users and tool vendors has equal importance than the numerical results.

Experience from the last years shows that quick response to user requests improves efficiency and removes ambiguity both at standardization and in case of industrial users and tool vendors. Without support of the former STFs, TB MTS would not be able to respond in a timely fashion. A few examples from the last years are:

- CR 6088: resolving this CR by STF 433 in a few weeks enabled a user to test an XML-based protocol; before it was possible to handle 3 elements only at a time, if they were unordered, using very complex TTCN-3 code constructs.

- CRs 5847, 5848, 5852, 5853, 5881, 5883, 5904, 5905: when STF160 started to include IMS supplementary services into their scope, several diversities were found in different TTCN-3 tool implementations that raised several CRs. Part-9 of the TTCN-3 standard has been clarified and extended at several places by STF 430 and the interim version v4.3.2 has been provided to 3GPP according to their request (the interim version has been used by STF160 as the baseline for tool vendors).

- CRs 5562, 5553, 5513, 5511, 5510, 5509, 5508, 5507, 5514: several issues for clarification as well as bug reports have been reported in the spring of 2010, in relation to the development of LTE UE conformance test suites by STF 160. All reported CRs has been resolved by STF 393 at its first sessions and in July 2010 the interim version v4.2.2 has been provided to STF 160 that has been used by STF160 in September as the baseline for tool vendors.

Part II - Execution of the work

# Technical Bodies and other Organizations involved

## Leading TB

TB MTS, contact person: Stephan Schulz, TB MTS chairman.

## Other interested ETSI Technical Bodies

All ETSI TBs developing or maintaining conformance and end-to-end test suites or interoperability test specifications also defined in TTCN-3 are receivers of the work done by the proposed STF.

In particular, the STF is in direct communication with 3GPP STF 160 and the technical officer of 3GPP RAN5.

## Other interested Organizations outside ETSI

ITU-T Study Group 17: ITU-T has endorsed the TTCN-3 standards produced by ETSI as ITU-T Recommendations in the Z.16x and Z17x series. TB MTS has an agreement with ITU-T SG17 on a "fast track" endorsement of the TTCN-3 standards to minimize the delay between the ETSI and ITU-T publications.

Other fora, like OMA, Wimax Forum & TETRA Forum are the users of the outcome of the proposed STF.

# Working method/approach

## Organization of the work

The CR resolution process (see MTS(10)0091) has been discussed and agreed by TB MTS. According to this, resolution of each CR comprises the following activities:

Review and technical discussion of the CR (all STF members;

agree technical solution (all STF members);

if no consensus is reached or the issue raises a backward incompatibility problem, consult with tool vendors and users (e.g. STF 160); if no technical agreement can be reached by the consultation, escalate the issue to the TTCN-3 Steering Group of TB MTS;

develop initial proposed draft text for resolution (changes needed in the text of the relevant standard(s)) (dedicated STF member: the CR "responsible");

iterative review and agree the resolution text (CR " responsible " and one or more reviewers);

implement CR resolution in the draft(s) of the standard(s) (editor of the relevant ETSI standard(s)).

According to the established way of working, STF sessions are used for the activities, requiring all STF members, i.e. to resolve CRs, except the last bullet item above. The final implementation of the resolution text, editorial preparation of drafts for TB approval and handling possible comments during the approval and ETSI publication is done on a voluntary basis, out of STF sessions.

For this reason, the work will be organized in sessions located in ETSI or premises of the STF members if that allows for an efficient treatment of the work.

## Base documents

| Document | Title | Current Status | Expected date for stable document |
| --- | --- | --- | --- |
| ETSI ES 201 873-1 V4.5.1 | Part 1: TTCN-3 Core Language | v4.4.1 published | Dec. 2012 |
| ETSI ES 201 873-4 V4.5.1 | Part 4: TTCN-3 Operational Semantics | v4.4.1 published | Dec. 2012 |
| ETSI ES 201 873-5 V4.5.1 | Part 5: TTCN-3 Runtime Interface (TRI) | v4.4.1 published | Dec. 2012 |
| ETSI ES 201 873-6 V4.5.1 | Part 6: TTCN-3 Control Interface (TCI) | v4.4.1 published | Dec. 2012 |
| ETSI ES 201 873-7 V4.5.1 | Part 7: Using ASN.1 with TTCN-3 | v4.4.1 published | Dec. 2012 |
| ETSI ES 201 873-8 V4.5.1 | Part 8: The IDL to TTCN-3 Mapping | v4.4.1 published | Dec. 2012 |
| ETSI ES 201 873-9 V4.5.1 | Part 9: Using XML schema with TTCN-3 | v4.4.1 published | Dec. 2012 |
| ETSI ES 201 873-10 V4.5.1 | Part 10: TTCN-3 Documentation Comment Specification | v4.4.1 published | Dec. 2012 |
| ETSI ES 202 781 V1.2.1 | TTCN-3 Language Extensions: Configuration and Deployment Support | v1.1.1 published | Dec. 2012 |
| ETSI ES 202 782 V1.2.1 | TTCN-3 Language Extensions: TTCN-3 Performance and Real Time Testing | v1.1.1 published | Dec. 2012 |
| ETSI ES 202 784 V1.3.1 | TTCN-3 Language Extensions: Advance Parameterization | V1.2.1 published | Dec. 2012 |
| ETSI ES 202 785 V1.3.1 | TTCN-3 Language Extensions: Behaviour Types | V1.2.1 published | Dec. 2012 |
| ETSI ES 202 786 V1.1.1 | TTCN-3 Language Extensions: Support of interfaces with continuous signals, v1.2.1 | V1.1.1 published | n/a |
| ETSI ES 202 789 V1.1.1 | TTCN-3 Language Extensions: Extended TRI | V1.1.1 published | n/a |

## Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | RES/MTS-00201873-1ed461 | TTCN-3 ed.V4.6.1: Core |
| D2 | RES/MTS-00201873-4 ed461 | TTCN-3 ed.V4.6.1: OS |
| D3 | RES/MTS-00201873-5 ed461 | TTCN-3 ed.V4.6.1: TRI |
| D4 | RES/MTS-00201873-6 ed461 | TTCN-3 ed.V4.6.1: TCI |
| D5 | RES/MTS-00201873-7 ed461 | TTCN-3 ed.V4.6.1: Use of ASN.1 |
| D6 | RES/MTS-00201873-8 ed461 | TTCN-3 ed.V4.6.1: Use of IDL |
| D7 | RES/MTS-00201873-9 ed461 | TTCN-3 ed. V4.6.1: Use of XSD |
| D8 | RES/MTS-00201873-10 ed461 | TTCN-3 ed. V4.6.1: T3doc |
| D9 | RES/MTS-00202781ed131 | TTCN-3 extension: Configuration and Deployment Support ed.V1.3.1 |
| D10 | RES/MTS-00202782ed131 | TTCN-3 extension: Performance and Real Time Testing ed.V1.3.1 |
| D11 | RES/MTS-00202784ed141 | TTCN-3 extension: Advance Parameterization ed.V1.4.1 |
| D12 | RES/MTS-00202785ed141 | TTCN-3 extension: Behaviour Types ed.V1.4.1 |
| D13 | RES/MTS-00202786ed131 | TTCN-3 extension: Support of interfaces with continuous signals ed.V1.3.1Core |
| D14 | RES/MTS-00202789ed131 | TTCN-3 extension: Extended TRI ed.V1.3.1 |

The scope of all work items above is to produce the new versions of the existing standards, containing the changes coming from resolved change requests.

## Deliverables schedule:

The schedule for all deliverables listed in clause 6.3 is the same:

TB adoption of WI 	31-October 2012

Stable Draft 	31-December 2013

Draft for approval 	31-Jan 2014

TB approval 	First MTS meeting at Spring 2014 (MTS#61)

Publication	30-June 2014

## Work plan, time scale and resources

| N | Task / Milestone / Deliverable | From | To | Funded experts (days) | Volunt. experts (days) |
| --- | --- | --- | --- | --- | --- |
| Phase 1 – for all ETSI Work Items above the schedule below is relevant |
| M0 | Start of work |  |  |  |
| T0 | Project management | 31-03-2013 | 31-12-2013 | 2 |  |
| T1 | Task 1 | 31-03-2013 | 31-11-2013 | 80 |  |
| T2 | Task 2 | 01-12-2013 | 31-12-2013 |  | 15 |
| M1 | Progress report to TB MTS#60 | 09-2013 |  | 1 |
| M2 | Final draft for TB approval | 31-01-2014 |  | 1 |
| M3 | TB approval (MTS#61) | TBD by TB MTS |  | 1 |
| M4 | STF Final Report | 31-03-2014 |  | 2 |
| M5 | Publication | 30-06-2014 |  |  |
| Total Phase 1 | 82 | 20 |

## Task and milestone description

Task 1 – Review, discuss, agree technical solution, develop initial draft text proposal, review and agree on proposed text

See the organization of the work in clause 6.1. As the tasks described in 6.1 are executed individually and iteratively for each CR, and in parallel for all CRs being progressed, the progress of the STF work cannot be measured by the status of the individual activities but by the number of resolved CRs. STF progress reports always contain these figures.

Task 2 –Implement CR in drafts of the standards

Milestone 1 – STF mid-year progress report to TB MTS

Milestone one is an STF progress report at the autumn meeting of TB MTS, containing the STF status, i.e. working sessions completed, upcoming working sessions and indicators of resource usage the STF progress (number of resolved CRs, CRs that required consultation with vendors and users, CRs escalated to the Steering Group).

Milestone 2 - STF final progress report to TB MTS

Milestone two is an STF final report at the first MTS meeting following the closing of the STF, containing the STF status, i.e. working sessions completed, upcoming working sessions and indicators of resource usage the STF progress (number of resolved CRs, CRs that required consultation with vendors and users, CRs escalated to the Steering Group).

# Required expertise

Up to 4 experts to ensure the following mix of skills:

Professional skills in the TTCN-3 language and knowing the existing TTCN-3 standards.

At least 1 expert by area with the following skills: ASN.1, IDL, XSD and XML.

At least 1 expert with skills in compiler theory and technology.

At least 1 expert with TTCN-3 tool implementation skills (knowledge of tool APIs).

Skills in testing methods (conformance, interoperability, performance and load etc.) is required.

Additional skills in mobile telecommunication technologies would be appreciated.

The actual number of experts and mix of skills may depend on the actual applications received and will be decided when setting up the STF

Part III:	Financial conditions

# Estimated cost

## Manpower cost

| Description | Working days | Rate €/day | Total cost € |
| --- | --- | --- | --- |
| Contracted experts (remunerated) | 82 | 600 | 49 200 |
| Contracted experts (voluntary) | 20 | 0 | 0 |
| CTI staff from ETSI budget | 0 |  |  |
| CTI staff (voluntary) | 0 |  |  |
| Total manpower cost | 102 |  | 49 200 |

## Travel Costs

| Description | Cost estimate |
| --- | --- |
| Present STF progress report to MTS#60 and final report to MTS#61 (2 travels) | 1 200 |
| Total cost | 1 200 |

## Other Costs

None.

Part IV:	STF performance evaluation criteria

# Key Performance Indicators

Contribution from ETSI Members to STF work

Voluntary work of experts (free of charge or with partial remuneration)

Steering Group meetings (number of participants/duration)

Contribution from other ETSI TBs

Direct contribution of delegates (e.g. number of documents/comments/e-mail)

Contributions received from other ETSI TBs

Contributing the TTCN-3 standards to ITU-T SG17 for endorsement and assisting the endorsement process

Liaison with other stakeholders

- TTCN-3 Change Requests are received in the CR handling tool (Mantis)

- The STF may liaise with 3GPP STF 160 and any other users within or outside ETSI

- TTCN-3 tools implementing newest TTCN-3 features

Quality of deliverables

Approval of deliverables according to schedule

Respect of time scale, with reference to start/end dates in the approved ToR

Quality review by TB

Quality review by ETSI Secretariat

In the course of the activity, the STF Leader will collect the relevant information, as necessary to measure the performance indicators.  The result will be presented in the Final Report.

# Document history

|  | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.1 | 19-Oct-2012 | Dr. György Réthy | draft |  |
| 0.2 | 19-Oct-2012 | A. Berrini |  |  |