## Slide 1: Test Description Language
Work Item DES/MTS-140_TDL – STF work plan
Andreas Ulrich, Siemens AG (Rapporteur) MTS#58, 2013-01-22

## Slide 2: STF XF
New STF on “Design of the Test Description Language (TDL)” approved!
  Intended to do the major work on an upcoming TDL standard
  Done in 2013
STF workplan in based on previously agreed approach as presented at MBTUC 2012

## Slide 3: STF efforts distribution & financials
Task | Description | Efforts [Person days] (contracted + CTI + other)
T0 | Project management (STF lead) | 5 + 0 + 0
T1 | TDL concepts | 62 + 10 + 0
T2 | TDL concrete syntax | 28 + 8 + 0
T3 | TDL semantics | 48 + 0 + 0
T4 | TDL reference implementation | 0 + 0 + 40
T5 | Consolidation of results | 8 + 2 + 0
Total |  | 151 + 20 + 40
151 Pd whereof
121 Pd paid (600€/d)
30 Pd voluntary efforts
Covered travel costs
2 trips to MTS meetings
1 trip to UCAAT 2013

## Slide 4: STF tasks and timeline
T0: Project management
M0
Jan
M1
Mar
M2
Jun
M3
Sep
M4
Oct
M5
Nov
M6
Dec
T1: TDL concepts
T2: TDL concrete syntax
T3: TDL semantics
T4: TDL reference implementation
T5
Consolidation of results

## Slide 5: Milestones
# | Description | Deadline (according to ToR)
M0 | STF start | 23-Jan-2013 (kick-off)
M1 | Early draft for review (concepts only) | 31-Mar-2013
 | MTS#59, Helsinki | May 2013 (t.b.c.)
M2 | Stable draft for review (concepts + early syntax & semantics) | 30-Jun-2013
 | MTS#60 + UCAAT 2013, Paris | Sep 2013 (t.b.c.)
M3 | Final draft for review (concepts + syntax + semantics) | 30-Sep-2013
M4 | Final draft for TB approval (revised version after feedback) | 31-Oct-2013
 | MTS#61 | Jan 2014 (t.b.c.)

## Slide 6: T1: TDL concepts
General
  Single document vs. Multi-part document?
  ToC, scope (can be gradually extended)
    Quick agreement necessary; by 31-Jan-2013?
Description of concepts, i.e. abstract syntax
  Proposal: Eclipse Modeling Framework (EMF) Ecore
    Simpler than OMG’s UML/MOF
    Good tool support
  Is the TDL Ecore model part of the standard?

## Slide 7: T2: TDL concrete syntax
Solicitation of requirements from an end user’s perspective on a TDL concrete syntax
  Involvement of CTI very necessary!
Graphical and/or textual syntax?
  Graphical syntax: How to define? Relation to UML?
  Textual syntax: LR(1) grammar
    Simpler, better tooling
Specification of TDL concrete syntaxes to be part of the standard

## Slide 8: T3: TDL semantics
Clean definition of semantics of TDL concepts
  Preferable and eventually for all TDL concepts
  Different concepts require different approaches
    Behaviour – Time – Data – Structure
Proposal: Translational semantics for TDL behavioural concepts
  Mapping TDL concepts to statecharts (UML/Harel?)
  Possibly easier than using operational semantics
Other parts described informally, i.e. plain text

## Slide 9: T4: TDL reference implementation
Goal
  Provide a proof of concept for TDL (Tasks 1 and 2)
  Provide reasoning on the semantics (Task 3)
Scope of ref. implementation to be agreed, e.g.
  Simple TDL text editor for some core features
  Visualization of the TDL meta-model representation for a given TDL spec
Caveat: Complete voluntary effort!
  Who owns the results from this task?

## Slide 10: T5: Consolidation of results
Preparation of the final draft for MTS approval
  Plan: MTS#61, Jan 2014 (t.b.c.)
Incorporation of feedback from earlier MTS reviews
Consolidation of results from Tasks 1 to 3
Incorporation of findings from Task 4

## Slide 11: TDL
Let’s get started!