## Slide 1: STF 454 “Design of TDL” – Status Report
Last change: 2013-04-13

## Slide 2: Document History
2013-05-13: Input to MTS#59
2013-04-03: In preparation of the 3rd session
2013-03-16: Outcome from Budapest meeting
2013-02-25: Reviewed during SG#2; agenda 2nd session
2013-02-22: Document created

## Slide 3: Report on Sessions/Meetings

## Slide 4: Outcome from 1st Session (week 7)
Goal: Gain common understanding in the team
Discussion of TDL use cases and users of TDL
Clarifying the scope of TDL for
  Conformance (functional) testing
  Interoperability testing
Discussed examples of test specs
  3GPP UE conf tests
  IMS iop tests
Any input to TDL must be given by convincing examples
Walkthrough of TDL feature list (not completed)
  Done: Structure – Interactions – Behavior
  Open: Data – Time – Misc.

## Slide 5: Outcome from 2nd Session (week 10)
Goal: Establishing the foundations of TDL
Closer look at examples
  IMS iop testing, Ericsson IMS, IPv6 iop testing
  3GPP conf testing, OMA conf testing
  Generated tests from MBT tools (other STF)
  HLTD requirements (pre-TDL work)
  Test spec languages CCDL
Consolidation of gathered TDL features
Further discussion on TDL features – with action items
Result and next steps
  Initial feature list mostly completed (can be always extended)
  Further discussions needed, addressed in Action Items

## Slide 6: Outcome from 3rd Session (week 15)
Goal: Laying the foundation of the TDL standard
First and complete walk-through and discussion of the meta-model covering
  Structure of a TDL model
  Packaging concept
  Test architecture
  Behavioural expressions
  Data values
  Time concepts
  Miscellaneous concepts
Fixing the structure of the TDL document

## Slide 7: Follow-up Activities
Preparation of the Early Draft (week 16)
  Main activities
    Setup of structure and ToC of TDL document
    Description of the meta model (abstract syntax)
    Actual writing of the TDL document along the agreed structure
  Presentation proposal submitted to UCAAT 2013
Online meeting in week 21 (planned)
  Discussion of feedback received from MTS and SG
  Discussion of open issues observed by STF experts
  Planning of 2nd period of STF up to milestone B
    Deadline for next version of Stable Draft must be set first (4 weeks before MTS#60)
    2 sessions (a 4 days, outside ETSI) + additional homework

## Slide 8: Final Session Plan, 1st Period
from | to | week | GA |  | FK |  | PM |  | AU |  | MFW |  | CTI |  | Other |  | Notes
21.01 | 25.01 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Prep.meet.
28.01 | 01.02 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
04.02 | 08.02 | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
11.02 | 15.02 | 7 | E | 2,5 | E | 2,5 | E | 2,5 | E | 2,5 | E | 2,5 | E | 2,5 |  |  | S#1: Wed-Thu full days, Fri 1/2 day
18.02 | 22.02 | 8 | H | 1,0 |  |  |  |  |  |  |  |  | E | 1,5 |  |  | 
25.02 | 01.03 | 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
04.03 | 08.03 | 10 | C | 2,5 | C | 2,5 | C | 2,5 | C | 2,5 | H | 2,5 | E | 1,0 |  |  | S#2: Budapest, Wed, Thu, Fri morning
11.03 | 15.03 | 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
18.03 | 22.03 | 12 | H | 1,0 | H | 1,0 | H | 1,0 | H | 1,0 | H | 0,5 | E | 1,0 |  |  | G2M, Wed
25.03 | 29.03 | 13 |  |  |  |  |  |  | H | 2,0 |  |  |  |  |  |  | Easter: 29.3.--1.4.
01.04 | 05.04 | 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
08.04 | 12.04 | 15 | E | 4,0 | E | 4,0 | E | 4,0 | E | 4,0 | E | 4,0 | E | 2,8 |  |  | S#3: ETSI, Tue, Wed, Thu, Fri
15.04 | 19.04 | 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | early draft ready
22.04 | 26.04 | 17 | H | 2,0 | H | 2,0 | H | 2,0 | H | 2,0 |  |  |  |  |  |  | 
29.04 | 03.05 | 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
06.05 | 10.05 | 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
13.05 | 17.05 | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MTS#59, 14.-15.5.
20.05 | 24.05 | 21 | H | 2,0 | H | 2,0 | H | 2,0 | H | 2,0 | H | 0,5 | H | 2,0 |  |  | G2M, Wed, Thu
27.05 | 31.05 | 22 |  |  | H | 1,0 | H | 1,0 | H | 4,0 |  |  | E | 2,0 |  |  | 

## Slide 9: Planning of 2nd STF period

## Slide 10: Covered Parts in TDL Stable Draft
Consolidation of TDL meta-model and achieving consistency
Description of semantics of all MM elements
Worked out concrete syntax
  Suggested: UML-like graphical syntax
  Issue to be clarified
    Is there a possible IP infringement with OMG’s UML when ETSI attempts to design a similar syntax for TDL?

## Slide 11: STF Technical Risks
Risk | Severity | Likelihood | Mitigation
Scope and contents of TDL draft moving or changing due to “green field” development | high | medium | Move insufficiently discussed topics to a follow-up STF on TDLv2.
Validity and consistency of developed concepts (meta-model) cannot be guaranteed | medium | medium | Remove all inconsistent and unfinished elements from the final TDL document; enforce validation activities outside of the STF.
Acceptance of proposed TDL concrete syntax missing by end users | low | medium | Collect feedback from end users and incorporate changes possibly in the current TDL document; otherwise task needs to be handled by a follow-up STF.
Delayed delivery of next draft due to vacation period (draft requested 4 weeks prior to MTS#60) | low | high | Try to distribute work to STF members such that they can work independently from each other.

## Slide 12: Very Tight STF Resources
Hiring of 5 experts opposed to 4 as suggested in ToR dilutes overall resources
  Already 30% of voluntary work
  Initial ramp-up to get all experts on same ground required
  Parallelisation of work difficult to achieve
    Mainly for the analysis and writing part
    But not for the design
In total 174 person days for contracted experts
  75 PD spent in first phase
  Only 99 PD contingency to achieve next milestones B+C

## Slide 13: Additionally Requested Resources
Setup of a development environment for the TDL meta-model
  Currently MM is designed using MS Visio  error-prone activity
  Tool environment ensures higher quality during MM design already, independent from (voluntary) MM validation phase
  Asset remains with ETSI, in opposite to prototype tools from validation phase  reuse for follow-up design activities
  Activity unforeseen in the ToR
Request of 5 additional funded person days for this task

## Slide 14: Session Plan, 2nd Period (Plan)
from | to | week | GA |  | FK |  | PM |  | AU |  | MFW |  | CTI |  | Other |  | Notes
03.06 | 07.06 | 23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
10.06 | 14.06 | 24 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
17.06 | 21.06 | 25 | ? | ? |  |  |  |  |  |  |  |  |  |  |  |  | 
24.06 | 28.06 | 26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
01.07 | 05.07 | 27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
08.07 | 12.07 | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
15.07 | 19.07 | 29 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
22.07 | 26.07 | 30 | C | 4,0 | C | 4,0 | C | 4,0 | C | 4,0 |  |  | E | 2,0 |  |  | S#4
29.07 | 02.08 | 31 | ? | ? |  |  |  |  |  |  |  |  |  |  |  |  | 
05.08 | 09.08 | 32 | ? | ? |  |  |  |  |  |  |  |  |  |  |  |  | 
12.08 | 16.08 | 33 | ? | ? |  |  |  |  |  |  |  |  |  |  |  |  | 
19.08 | 23.08 | 34 | ? | ? |  |  |  |  |  |  |  |  |  |  |  |  | 
26.08 | 30.08 | 35 | C | 4,0 | C | 4,0 | C | 4,0 | C | 4,0 | C | 4,0 | E | 2,0 |  |  | S#5; stable draft ready
02.09 | 06.09 | 36 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
09.09 | 13.09 | 37 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
16.09 | 20.09 | 38 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MTS#60 ???
23.09 | 27.09 | 39 |  |  |  |  |  |  |  |  | ? | ? |  |  |  |  | 
30.09 | 04.10 | 40 |  |  |  |  |  |  |  |  | ? | ? |  |  |  |  | 

## Slide 15: Next Steps
MTS#59 meeting
  Discussion of submitted early draft
  Agreement on STF continuation

## Slide 16: TDL Feature Discussion

## Slide 17: Communication STF – SG
Ensure overall direction of TDL design is OK
Resolve deadlocks in STF internal discussions by providing guidance and advice
Develop a roadmap for TDL
TDL feature list with mapping to TDL use cases
  STF will make proposals
  Feedback expected from SG

## Slide 18: TDL Use Cases
Purpose: Promote TDL features based on their potential usage
UC | Short description | Example
A | TDL for documentation (incl. informal parts) | 3GPP test specs
B | TDL for generation of tests that can be made executable (i.e. all parts are formal) | Automatic mapping of a TDL spec to partial TTCN-3 code
C | TDL for representation of generated tests (i.e. output from MBT tools) | Test cases generated from system models
D | TDL for representation of test logs | Test execution log of a TTCN-3 tool
E | TDL for test generation (i.e. input to MBT tools) | Test models as activity diagrams
F | TDL for performance testing | On-the-fly testing from a TDL spec
G | TDL for interoperability testing | Use case models, from which tests are derived
Focus in
early draft

## Slide 19: Internal TDL Feature Discussion
For use in STF, communication with SG
Proposed structure (template)
  TDL feature name
  Covered TDL use cases
  Motivation
  Description (abstract syntax, meta-model)
  Semantics
  Proposed textual concrete syntax
  Proposed graphical concrete syntax
  Examples of use

## Slide 20: TDL Feature Description in Standard
Structure of TDL feature description
  TDL feature name (title of sub-clause)
  Overview (covered in early draft)
    Free description of the feature
  Abstract syntax
    Representation of the feature and its elements in the meta-model
  Semantics
    Preferably formal description of the semantics of the feature
  Constraints
    Constraints on the feature that can be statically analyzed
  Classifier description
    Description of all elements contained in the meta-classes
Note 1: Concrete syntax moved to annex!

## Slide 21: General Design Guidelines
Global interaction flow
  Interaction flow of a test description is totally ordered, unless flow operators are used to express explicitly partial ordering between interactions
Global time
  TDL assumes the existence of a discrete global clock that is used to label all tester/SUT interactions with a global timestamp
Global data
  Data in tester/SUT interactions is globally visible within an interaction flow

## Slide 22: TDL Features
Features documented in “tdl_features (copy).xlsx” on docbox
  https://docbox.etsi.org/STF/STF454_MTS_TDL/Public/tdl_features (copy).xlsx
Latest TDL standard document on docbox
  https://docbox.etsi.org/STF/STF454_MTS_TDL/Public/ETSI_ES_TDL.pdf
Demonstration of (possible) graphical TDL concrete syntax
  https://docbox.etsi.org/STF/STF454_MTS_TDL/Public/STF454-TDL-Overview.pptx