|  | STF 476 – Progress Report for ETSI |
| --- | --- |
|  | Presented to ETSI meeting | Author: | Philip Makedonski |
|  | MTS#62 | Munich | Date: | 28-Apr-2014 |
|  | 14-May-2014 | 15-May-2014 | Version | 1.0 |
|  | Doc ref |  | page 1 of 2 |

| STF | 476 |  | STF leader | Philip Makedonski |
| --- | --- | --- | --- | --- |
| TB/WG | MTS |  | TB responsible | Stephan Schulz |
|  |  |  | STF Assistant | Elodie Rouveroux |

| STF title: | TDL Adaptation to Users (Phase 2) |
| --- | --- |

| Milestone | A |  | Status | Covers the period until (cut-off date) | 15-May-2014 |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Template |  |  |
| Objective | Progress Report#1 approved by MTS#62 plenary (14-15 May 2014); including early draft of Parts 1 and 2, analysis report of ETSI need for textual syntax and work plan for the continuation of the STF. The draft documents will be uploaded by the STF Leader on the MTS contributions area of the ETSI Portal before 1 May 2014. |
| Achieved | yes |  |
| Remarks | Submitted on 30-Apr-2014 |

Achieved dates

| Template | Draft report | TB approval | ETSI approval | Sent to EC | EC approval |
| --- | --- | --- | --- | --- | --- |
| 16-Apr-2014 | 30-Apr-2014 |  |  |  |  |

# Executive summary

- This progress report covers the work of STF 476 on reaching Milestone A, done in the period between 15-Feb-2014 and 01-May-2014. This period concludes the submission of the completed deliverables defined for Milestone A.

- The work was done during two working sessions, accompanied by coordinated homework among the experts and two technical discussions with the established steering group, which provided technical guidance.

- No changes to the STF work plan, resource requirements, and STF team are proposed at this point. An additional expert will join the STF in May-2014, as planned in the preparatory meeting.

- The STF members have submitted a proposal for a tutorial at UCAAT 2014 to promote and communicate the work of the STF.

# Introduction

This progress report covers the work of STF 476 on Milestone A, done in the period between 15-Feb-2014 and 01-May-2014. This period concludes the submission of the deliverables defined for Milestone A. The work was done primarily during two working sessions at ETSI, accompanied by coordinated homework among the experts and two technical discussions with the established steering group.

# Contractual milestone

The ToR outlines the scope of Milestone 1 (A), comprising the following deliverables:

- Early draft on Part 1: TDL meta-model and semantics that addresses all needed extensions w.r.t. automation;

- Early draft on Part 2: TDL graphical syntax that covers a majority of meta-model elements;

- Analysis report on the ETSI’s needs for a TDL textual syntax.

All requested deliverables have been uploaded in the MTS contributions area of the ETSI portal on 30-Apr-2014. Based on discussions with the steering group, the scope of the early draft of Part 1 has been refined to include high priority features such as a mechanism for “sub-configurations” and refined “data handling”. Based on discussions with the steering group the scope of the early draft of Part 2 has been refined to including proposed graphical syntax symbols for the majority of non-abstract meta-model elements, with informal descriptions of selected graphical symbols. The analysis report was prepared in close collaboration with CTI, making sure all relevant concerns were taken into consideration.

# Progress of the work

The work plan comprises three milestones, primarily prepared during six working sessions, with individual and coordinated homework in between. Two working sessions have been allocated for each milestone – one for reviewing feedback on the previous milestone and starting preparation of the next milestone, and one for finalizing the next milestone. Tasks for homework are allocated at the end of each session, progress on which is discussed during coordinated remote homework and results are reviewed at the beginning of the next session.

During the work on the first milestone, comprising the first two working sessions and associated homework, progress on the following activities has been achieved:

Task 0 – Project Management

- All STF working sessions have been planned and allocated. Session 3 provisionally located at ETSI has been moved to Berlin and upgraded to five days.

- Progress report for Milestone A (this document) and interim progress reports for the steering group have been prepared and submitted in a timely manner.

- Participation in steering group and MTS meetings has been arranged.

- Proposal for a tutorial at UCAAT has been prepared and submitted.

Task 1 – Extended TDL meta-model

- Core concepts related to variables have been outlined.

- Refinement of action references has been outlined so that actions can define formal parameters which shall be assigned to actual parameters in action references.

- A concept for “sub-configurations” has been outlined and implemented allowing more flexible referencing of test descriptions that use test configurations comprising a sub-part of the test configuration of the referencing test description.

- Feedback on the meta-model as well as the need for further changes based on the ongoing work on the graphical syntax has been collected and evaluated.

Task 2 – TDL graphical syntax

- Existing approaches for graphical syntax definitions have been analyzed and considered for the specification of the TDL graphical syntax

- Initial requirements from end users have been collected and incorporated in the early draft as proposed graphical syntax symbols for the majority of the concrete meta-model elements

- Means for the prototypical validation of the proposed graphical syntax symbols and their mapping have been evaluated

Task 3 – TDL exchange format

- The work on this task begins after the first milestone. No progress on this task up to this point.

Task 4 – Analysis TDL textual syntax

- End-user requirements for a textual and tabular (or so-called “textual in tabular”) notation have been discussed with CTI as the central interface to different TBs

- The desired notation, its primary role and uses, and potential considerations related to its specification and mapping to TDL have been evaluated and discussed with CTI

- A report summarizing the findings from the above activities has been prepared and submitted to MTS#62 for a decision on the need for further activities related to this task.

# Assessment of technical risk, difficulties encountered/expected, unresolved issues

The progress of the work of the STF may be negatively affected by the following risks:

Task (inter-) dependencies may create bottlenecks for the work of the STF

Due to the parallel and distributed work on multiple deliverables across multiple experts, dependencies among individual activities may create hindrances for the progress of the STF.

Severity: Medium, Likelihood: Low

Mitigation strategies:

- Limit dependencies between activities where possible.

- Make dependencies explicit where these are inevitable in order to raise awareness, as well as monitor and control potential implications.

- Ensure communication and collaboration among experts working on inter-dependent tasks.

- Reassign experts where applicable in order to accelerate progress of delayed activities and eliminate bottlenecks in a timely manner.

Misunderstandings and communication barriers hinder progress

Misunderstandings and communication issues during discussions and individual work may negatively impact the progress of the STF work.

Severity: Medium, Likelihood: Medium

Mitigation strategies:

- Moderation and awareness – recognize and differentiate between misunderstandings, where clarification is needed, and technical disagreements, where different solutions are proposed.

- Emphasis on facts, substantiated and illustrated with examples, and written input and output of discussions, which describes ideas, problems, and solutions in sufficient detail, and can be referenced to in subsequent discussions.

- Identify fundamental differences in alternative proposals and their impact in order to establish a baseline for discussions, rather focusing discussions on superficial and non-essential differences.

- Communicate and resolve persistent issues and disagreements with the help of the steering group.

Misalignment of expectations towards the STF and the output of the STF

Due to potentially unrealistic or misaligned expectations towards the STF from different stakeholders, the output of the STF may not be able to meet these expectations.

Severity: Medium, Likelihood: Medium

Mitigation strategies:

- A steering group has been established to provide technical guidance and mediate technical disagreements.

- Frequent reporting and technical discussions with the steering group and TC MTS ensure that the work of the STF is aligned with its expectations. The STF has an opportunity to communicate any expectations that are perceived to be unrealistic back to the steering group and TC MTS.

- Concrete examples are prepared to support technical discussions and ensure alignment of expectations.

# Proposed changes in the STF work plan

There are no changes in the STF work plan up to this point.

# Resources requirements

There are no changes in the STF resource requirements up to this point. A contingency of 93 working days after the initial allocation and contracts established during the preparatory meeting will be allocated by May-2014 based on the progress of the STF and the feedback on Milestone A at MTS#62, as agreed during the preparatory meeting.

Depending on the decision of TC MTS based on the analysis report from Task 4, additional resources for this STF may be allocated to cover the extended scope of the STF or a new STF may be initiated to pursue further activities related to Task 4.

# Changes in the STF Team

There are no foreseen changes in the STF team. An additional expert will join the team in May. This has been agreed upon and planned during the preparatory meeting.

# Meetings/events attended on behalf of the STF

Experts from the STF attended MTS#61 and reported on the results from STF 454, which serve as the basis for the work of STF 476. The experts also participated in preparatory discussions for this STF and the alignment of the work of this STF to other activities within TC MTS.

Achievements of the STF up to Milestone A, as well as the planning for Milestone B will be presented discussed at MTS#62 and an associated Technical Session in Munich on 14/15-May-2014. Philip Makedonski (STF leader) and Andreas Ulrich (host) will attend in person, while Martti Käärik and Gusztav Adamis will attend remotely.

Two remote interim technical discussions with the steering group were attended by the STF members, where progress of the STF and outstanding questions and clarifications were discussed and aligned with the steering group.

# Meetings/events planned to be attended

| Date | Place | TB/Orga | Event description | Reason to attend | Expert(s) |
| --- | --- | --- | --- | --- | --- |
| 14/15-May-2014 | Munich | MTS | MTS#62, Technical session on TDL | Present and discuss achievements up to Milestone A, agree on planning for Milestone B | Philip Makedonski (in person) Andreas Ulrich (in person) |
| Sep/Oct-2014 | TBA | MTS | MTS#63 | Present and discuss achievements up to Milestone B, agree on planning for Milestone C | TBA |
| Jan-2015 | TBA | MTS | MTS#64 | Present and discuss achievements up to Milestone C, agree on planning for Phase 3 | TBA |
| 16-18-Sep-2014 | Munich | MTS, All4Tec, GTB | User Conference on Advanced Automated Testing (UCAAT) and associated events. | Present a tutorial on TDL if submission is accepted, present TDL at MTS special session. | TBA |

# STF communications, presentations, promotion, inside and outside ETSI, WEB pages etc

The following activities related to the communication, presentation, and promotion of the work of the STF have been considered, planned, and/or performed:

- The STF has submitted a proposal for a tutorial session on TDL at the UCAAT 2014. During an associated special session on MTS activities, a brief introduction to TDL is also planned.

- Ongoing dissemination activities from STF members from research institutions include raising awareness and promoting TDL on their respective websites and within teaching and research activities.

- A website for the STF will be published shortly upon agreement within the STF and TC MTS.

- A dedicated project has been created on the online issue reporting portal for ETSI (“ETSI’s Bug Tracker”) where change requests for TDL can be submitted and managed in an open and transparent manner.

# Technical advice required from the reference Technical Body

A steering group has been assembled by TC MTS to provide technical guidance and expert advice during technical sessions with the STF. Up to this point, the steering group has been supporting the work of the STF very well, with technical sessions arranged between working sessions of the STF to discuss the progress of the STF and any open questions or unresolved disagreements.

# Status of the deliverables

Milestone A is comprised of the following deliverables.

- Early draft for Part 1 “Test Description Language; Meta-Model and Semantics” including changes to the common concepts, the meta-model, and the semantics related to selected activities targeted for the early draft (sub-configurations). Available at:	 
ftp://docbox.etsi.org:21/STF/STF476_MTS_TDL2/Public/es_203119-1v010201_earlyDraft.doc

- Early draft for Part 2 “Test Description Language; Graphical Syntax” including graphical concrete syntax for end users with graphical symbols for the majority of concrete meta-model elements, as well as detailed descriptions for selected meta-model elements targeted for the early draft. Available at:	
ftp://docbox.etsi.org:21/STF/STF476_MTS_TDL2/Public/es_203119-2v010101_earlyDraft.doc

- Analysis report on Task 4 “A concrete Syntax for ETSI’s Needs” including analysis of relevant use cases, design considerations, a recommendation, and proposed approach on how to proceed with potential future activities in this direction. Available at: 	
ftp://docbox.etsi.org:21/STF/STF476_MTS_TDL2/Public/STF%20476%20-%20Task%204%20Report.pdf

# Next report

The next report is scheduled for 12-Sep-2014, together with the deliverables for Milestone B for MTS#63.

# Any other business

None.