|  | ToR STF ZM (TC MTS) |
| --- | --- |
|  | Version: 0.1 |
|  | Author: Andras Kovacs – Date: 8 Oct 2014 |
|  | page 1 of 8 |

Terms of Reference for Specialist Task Force STF ZM

(TC MTS) ”Extension of Conformance tests for TTCN-3 tools”

Summary information

| Approval status | Approved by MTS#63 (1-2 Oct) MTS(14)63_012 |
| --- | --- |
| Funding overview | Budget: 41 800 € ETSI FWP Contracted experts: up to 85 working days, including voluntary contribution (20% of total). Manpower cost: up to 68 days @ 600 €/day = 40 800 € + 17 days free of charge Travel cost up to 1 000 €. |
| Time scale | Dec 2014 to end July 2015 |
| Work Items to be approved | RTS/MTS-00132-1ed151 TS 102 950-1 ed151 RTS/MTS-00132-2ed151 TS 102 950-2 ed151 RTS/MTS-00132-3ed151 TS 102 950-3 ed151 |
| Notes from Secretariat | This is a continued activity to ensure that TTCN-3 test suites remain compatible with multiple TTCN-3 tools. Strong support from 3GPP, ITS, INT/IMS stakeholders. Presentation of previous work on TTCN tools by TC MTS to Board#91 BOARD(13)91_036. Use TTCN methodology. Work will be done under close CTI overview. STF will be started after base documents listed in §3.13 are published. |

Part I – Reason for proposing the STF

- Rationale

  - Background information

Over the last decade TTCN-3 has become a significantly important testing technology with very high deployment at various ETSI member companies as well as other organizations internationally. With its established usage in 3GPP, ETSI, OMA and the AUTOSAR (a consortium of car makers and OEM suppliers), its role in standardization is further growing. 3GPP is using TTCN-3 as the test specification language e.g. for IMS call control testing from Rel. 8 onward. TC INT is using TTCN-3 for automating IMS core network interoperability testing. TC ITS is using TTCN-3 to specify all its test suites under the EC mandate M/453.

Significant number of TTCN-3 test toolsets are available on the market (at least 7 commercial tools and 2 internal tools of industrial ETSI members) that also indicate the high interest and use of the language. Due to serving several domains and application areas, the TTCN-3 standards which provide the foundation for this testing technology, are quite complex and encompass multiple hundreds of pages. Part 1 of the TTCN-3 series, the TTCN-3 core language, alone is estimated to contain on the order of 5,000 requirements. Over the past 10 years the TTCN-3 community has repeatedly requested by for some kind of assurance that tools conform to TTCN-3 standards. A standardized testing language such as TTCN-3 should lead by example, i.e., tools that check conformance of systems to standards should also be tested for their compliance to standard.

  - Organization in phases

Based on the above requests, TC MTS developed a first conformance test suite in STF 409 which lead to the discovery of 19 issues or ambiguities in the TTCN-3 standard version v4.2.1 when covering about 1/3 of the clauses in the main standard with some tests. The test suite was extended, re-based to TTCN-3 v4.5.1 by STF433, STF454, and STF470 and a new coverage analysis approach, reaching 100 % coverage of the core language clauses, and synchronized with the up-to-date revision. TTCN-3 is, however, a living language. A new version is published by ETSI each year; the latest published version is v4.6.1.

TC MTS’s target with this STF request is to re-synchronize the development of the TTCN3 language and its conformance test suite, considering the changes being introduced in v4.7.1, and to validate the extensions of the conformance test suite over preliminary implementations in multiple TTCN-3 tools. This way the updated core language standard can be published together with the updated conformance test suite. This would support that TTCN-3 test suites will also in the future compile on multiple TTCN-3 tools, by removing possible misunderstandings and ambiguities when implementing a new language feature in test tools.

- Objective

The purpose of this work is to update the TTCN-3 tool conformance test specification to the latest version under development of the TTCN-3 language, thus re-synchronizing language development and the test suite development and to maintain full clause coverage of the core language. More concretely, to revise and update the ICS, test purposes and the TTCN-3 tests. See details in clause 1.2.1.

- Relation with ETSI strategy and priorities

This STF directly supports the ETSI strategic objectives 3rd Generation partnership, "Interoperability and Testing" and “Intelligent Transport Systems (ITS)”.

Market impact, benefits to be gained

Strategic importance behind the work: the decisions by 3GPP RAN5 to move to TTCN-3 from Release 8 onwards, TC TISPAN to develop NGN test suites, TC INT to develop core IMS network test suites, and TC ITS to develop conformance and interoperability test suites in TTCN-3, all required the availability of a number of different, high quality, commercial TTCN-3 tools and well as the ability for ETSI members to assess that these TTCN-3 tools really comply to the ETSI TTCN-3 standards.

  - Interest of ETSI Members and other stakeholders

Today as 3GPP, INT, and ITS test teams have started to use TTCN-3 as their conformance, interoperability and benchmarking test suites development language, the biggest potential stakeholder is the mobile telecommunication and intelligent transport systems community: operators, network and user equipment manufacturers, chipset and ITS infrastructure vendors, automotive companies, and test equipment manufacturers.

  - Relation with other activities within ETSI and/or related organizations

TTCN-3 is THE standard programming language used by all ETSI TCs producing conformance test suites. It is also used for benchmarking test suites, interoperability test suites and interworking test suites.

  - Priority within the TC

This STF proposal has a HIGH priority in order to support further growth of TTCN-3 in 3GPP, ETSI, OMA, AUTOSAR and other bodies and to response to user requirements in a timely fashion.

- Context of the proposal

  - ETSI Members support

The following ETSI Members support the creation of an STF to produce the deliverables listed in §3.14:

| ETSI member | Name | Role | Motivation |
| --- | --- | --- | --- |
| Telefon AB LM Ericsson | Dr. Gyorgy Rethy | Ericsson Test Competence Centre, Product Manager | TTCN-3 is extensively used and plays a strategic role in all phases of product development. |
| Institut fuer Informatik, Universitaet Goettingen | Dieter Hogrefe |  | The University of Goettingen is interested in the further development of TTCN-3, because we are involved in several research and development projects where testing with TTCN-3 plays a central role. |
| Fraunhofer FOKUS | Ina Schieferdecker | Competence Centre on Modelling and Testing, Director | TTCN-3 plays a central role in our R&D projects and in our training programs, so that TTCN-3 tools compliance to the standard and their interoperability is important to us. |
| Conformiq | Stephan Schulz | CTO | TTCN-3 plays a central role as an output format for our tool in our commercial projects and in our training programs. TTCN-3 tool independence is for us a key asset of TTCN-3 |
| Testing Technologies | Theofanis Vassiliou-Gioles | CEO | Testing Technologies promotes TTCN-3 since the very beginning 10 years ago with tools and services. From end-users we understand that the compatibility of TTCN-3 tools applied is crucial for the further deployment of TTCN-3, at companies and at standardisation bodies and for gremias. |
| Elvior | Andres Kull | CRO | Elvior as TTCN-3 tool vendor is interested in evolving of the language. It is important that different tool vendors interpret all aspects of TTCN-3 language in a similar way, output of this STF will help to achive this target. |
| Broadbit | Andras Kovacs | SENIOR ITS EXPERT | Broadbit is a TTCN-3 tool and service provider and supports this activity |

  - Market impact

The common motivation of the supporting organizations is to increase the overall use of TTCN-3 and respond to user community duly and timely.

  - Tasks that cannot be done within the TB and for which the STF support is necessary

Earlier attempts by TC MTS to create an official test suite based on voluntary contributions, e.g. by collecting regression tests from tool vendors, have not lead to a fruitful output. There are many different factors and reasons. Tool vendors consider regression tests maybe as their most important asset over their competition. Also differences in regression test approaches, structures of test suites and granularity of test cases have had disallowed creating a meaningful test suite. The excellent results of STF 409, STF 433, STF 454, and STF 470 have shown that the STF model works for this purpose very well.

Also, the nature of the work (analysis of programming languages, interworking of different notation languages, coding technologies, test scripting) requires mixed and specialized expertise that is not common and partly available by delegates attending ETSI meetings.

  - Related voluntary activities in the TB

The ETSI Members supporting the creation of the STF are prepared to provide the following voluntary contribution:

- Telefon AB LM Ericsson: participation in Steering Committee, review of documents.

- Telecom Italia: participation in Steering Committee.

- Universitaet Goettingen: input in form of TTCN-3 CRs, providing voluntary resources in addition to STF resources for reviewing the draft documents, participation in TTCN-3 steering committee

- Fraunhofer FOKUS: reviewing the draft documents, participation in TTCN-3 steering committee

- Conformiq: reviewing the draft documents, participation in Steering Committee.

- Testing Technologies: participation in Steering Committee, provision of TTCN-3 tool for validation & voluntary resource for STF work.

- Elvior: participation in Steering Committee, provision of TTCN-3 tool for validation & voluntary resource for STF work.

  - Outcome from previous funded activities in the same domain

TC MTS developed a first conformance test suite in STF 409, covering about 1/3 of the clauses in the main standard with some tests. The test suite was extended, re-based to TTCN-3 v4.5.1 by STF433, STF454, and STF470 and a new coverage analysis approach, reaching 100 % coverage of the core language clauses, and synchronized with the up-to-date revision. TTCN-3 is, however, a living language. A new version is published by ETSI each year; the latest published version is v4.6.1.

  - Consequences if not agreed

The further adoption of TTCN-3 at ETSI, 3GPP, OMA, and the AUTOSAR consortium are put at risk, if this continuation work is not done. As tool support of the required features is dependent on the standardization of the features, not agreeing this proposal would have an unfavourable effect on the above domains. Also, further uptake and usefulness of the language will be adversely affected, thus jeopardizing ETSI’s significant contribution to this work.

Part II - Execution of the work

- Technical Bodies and other Organizations involved

  - Leading TB

TC MTS.

  - Other interested ETSI Technical Bodies

3GPP LTE, TC BRAN, TC ITS, TC INT, TC ERM: these TCs use TTCN-3 for test suite development and their members are impacted by TTCN-3 tools’ compatibility.

  - Other interested Organizations outside ETSI

OMA is using TTCN-3 to develop and maintain conformance test suites.

ISO/IEC 15118 committee is using TTCN-3 to develop and maintain conformance test suites.

- Working method/approach

  - Organization of the work

The goal of this STF is the updating and extension of conformance test suite for TTCN-3 tools. Therefore the work is organized around the usual stages of conformance test suite development, i.e. delivery of an early draft, stable draft, and final draft that are defined as milestones M1–M4 below. The STF consists of just one single phase of development.

Once draft versions of the conformance test suite for TTCN-3 tools become available, they will be sent out to ETSI MTS and tool vendors outside of ETSI for review and feedback. Since there are two milestones M1 and M2 foreseen to solicit feedback, there is sufficient room for delivering an enhanced and improved conformance test suite for TTCN-3 tools that fits the needs of tool vendors.

The existing conformance test suite for TTCN-3 tools will be enhanced by updating and extending it, in order to bring it in line with V4.7.1 of the core language standard.

Effort estimation for the various tasks of the STF is centered around the number of sessions that can be organized within the timeframe of this STF and the number of experts involved in each task:

- STF leader performs Tasks 1, 4, 5, and 8

- Other tasks are equally shared among involved experts, with Tasks 2 and 3 comprising the main effort in this STF.

MTS Committee has established a TTCN-3 Steering Group for the direct steering of STFs for TTCN-3 evolution and conformance tests that will closely follow the progress of this STF. STF outputs will also be reviewed and approved by TC MTS. It is very likely that some active TC MTS members will apply to be involved in this STF and will hence be in direct contact with TC MTS via the usual communication means (MTS_GEN mailing list, MTS face-to-face meetings, conference calls). Support from the CTI department will also be requested and is seen as being vital to the success of this work.

  - Base documents

| Document | Title | Current Status | Expected date for stable document |
| --- | --- | --- | --- |
| ETSI ES 201 873-1 V4.7.1 | Methods for Testing and Specification (MTS);The Testing and Test Control Notation version 3;Part 1: TTCN-3 Core Language | Under development |  |
| ETSI ES 201 873-4 V4.7.1 | Methods for Testing and Specification (MTS);The Testing and Test Control Notation version 3; Part 4: TTCN-3 Operational Semantics | Under development |  |
| ETSI ES 201 873-10 V4.7.1 | Methods for Testing and Specification (MTS);The Testing and Test Control Notation version 3; Part 10: TTCN-3 Documentation Comment Specification | Under development |  |
| ETSI TS 102 950-1 V1.4.1 | Methods for Testing and Specification (MTS);TTCN-3 Conformance Test Suite;Part 1: Implementation Conformance Statement (ICS) | Published |  |
| ETSI TS 102 950-2 V1.4.1 | Methods for Testing and Specification (MTS);TTCN-3 Conformance Test Suite; Part 2: Test Suite Structure and Test Purposes (TSS&TP) | Published |  |
| ETSI TS 102 950-3 V1.4.1 | Methods for Testing and Specification (MTS);TTCN-3 Conformance Test Suite; Part 3: Abstract Test Suite (ATS) and Implementation eXtra Information for Testing (IXIT) | Published |  |

  - Deliverables

| Deliv. | Work Item code Standard number | Working title Scope |
| --- | --- | --- |
| D1 | RTS/MTS-00132-1ed151 TS 102 950-1 ed151 | TTCN-3 Conformance Test Suite Part 1 : Implementation Conformance Statement |
| D2 | RTS/MTS-00132-2ed151 TS 102 950-2 ed151 | TTCN-3 Conformance Test Suite Part 2: Test Suite Structure & Test Purposes |
| D3 | RTS/MTS-00132-3ed151 | TTCN-3 Conformance Test Suite Part 3: Abstract Test Suite & IXIT |

  - Deliverables schedule:

The general timeline of deliverables produced in this STF is defined as follows:

M1: Work Item adoption by TB -	October 2014

M2: Stable Draft -	April 2015

M3: Draft for approval -	July 2015

M4: TB approval (AbC) -	August 2015

M5: Publication of results -	August 2015

  - Work plan, time scale and resources

| No. | Task / Milestone / Deliverable | From | To | Funded experts (days) | CTI experts (days) |
| --- | --- | --- | --- | --- | --- |
| M1 | Start of work | December 2014 |  |  |
|  | Task 1 | 01-Dec-2014 | 31-Mar-2015 | 1 | 0.25 |
|  | Task 2 | 01-Dec-2014 | 31-Mar-2015 | 45 | 11.25 |
|  | Task 3 | 01-Dec-2014 | 31-Mar-2015 | 4 | 1 |
| M2 | Stable Draft | April 2015 |  |  |
|  | Task 4 | 01-Apr-2015 | 30-Jun-2015 | 3 |  |
|  | Task 5 | 01-Apr-2015 | 30-Jun-2015 | 2 | 0.5 |
|  | Task 6 | 01-Apr-2015 | 30-Jun-2015 | 7 | 1.75 |
| M3 | Draft for approval | July 2015 |  |  |
|  | Task 7 | 01-Jul-2015 | 31-Jul-2015 | 2 | 0.5 |
| M4 | TB approval (AbC) | August 2015 |  |  |
|  | Task 8 | 01-Aug-2015 | 31-Aug-2015 | 4 | 1 |
| M5 | Publication of results | August 2015 |  |  |
| Total | 68 | 17 |

  - Task and milestone description

- Task 1: Listing of changes between the V4.6.1 and V4.7.1 revisions of the TTCN-3 core standard, and corresponding assignment of Task 2 -3 work among STF experts

- Task 2: Extension of the TTCN-3 conformance test suite by writing tests for the new/changes language features

- Task 3: Extension of the TTCN-3 conformance test execution tools, as needed, to support changed language features relating to external functions, pre-processing, ports ...etc.

- Task 4: Validation of the extended TTCN-3 conformance test suite over at least two TTCN-3 compilers

- Task 5: Discussion of validation results with involved tool vendors, assignment of TTCN-3 conformance test suite refinement tasks as needed.

- Task 6: Correction and refinement of the extended TTCN-3 conformance test suite, based on the validation feedback.

- Task 7: Raising of CRs to the TTCN-3 developers over the observed language issues/ambiguities

- Task 8: Presentation of results to TC MTS, documentation of the TSS/TP and Pixit structure of the resulting test suite, submission of results to corresponding work items, write-up of STF work reports.

- Required expertise

Number of experts required: 2-3, with the following expertise:

- Expert skills in TTCN-3.

- Experience in conformance test development.

- Additional skills in mobile telecommunication technologies would be appreciated.

- Support from the CTI will be vital to the success of this work.

Part III:	Financial conditions

- Estimated cost

  - Manpower cost

| Description | Working days | Rate €/day | Total cost € |
| --- | --- | --- | --- |
| Contracted experts (remunerated) | 68 | 600 | 40800 |
| Contracted experts (voluntary, 20% from total) | 17 | 0 | 0 |
| CTI staff (voluntary) | 0 | 0 | 0 |
| Total manpower cost | 85 |  | 40800 |

  - Travel Costs

| Description | Cost estimate |
| --- | --- |
| Attending MTS plenary meeting to present STF results for approval (1 travel within Europe) | €1000 |
| Total cost | €1000 |

  - Other Costs

– none –

Part IV:	STF performance evaluation criteria

- Key Performance Indicators

The STF shall base its work on the yet unpublished TTCN-3 standard. In the cases when clarification of the standards is needed, the STF shall coordinate with STF 478 or its continuation STF. Validation of the developed test specification – in particular the TTCN-3 code – is considered to be a task performed by the STF but is also expected to be assisted and supported by MTS TTCN-3 tool vendor members including but not limited to Elvior, Testing Technologies, Tool vendors will provide licenses, required tool versions, and tool usage support to the STF members as necessary. The results will be presented in the Final Report. The following indicators will be used:

Contribution from the ETSI Members

- Voluntary work of experts provided free of charge in form of CRs being provided and CR resolutions being reviewed

- Steering Group meetings

- Provision of TTCN-3 tools & support

- Contribution from other ETSI TBs

Interests of ETSI and non-ETSI stakeholders

- Feedback from TTCN-3 tool vendors

- Number of tools compliant to test suite

Quality of the STF results

- Approval of deliverables from the Reference TB according to schedule

- Respect of time scale, with reference to start/end dates in the approved ToR

- Application of the ETSI drafting rules

- Document history

| Version | Date | Author | Status | Comments |
| --- | --- | --- | --- | --- |
| 0.1 | 08-Sep-14 | Kovacs | Draft | Approved by MTS#63 |
| 0.2 | 08-Oct-14 | Kovacs | Draft | Added additional information according to the new template |

# Comments

Philip Makedonski 10/1/14, 2:21 AM

Needs to be updated