|  | STF 475 – Progress Report for ETSI |
| --- | --- |
|  | Presented to ETSI meeting | Author: | Nikolay Pakulin |
|  |  |  | Date: |  |
|  |  |  | Version |  |
|  | Doc ref |  | page 1 of 2 |

| STF | 475 |  | STF leader | Nikolay Pakulin |
| --- | --- | --- | --- | --- |
| TB/WG | MTS |  | TB responsible | Stephan Schulz |
|  |  |  | STF Assistant | Elodie Rouveroux |

| STF title: | Conformance test suite for using XML schema with TTCN-3 |
| --- | --- |

| Milestone | B |  | Status | Covers the period until (cut-off date) | 30-Sep-2014 |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Template |  |  |
| Objective | Progress Report#2 approved by MTS#63 plenary (provisionally scheduled end September, week 39), with the 2nd draft of ATS. The draft documents will be uploaded by the STF Leader on the MTS contributions area of the ETSI Portal one week before the start of the plenary |
| Achieved | Yes/No | Indicate whether the objective has been achieved If the objective is not achieved, give a short explanation in the “remarks” |
| Remarks | MTS#63 to be confirmed (assumed 24-25 September) |

Achieved dates

| Template | Draft report | TB approval | ETSI approval | Sent to EC | EC approval |
| --- | --- | --- | --- | --- | --- |
| 09-Mar-2014 |  |  |  |  |  |

# Executive summary

XML is increasingly being used as a data format in ETSI and other standard bodies. Consequently, the related TTCN-3 test specifications include the use of XML as it is the case, for example, in testing of IMS Supplementary Services. TC MTS has received an urgent request from 3GPP to create tests for certifying TTCN-3 tools used for User Equipment conformance tests that use XML schema. A significant number of TTCN-3 test toolsets are available on the market (at least 7 commercial tools and 2 internal tools of industrial ETSI members). Most of them support the use of XML.

MTS has established a TTCN-3 Conformance Test Suite covering the part 1 of TTCN-3 “Core Language”. The use of XML schema with TTCN-3 has been standardized by TC MTS separately from the Core Language, in part 9 “TTCN-3: Using XML schema with TTCN-3”, and is therefore not covered by the existing TTCN-3 Conformance Test Suite.

TC MTS’s target with this STF request is to cover all XML features used by the 3GPP UE tests and in overall 80% of all sections of the part 9 “TTCN-3: Using XML schema with TTCN-3” with conformance test cases. This would secure that TTCN-3 test suites using XML schema will compile on multiple TTCN-3 tools, and remove possible misunderstandings and ambiguities when implementing the use of XML schema in TTCN-3 test tools.

Furthermore, other ETSI technical bodies and industrial fora are also using XML together with TTCN-3 as the test specification language, for example ETSI INT and the NTAF (Network Test Automation Forum).

The STF team consists of 4 experts. The STF has spent 10.5 working days in the reporting period, with most of the work is scheduled for end of 2014. The STF has defined the ATS structure, the testing method and developed 185 tests (27 negative, 157 positive) that use 196 XML Schema documents. The ATS covers 61 clauses of part 9 (out of 138 clauses of Part 9). 50 clauses are covered out of 63 clauses that were identified as priority for TF 160 (3GPP RAN).

# Introduction

The creation of the XML schema TTCN-3 conformance test specification work will comprise the following tasks:

•	Cataloguing of requirements.

•	Adapting existing framework used by the Core Language TTCN-3 reference test specification

•	Develop tools for the validation of XML encoding/decoding

•	Develop the implementation conformance statement (ICS).

•	Develop the test suite structure and test purposes (TSS & TP).

•	Develop the abstract test suite (ATS) and IXIT

The STF consists of 4 experts:

•	Nikolay Pakulin, ISPRAS

•	Bogdan Stanca-Kaposta, Testing Technologies

•	Tomaš Urban, Elvior OU

•	Bostian Pintar, Sintesio

The STF session plan contains 5 one-week working sessions with all experts present and 1 extra week with 3 experts present, total 96 remun. days and 24 volunt. days. Working sessions were held on

•	Feb. 03-07 at ETSI, Sophia Antipolis

•	April 23-26 at Elvior, Tallinn.

•	Sept. 15-20, home session.

Future working sessions are scheduled for home sessions. No meeting are planned.

•	October, home session.

•	October, home session.

•	December, home session.

TTCN3 Part 9 includes 138 normative sections. Features defined in 63 sections were identified in the XSD files of 3GPP test suites.

# Contractual milestone

The contractual milestone B, related to this Progress Report #2 is achieved by TB MTS approving this progress report.

# Progress of the work

By now the STF has exploited 60.75 man-days out of 120. Two face-to-face sessions were organized:

•	Feb. 03-07 at ETSI, Sophia Antipolis

•	April 23-26 at Elvior, Tallinn.

Home work sessions were held on April 14-17 and September 15-20.

The following results were achieved:

1.	Defined the structure of the test suite. Conventions on naming, formatting, etc. developed.

2.	Defined testing method.

3.	Developed reference implementation of the utility that compares XML documents; used that implementation to validate the ATS in TTworkbench and TestCast.

4.	Created 185 tests (27 negative, 157 positive) that use 196 XML Schema documents. The ATS covers 61 sections of TTCN-3 Part 9. 50 clauses are covered out of 63 clauses that were identified as priority for TF 160 (3GPP RAN).

# Assessment of technical risk, difficulties encountered/expected, unresolved issues

We can underline the following risks connected with the test suite development.

1.	Complexity of XML Schema language and tricky issues around TTCN3-XML conversion lead to a risk of not meeting the objective “to cover overall 80% of all sections of the part 9”. At the moment 53% of the manpower is consumed, and 44% of sections covered. The covered sections are relatively simple, dealing with simple types mostly. The remaining section of complex content might require more effort per test case.

2.	Validation of the test suite require from TTCN-3 tool vendors to implement matchFile external file that implements an algorithm to compare XML documents. The deliverable contains a reference implementation in Java based on XmlUnit tool.

a.	The first risk is that if vendor implements this function by its own, say, in other language, the result of test execution might be hampered by defects in the implementation in the comparison algorithm.

b.	The second risk is the complexity of XML comparison utility. Vendor might give up validation if they consider implementation of matchFile external function prohibitively expensive.

# Proposed changes in the STF work plan

No proposed change.

# Resources requirements

No additional resource is required as per se.

# Changes in the STF Team

There was no change in the STF's composition and no change is foreseen or required.

# Meetings/events attended on behalf of the STF

The STF leader Nikolay Pakulin has participated in MTS#63 on October 1-2, where he has presented the current report.

# Meetings/events planned to be attended

| Date | Place | TB/Orga | Event description | Reason to attend | Expert(s) |
| --- | --- | --- | --- | --- | --- |
| Beginning of 2015 | TBD | MTS#64 | TC MTS regular meeting | STF 475 milestone C, Final report. | Nikolay Pakulin, Bogdan Stanca-Kaposta |

# STF communications, presentations, promotion, inside and outside ETSI, WEB pages etc

The STF has communicated with STF 160 experts via joint meeting and email correspondence.

The STF has communicated with IBM Rational Tau team via email correspondence.

# Technical advice required from the reference Technical Body

No technical issue needs escalation to the Steering Group of the STF or the TC MTC.

# Status of the deliverables

The snapshot of the SVN repository containing the ATS and developed tools is available under https://forge.etsi.org/svn/TTCN3_PART9/tags/release-mts-63/ tag.

The zip archive with the sources of the ATS and tools, including the sources of the reference implementation of XML comparing utility, are attached to this report among contribution to MTS#62 meeting at http://portal.etsi.org/Contribution.aspx?MeetingId=15331

# Next report

The next report is scheduled for: Milestone report B, MTS#64 (January 2014).

# Any other business

None.