## Slide 1: Proposed topics for TDL phase 3
Siemens Corporate Technology | Month 20XX

## Slide 2: General timeline for TDL phase 3 STF
  M1: Start of work: 01-Feb-2015
  M2: 1st draft: 24-Apr-2015 (2 weeks ahead of MTS#65)
  M3: Start of work 2: 01-May-2015 (for some tasks of the STF)
  M4: 2nd draft: 18-Sep-2015 (2 weeks ahead of MTS#66)
  M5: 3rd draft: 18-Dec-2015 (4 weeks ahead of MTS#67)
  M6: End of work: 31-Jan-2016

## Slide 3: Assumptions for resource/cost calculation
  STF management (reporting etc.): 6 days
  Each draft at M2, M4, M5 shall be accomplished in 2 sessions à 5 days per person
  Cost calculation
    Voluntary effort of 20% for contracted work
    Remuneration: 600 € per day
    Travelling costs (3 MTS meetings + UCAAT or similar): 4000 €

## Slide 4: 1) New: Test generation capabilities
WI on TDL-MM v 1.3.1
  Enhance and enable TDL to generate abstract tests, i.e. test descriptions expressed in TDL (phases 1/2 put emphasis on generation of concrete tests, i.e. test cases expressed, e.g., in TTCN-3)
  Additional language features
    Nondeterministic choice over behavior (to specify choice over test description references)
      Similar to Highlevel-MSC (not so much of state machines); see next slides
      (Might cover also parallel composition of tests)
    Nondeterministic choice over data
      Consider test descriptions with free, unassigned parameters
      Provide a data pool for data values to be assigned to these free parameters  test data gen.
        Correct data, invalid data, data interval/range etc.
      Similar to UTP data pool
  Need to cover test campaign specification (set of test cases and their ordering of execution)
  Start of work: M3; end of work: M5 (2 draft versions)
  Resources: 2 persons in 4 sessions

## Slide 5: Test scenario graph modeling – Example

## Slide 6: Modeling scenario graph and alternative approach
vs.
Test generator generates tests according to chosen coverage criterion.
User models tests explicitly and keeps control over them.

## Slide 7: 2) Improved: TDL static and operational semantics
WI on TDL-MM v 1.3.1
  Currently all semantic descriptions provided as free text
  Review and refinement of static semantics of all MM elements
    Possibly: refinement of static semantics in OCL constraints
  Elaboration of operational semantics for parts of the MM related to behavior descriptions
    Improved text
    More formalization desirable, e.g. provision of a mapping to UPPAAL models (translational semantics), but might be not achievable
  Start of work: M3, end of work: M5 (2 drafts)
  Resources: 2 persons in 4 sessions

## Slide 8: 3) Maintenance of TDL-MM
WI on TDL-MM v 1.3.1
  Updates and resolving of change requests on the MM (left-over from TDL2)
  Start: M1, end: M4
  Resources: 1 person in 4 sessions

## Slide 9: 4) Maintenance of TDL-GR and TDL-XF and TDL-TO
WI on TDL-GR v 1.2.1, TDL-XF v 1.2.1, TDL-TO v 1.2.1
  Updates and resolving of change requests on the MM
  Some extensions of TDL-TO (part 4) according to ETSI’s needs, e.g. parallel events etc.
  Start: M3, end: M5
  Resources: 2 persons in 4 sessions

## Slide 10: 5) UML profile for TDL; amendment of TDL-MM part 1
WI on TDL-MM v 1.3.1
  Provided as an informative or normative annex of part 1
  Defines a mapping of all or a subset of essential parts of the TDL-MM to the UML-MM
  Partial validation of the mapping within Eclipse environment, e.g. based on Papyrus UML editor
  Start: M1, end: M5
  Resources: 2 persons in 6 sessions

## Slide 11: 6) Reference implementation for textual TDL (incl. ETSI syntax on TDL-TO)
New WI: DTR/MTS-203119REFv1.1.1
  Provision of a reference implementation of TDL in textual syntax
    TDL MM in a possible textual syntax, closely related to TTCN-3 (or another programming language)
    Includes the ETSI syntax on a test purpose language
    Includes the implementation of the TDL-XF (exchange format)
  Based on open-source software and also provided as open-source to the community
    Eclipse, EMF, Xtext
  Start: M1, end: M5
  Resources: 2 persons in 6 sessions

## Slide 12: Overall resources requested
  Task 0: Management 6 M1 – M6
  Task 1: Test generation 30 M3 – M5
  Task 2: Semantics 20 M3 – M5
  Task 3: Maintenance TDL-MM 40 M1 – M4
  Task 4: Maintenance GR, XF and TO (part 4) 70 M3 – M5
  Task 5: UML profile 40 M1 – M5
  Task 6: Reference implementation 60 M1 – M5
  Total: 266 days
  Costs
    Contracted efforts (20% voluntary): 213 days * 600 € = 127,800 €
    Travel costs: 4000 €
  Assuming a budget of 120k€, there are at most 242 days available