|  | STF 492 – Final Report for ETSI |
| --- | --- |
|  | Presented to ETSI meeting | Author: | ETSI |
|  | MTS#68 | Budapest | Date: | 02-05.2016 |
|  |  |  | Version | 1.0 |
|  | Doc |  | page 1 of 2 |

| STF | 492 |  | STF leader | Philip Makedonski |
| --- | --- | --- | --- | --- |
| TB/WG | MTS |  | TB responsible | Dirk Tepelmann |
|  |  |  | STF Assistant | Elodie Rouveroux |

| STF title: | TDL for Test Generation - Phase 3 A Reference Implementation |
| --- | --- |

| Milestone | D |  | Status | Covers the period until (cut-off date) | 31-Mar-2016 |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Template |  |  |
| Objective | Final Report approved by MTS#68 plenary (May 2016); final drafts of RES/ES 203 119-1, -2, -3, -4, TR 203 119 approved by TC MTS and accepted by the ETSI Secretariat for Members Vote. The final drafts will be uploaded by the STF Leader on the MTS contributions area of the ETSI Portal at least 30 days before the start of the plenary. |
| Achieved | yes |  |
| Remarks |  |

Achieved dates

| Template | Draft report | ETSI approval | Sent to EC | EC approval |
| --- | --- | --- | --- | --- |
| 13-Apr-2016 | 02-May-2016 |  |  |  |

Activities carried out by the STF in the period from 09-Jun-2015 to 31-Mar-2016

# Executive summary

This progress report covers the entire work of STF 492 spanning the period between 09-Jun-2015 and 31-Mar-2016. This period concludes the submission of the completed deliverables defined for Milestone D, including the final drafts for ES 203 119-1 V1.3.1, ES 203 119-2 V1.2.1, ES 203 119-3 V1.2.1, ES 203 119-4 V1.2.1, covering extensions to the abstract syntax and associated semantics of TDL, an adaptation of the standardised graphical syntax and exchange format for TDL, as well as to the extension for the specification of structured test objectives.  Additionally, the final draft for TR 203 119 documents the technical aspects of the work on the reference implementation.

STF 492 continued the work of STF 454 and STF 476, implementing Phase 3 of the development of TDL at ETSI MTS.

The work of STF 492 was done during four working sessions, accompanied by coordinated homework among the experts and technical discussions with the established steering group, which provided technical guidance.

The work of STF 492 was main driving force for the TDL Launch event at UCAAT 2015, comprising a tutorial on TDL, a keynote speech with guest speakers from supporting organizations, including standardization, industry, and academia, as well as a stand with demos and discussions with interested stakeholders during the breaks. Further dissemination activities have been performed by the experts and their respective organizations.

The final deliverables have been submitted to the attention of TC MTS for approval at MTS#68.

# Introduction

This progress report covers the entire work of STF 492, done in the period between 09-Jun-2015 and 31-Mar-2016. This period concludes the submission of the deliverables defined for Milestone D. The work was done primarily during four working sessions, two of which at ETSI, accompanied by coordinated homework among the experts and technical discussions with the established steering group

## Scope, major aims of the STF work

The ToR defines the final result of this STF as the delivery of the final drafts of the multi-part ETSI standard ES 203 119 comprising:

TR 203 119 Technical report on the reference implementation of TDL and the reference implementation itself hosted on an open internet platform serving as a portal for the community;

ES 203 119-1 TDL Part 1: An adaptation of the current TDL meta-model including the specification of a UML profile for TDL enabling the use of TDL in a UML environment; it addresses also change  requests that stem from the work on the reference implementation and from early adopters of TDL from the community;

ES 203 119-2 TDL Part 2: An adaptation of the TDL graphical syntax according to the changes in Part 1, including change  requests addressing challenges from the reference implementation and early adopters;

ES 203 119-3 TDL Part 3: An adaptation of the TDL exchange format specification according to the changes in Part 1, including change  requests addressing challenges from the reference implementation and early adopters;

ES 203 119-4 TDL Part 4: An adaptation and extension of the capabilities for structured test objective specification to include additional features which are in the interest of ETSI technical bodies as well as implementation of change requests from the reference implementation and other early adopters.

## STF activity and expected output

STF 492 contributes to the work of TC MTS on the development of the “Test Description Language” (TDL), which acts as an intermediary between test purpose specification with TPLan and test case specification and implementation with TTCN-3. The STF contributes to the ongoing activities in TC MTS to establish model-based testing (MBT) technologies within ETSI.

Building on the work of STF 454 and STF 476, STF 492 covers Phase 3 of the development of TDL at ETSI MTS focusing on a reference implementation of TDL and a UML profile for TDL.

STF 492 targeted acceleration of the adoption of TDL by providing a reference implementation of TDL to lower the barrier to entry for both users and tool vendors in getting started with using TDL. The reference implementation comprises graphical viewers, textual editors, as well as a UML profile for TDL to enable its interoperability with and application in UML-based working environments and model-based testing approaches. STF 492 contributed to the public launch of TDL at UCAAT 2015 which took place at ETSI, a major milestone in the development of TDL

## Relation with the reference TB and with other bodies, inside and outside ETSI

Guiding the development of TDL within the STF, the TC MTS set up a dedicated Steering Group to review intermediate results and provide recommendations for further development. In addition, several informal meetings of the STF with members of ITS, oneM2M, and 3GPP were held at ETSI premises to receive feedback from potential end-users of TDL. During the TDL launch at UCAAT, feedback was gathered from various stakeholders inside and outside ETSI expressing interest in TDL.

# Overview of the organization of the activity

## Team composition and experts’ qualification

Gusztav Adamis, Ericsson Hungary Ltd, gusztav.adamis@ericsson.com:
Expert in TTCN-3, SDL, MSC, UML, test automation.

Martti Käärik, OU Elvior, martti.kaarik@elvior.com:
Expert in UML, modelling, model-based testing, testing and test design tooling.

Finn Kristoffersen, Cinderella Aps, finn@cinderella.dk: 
Expert on TTCN-3, tooling implementation, testing.

Philip Makedonski, Institut für Informatik, University of Göttingen, makedonski@informatik.uni-goettingen.de:
Expert on meta-modelling, tooling, language design.

Xavier Zeitoun, CEA, xavier.zeitoun@cea.fr: 
Expert on UML, meta-modelling, UML profiling.

## STF teamwork, distribution of tasks, working methods

Gusztav Adamis: 
Rapporteur for ES 203-119-2, working on graphical syntax maintenance, UML profile for TDL.

Martti Käärik:
Rapporteur for ES 203-119-1, working on graphical viewer implementation, meta-modelling and semantics definition, TR 203-119.

Finn Kristoffersen: 
Working on structured test objective extension, maintenance, and implementation.

Philip Makedonski: 
STF leader, rapporteur for ES 203-119-3, ES 203-119-4, TR 203-119, working on meta-modelling, constraint formalisation, graphical viewer implementation, exchange format maintenance, textual syntax and examples, structured test objective extension, maintenance, and implementation, TR 201-119.

Xavier Zeitoun: 
Working on UML profile for TDL.

The main working method used in the STF was group work. Sub-teams were created to prepare initial material for the individual tasks. Preliminary results from the work of the STF team members were presented, discussed, and iteratively refined within the whole team. Conference calls were organised between working sessions to discuss progress and coordinate work on interdependent tasks.

## Liaison with the reference TB and/or the Steering Group

To guide the development of TDL within the STF, a Steering Group was set up with members from MTS. The SG reviewed the intermediate results from the STF and gave recommendations for further development. There were seven joint coordination meetings between the STF and the SG as follows:

2015-06-10, SG#1, face-to-face technical session in connection with MTS#65

2015-07-17, SG#2, conference call

2015-09-18, SG#3, conference call

2015-09-30, SG#4, face-to-face technical session in connection with MTS#66

2015-11-16, SG#5, conference call

2016-01-26, SG#6, technical session in connection with MTS#67

2016-03-03, SG#7, conference call

## Meetings attended on behalf of the STF with the reference TB and other ETSI TBs

2015-06-10/11, MTS#65, Sophia-Antipolis

Participants: Makedonski, Käärik, Adamis, Kristoffersen, Zeitoun

Main results:

Initial STF session co-located with MTS#65, updated planning, discussion of scope and tasks with MTS and the TDL SG

2015-10-01/02, MTS#66, Berlin

Participants: Makedonski, Käärik (remote), Adamis (remote), Zeitoun (remote), Kristoffersen (remote)

Main results:

Report on the progress of STF 492, implementation demonstrations

Scope, materials, and planning of the TDL Launch event discussed.

2016-01-27/28, MTS#67, Berlin

Participants: Makedonski (remote), Käärik (remote), Adamis (remote), Zeitoun (remote), Kristoffersen (remote)

Main results:

Drafts for Milestone C approved

Discussion of feedback from the TDL Launch event at UCAAT 2015

Discussion of future activities related to TDL

## STF communications, presentations, promotion, inside and outside ETSI, WEB pages etc

The results of the STF were presented in a detailed tutorial at the ETSI User Conference on Advanced Automated Testing (UCAAT) 2015 in Sophia Antipolis as part of the TDL launch event, addressing a large number of potential users for TDL both in- and outside of ETSI. During the event a keynote with guest speakers from different organisations showcased different perspectives on TDL from supporting parties. Demos and further discussions at the dedicated TDL booth stand during the coffee and lunch breaks further reinforced the presence of TDL at the event. Interest from different domains and organisations was expressed at the event and important connections with interested parties were established during the conference. The official TDL website was also launched during the event. An additional website describing the work of the STF has been setup at the ETSI portal.

# Final status of the activity

## Overview of the STF work

The work of the STF resulted in the delivery of the Final Drafts of the multipart ES 203 119 "Methods for Testing and Specification (MTS); The Test Description Language (TDL);" including:

ES 203 119-1 TDL Part 1: An adaptation of the current TDL meta-model including the specification of a UML profile for TDL enabling the use of TDL in a UML environment; it addresses also change  requests that stem from the work on the reference implementation and from early adopters of TDL from the community;

ES 203 119-2 TDL Part 2: An adaptation of the TDL graphical syntax according to the changes in Part 1, including change  requests addressing challenges from the reference implementation and early adopters;

ES 203 119-3 TDL Part 3: An adaptation of the TDL exchange format specification according to the changes in Part 1, including change  requests addressing challenges from the reference implementation and early adopters;

ES 203 119-4 TDL Part 4: An adaptation and extension of the capabilities for structured test objective specification to include additional features which are in the interest of ETSI technical bodies as well as implementation of change requests from the reference implementation and other early adopters.

The work on the reference implementation of TDL resulted in the Final Draft of the TR 203 119 Technical report on the reference implementation of TDL and the reference implementation itself. The reference implementation itself is currently available at the ETSI forge. The details of how it shall be made available to a wider audience are still under discussion within MTS and ETSI at large. Different parts of the reference implementation, such as the UML profile may need to be made available in more that one way as UML profiles within the Eclipse platform are typically made available via the UML profile repository.

## Technical risk, difficulties encountered and corrective actions taken

The following risks have been identified as potential difficulties for the progress of the work of the STF::

Task (inter-) dependencies may create bottlenecks for the work of the STF

Due to the parallel and distributed work on multiple deliverables across multiple experts, dependencies among individual activities may create hindrances for the progress of the STF.

Severity: High, Likelihood: High

Mitigation strategies:

- Limit dependencies between activities where possible.

- Make dependencies explicit where these are inevitable in order to raise awareness, as well as monitor and control potential implications.

- Ensure communication and collaboration among experts working on inter-dependent tasks.

- Reassign experts where applicable in order to accelerate progress of delayed activities and eliminate bottlenecks in a timely manner.

- Restrict further additions and modifications to items that other activities depend on.

Misunderstandings and communication barriers hinder progress

Misunderstandings and communication issues during discussions within the STF and with other stakeholders may negatively impact the progress of the STF work.

Severity: Medium, Likelihood: Medium

Mitigation strategies:

- Moderation and awareness – recognize and differentiate between misunderstandings, where clarification is needed, and technical disagreements, where different solutions are proposed.

- Emphasis on facts, substantiated and illustrated with examples, and written input and output of discussions, which describes ideas, problems, and solutions in sufficient detail, and can be referenced to in subsequent discussions.

- Identify fundamental differences in alternative proposals and their impact in order to establish a baseline for discussions, rather focusing discussions on superficial and non-essential differences.

- Communicate and resolve persistent issues and disagreements with the help of the steering group.

Misalignment of expectations towards the STF and the output of the STF

Due to potentially unrealistic or misaligned expectations towards the STF from different stakeholders, the output of the STF may not be able to meet these expectations.

Severity: Medium, Likelihood: Medium

Mitigation strategies:

- A steering group has been established to provide technical guidance and mediate technical disagreements.

- Frequent reporting and technical discussions with the steering group and TC MTS ensure that the work of the STF is aligned with its expectations. The STF has an opportunity to communicate any expectations that are perceived to be unrealistic back to the steering group and TC MTS.

- Concrete examples are prepared to support technical discussions and ensure alignment of expectations.

## Lessons learnt

Based on the experiences with the STF and especially with respect to the identified the following observations and recommendations can be made:

- Dependencies among tasks can prove to be critical to the progress of the work. Delays with tasks on which other activities depend can negatively impact the progress and the quality of the work. It is recommended that important dependencies between tasks are formally taken into account during STF milestone planning and put right into the Terms of Reference.

- Expectations towards the output of the STF need to be kept in alignment the SG and other stakeholders in a timely manner. Issues raised late put unnecessary pressure on all parties involved and there may be no resources left to address them properly.

# ETSI deliverables

| Deliverable: RES/MTS-203119-1v1.3.1 (ES 203 119-1) Current status: Final draft for approval Working title: Methods for Testing and Specification (MTS); Test Description Language Meta-Model and Semantics | Achieved date |
| --- | --- |
| Creation of WI by WG/TB | 2014-10-02 |
| TB adoption of WI | 2014-10-17 |
| Start of work | 2015-06-05 |
| Early draft | 2015-07-24 |
| Stable draft | 2015-12-23 |
| Final draft for approval | 2015-03-01 |
| TB approval | 2016-05-12 |
| Draft receipt by ETSI Secretariat |  |
| Publication |  |
| Deliverable: DES/MTS-203119-2v1.2.1 (ES 203 119-2) Current status: Final draft for approval Working title: Methods for Testing and Specification (MTS); Test Description Language Graphical Syntax | Achieved date |
| Creation of WI by WG/TB | 2014-10-02 |
| TB adoption of WI | 2014-10-17 |
| Start of work | 2015-06-05 |
| Early draft | 2015-12-23 |
| Stable draft |  |
| Final draft for approval | 2016-03-01 |
| TB approval | 2016-05-12 |
| Draft receipt by ETSI Secretariat |  |
| Publication |  |
| Deliverable: DES/MTS-203119-3v1.2.1 (ES 203 119-3) Current status: Final draft for approval Working title: Methods for Testing and Specification (MTS); Test Description Language Exchange Format | Achieved date |
| Creation of WI by WG/TB | 2014-10-02 |
| TB adoption of WI | 2014-10-17 |
| Start of work | 2015-06-05 |
| Early draft |  |
| Stable draft | 2015-12-23 |
| Final draft for approval | 2016-03-01 |
| TB approval | 2016-05-12 |
| Draft receipt by ETSI Secretariat |  |
| Publication |  |
| Deliverable: DES/MTS-203119-4v1.2.1 (ES 203 119-4) Current status: Final draft for approval Working title: Methods for Testing and Specification (MTS) Test Description Language Extensions: Structured Test Objective Specification | Achieved date |
| Creation of WI by WG/TB | 2014-10-02 |
| TB adoption of WI | 2014-10-17 |
| Start of work | 2015-06-05 |
| Early draft | 2015-12-23 |
| Stable draft | 2016-03-02 |
| Final draft for approval | 2016-04-05 |
| TB approval | 2016-05-12 |
| Draft receipt by ETSI Secretariat |  |
| Publication |  |
| Deliverable: DTR/MTS-203119REFv1.1.1 (TR 203 119) Current status: Final draft for approval Working title: Methods for Testing and Specification (MTS) Test Description Language Reference Implementation | Achieved date |
| Creation of WI by WG/TB | 2014-10-02 |
| TB adoption of WI | 2014-10-17 |
| Start of work | 2015-06-05 |
| Early draft |  |
| Stable draft | 2015-12-23 |
| Final draft for approval | 2016-04-12 |
| TB approval | 2016-05-12 |
| Draft receipt by ETSI Secretariat |  |
| Publication |  |

# Resources allocated and spent

## Estimated cost

## Manpower cost

| Description | Working days | Rate €/day | Total cost € |
| --- | --- | --- | --- |
| Contracted experts (remunerated) | 188 | 600 | 112 800 |
| Contracted experts (voluntary, 20% from total) | 47 | 0 | 0 |
| CTI staff (voluntary) | 25 | 0 | 0 |
| Total manpower cost | 260 |  | 112 800 |

## Travel Costs

| Description | Cost estimate |
| --- | --- |
| Attending MTS plenary meetings (3 travels within Europe to MTS#62, #63, #64) | 3 000 € |
| Presentation at UCAAT 2014 or a related conference (1 travel within Europe) | 1 000 € |
| Total cost | 4 000 € |

## Other Costs

None.

## Summary of resources allocated and spent (real cost)

The following tables present the summary of the activities carried out by the STF in the period 09-Jun-2015 to 31-Mar-2016. Status date: 02-May-2016.

Table 1: Status of resources funded and spent

| Contribution (funded) |
| --- |
|  | Manpower | Travel | Subc. | Other | Total |
|  | Days | Rate | EUR | EUR | EUR | EUR | EUR |
| Experts remun. | 188 | 600 | 112 800 | 4 000 | 0 | 0 | 116 800 |
| Experts volunt. | 47 | 0 |  |  |  |  |  |
| CTI | 25 | 0 |  |  |  |  |  |
| Total funded | 260 |  | 112 800 | 4 000 |  |  | 116 800 |
| Contribution (spent) |
|  | Manpower | Travel | Subc. | Other | Total |
|  | Days | Rate | EUR | EUR | EUR | EUR | EUR |
| Experts remun. | 188 | 600 | 112 800 | 2 759,79 | 0 | 0 | 115 559,79 |
| Experts volunt. | 47 | 0 |  |  |  |  |  |
| CTI (*) | 25 | 0 |  |  |  |  |  |
| Total spent | 260 |  | 112 800,00 | 2 759,79 |  |  | 115 559,79 |
| Balance | 0 |  | 0 | 1 240,21 |  |  | 1 240,21 |

(*) days spent not registered in Timesheets.

Table 2: Time spent by experts (remunerated)

| Company / ETSI Member | Expert | Work days | Rate | Cost (EUR) |
| --- | --- | --- | --- | --- |
| Ericsson Hungary Ltd | Adamis, Gusztav | 28 | 600 | 16 800 |
| OU Elvior | Käärik, Martti | 48 | 600 | 28 800 |
| Cinderella Aps | Kristoffersen, Finn | 21 | 600 | 12 600 |
| Institut für Informatik | Makedonski, Philip | 49 | 600 | 29 400 |
| CEA | Zeitoun, Xavier | 42 | 600 | 25 200 |
| Total |  | 188 |  | 112 800 |

Table 3: Time spent by experts (voluntary)

| Company / ETSI Member | Expert | Work days | Equiv. rate | Equiv. amount (EUR) |
| --- | --- | --- | --- | --- |
| Ericsson Hungary Ltd | Adamis, Gusztav | 7 | 600 | 4 200 |
| OU Elvior | Käärik, Martti | 12 | 600 | 7 200 |
| Cinderella Aps | Kristoffersen, Finn | 5 | 600 | 3 000 |
| Institut für Informatik | Makedonski, Philip | 13 | 600 | 7 800 |
| CEA | Zeitoun, Xavier | 10 | 600 | 6 000 |
| Total |  | 47 |  | 28 200 |

Table 4: Travels

| Expert | Event | Place | Date from | Dur. days | Cost (EUR) | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Makedonski, Philip | MTS#66 / TDL | Berlin | 29/09/2015 | 2 | 237,70 |  |
| Adamis, Gusztav | UCAAT 2015 / TDL | Sophia Antipolis | 19/10/2015 | 3 | 624,79 |  |
| Käärik, Martti | UCAAT 2015 / TDL | Sophia Antipolis | 20/10/2015 | 3 | 537,15 |  |
| Kristoffersen, Finn | UCAAT 2015 / TDL | Sophia Antipolis | 19/10/2015 | 3 | 335,94 |  |
| Makedonski, Philip | UCAAT 2015 / TDL | Sophia Antipolis | 19/10/2015 | 4 | 639,82 |  |
| Zeitoun, Xavier | UCAAT 2015 / TDL | Sophia Antipolis | 19/10/2015 | 4 | 384,39 |  |
| Total |  |  |  |  | 2 759,79 |  |

# Performance indicators

## Performance indicators required in the EC/EFTA contract

The work of the STF had an impact on the performance indicators agreed within the ToR in the following way:

Interests of ETSI and non-ETSI stakeholders

- Voluntary work of experts directly involved in the STF or outside the STF:
Experts spent additional resources on a voluntary basis in order to ensure the progress of the work and address issues that need further clarification or input from external stakeholders. Additionally experts from MTS participated in the Steering Group for this STF.

- Presentations to other ETSI TBs:
There were no formal presentations of the STF given to other TBs. Instead, potential users of TDL, such as 3GPP, ITS and oneM2M, were met on an informal basis to discuss with them their specific requirements.

- Contributions received from other ETSI TBs:
The STF analysed contributions in terms of technical specifications from 3GPP RAN5, IMS, IPv6, ITS, oneM2M and others as input to the work on TDL.

- Contributions presented to TB MTS meetings:
The STF reported regularly to MTS and also the SG its progress in the project and discussed acute issues.

- Presentations in workshops, conferences, stakeholder meetings (outside ETSI):
A tutorial, a keynote, and a demo stand for TDL were prepared as part of the TDL Launch event at the ETSI UCAAT conference, in Sophia Antipolis, October 2015. Feedback was received from various interested parties attending the conference, both from industry, standardisation, and academia.

- Comments received on drafts (e.g. from personal communication, mailing lists, etc.):
There was an extensive exchange of ideas, recommendations etc. between the STF and the MTS SG.

- Potential interest of new members to join ETSI:
The work of MTS in general is attractive also outside of ETSI, multiple participants at the ETSI UCAAT 2015 expressed interest in contributing towards the work of MTS in general and the work on TDL in particular during discussions at the TDL demo booth.

- Liaison to identify requirements and raise awareness on ETSI deliverables:
Informal discussions with interested stakeholders and related projects and activities of the STF members have contributed to raising awareness about the work on TDL.

Quality of the STF results

- Availability of a TDL reference implementation featuring major TDL concepts:
A reference implementation of TDL has been one of the major goals of STF 492. The reference implementation is currently available within the ETSI forge. The details of making the reference implementation available to a wider audience are still under discussion within MTS and ETSI.

- Application of the ETSI drafting rules:
Drafting rules were followed.

- Approval of deliverables according to schedule:
All deliverables were submitted mostly in time, with minor delays for some additional polish and are in the process of receiving approval.

- Respect of time scale, with reference to start/end dates in the approved ToR:
The timeframe of the ToR was followed.

## Performance Indicators objectives not achieved

This section does not apply since all performance indicators were achieved at various levels.