|  | STF 533 – Progress Report for ETSI |
| --- | --- |
|  | Presented to ETSI meeting | Author: | Prof. Jens Grabowski |
|  |  |  | Date: | 05/05/2017 |
|  |  |  | Version |  |
|  | Doc ref |  | page 1 of 4 |

| STF | 533 |  | STF leader | Jens Grabowski |
| --- | --- | --- | --- | --- |
| TB/WG | MTS |  | TB responsible | Emmanuelle Chaulot-Talmon |
|  |  |  | STF Assistant | Elisabetta Comin |

| STF title: | TTCN-3 Evolution 2017 |
| --- | --- |

| Milestone | A |  | Status | Covers the period until (cut-off date) | 01/06/2017 |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Template |  |  |
| Objective | Progress report (incl. status, planned work, priorities on the CRs identified) approved at MTS#71 (31 May-01June 2017) |
| Achieved | Yes |  |
| Remarks | In agreement with ETSI, this progress report has been provided after the first working session of STF533 on 09/06/2017. |

Achieved dates

| Template | Draft report | TB approval | ETSI approval |
| --- | --- | --- | --- |
| 05/05/2017 |  |  |  |

# Executive summary

The TTCN-3 testing language has intensively been developed by ETSI during the last decade and, by today, it consists of 14 ETSI standards, altogether more than 1400 pages. The language is also endorsed by ITU-T as the Z.16x and Z.17x Recommendation series. By now TTCN-3 is the prevalent formal specification language of standardized test suites and has also become an important testing technology at various ETSI member companies and in several industrial domains (http://www.ttcn-3.org/index.php/about/references/applicatio-domains) and standards organizations (http://www.ttcn-3.org/index.php/about/references).

TTCN-3 has an important role in standardization; it is an enabler technology in many areas. Several conformance and end-to-end/interoperability test standards have been developed and being developed by 3GPP, ETSI TBs INT, ERM, and ITS. 3GPP is using TTCN-3 for UE conformance tests from Rel. 8 and onward to LTE and VoLTE, with NB-IoT on horizon. In the ITS area also several TTCN-3 test suites have been developed and they start playing important roles in ITS Plugtest events as well. In 2016 oneM2M has started using it for IoT/M2M conformance test development.

The purpose of STF533 – “TTCN-3 evolution 2017” is to maintain the high quality of the language – that currently consists of 15 ETSI standards - and at the same time keep it harmonized with the new requirements of the users, new application areas and new ways of working like Agile SW development. In addition STF533 produces the new TTCN-3 extension “Object-oriented features” and will work on language harmonization issues.

The STF team consists of 6 experts. During its first working sessions, the STF progressed 29 CRs and identified concepts to be considered during the development of the the new TTCN-3 extension “Object-oriented features”.

# Introduction

The TTCN-3 language evolution work will comprise the following tasks:

- Review and resolve change requests reporting technical defects, or requesting clarifications and new language features for all existing TTCN-3 language standards.

- Develop proposals for language extensions requested by 3GPP, OMA, ETSI members and the TTCN-3 community and consent the solution with the contributor(s).

- Implement agreed solutions.

- Manage the change request (CR) process.

- Manage the interim versions of the standard, according to 3GPP needs, and the versions for approval.

- Present the TTCN-3 standards’ status and the work of the STF at the conference(s) associated with ETSI TB MTS and at ETSI TB MTS meetings.

- Work on TTCN-3 language harmonization.

- Develop the new TTCN-3 extension “Object-oriented features”.

The STF consists of 6 experts:

- Jens Grabowski, University of Göttingen (STF Leader)

- Julien Deltour, PragmaDev

- Kristóf Szabados, Ericsson

- György Réthy, Ericsson

- Tomáš Urban, Elvior

- Jacob Wieland,Spirent Communications

György Rethy does not physically participate in the STF sessions, but contributes by following the ongoing work in Mantis and providing useful feedback via email and telephone.

# Contractual milestone

The contractual milestone M1, related to this Progress Report M1 is achieved by TB MTS approving this progress report.

# Progress of the work

The current STF session plan contains 4 one-week working sessions with all experts present and one week of voluntary work spent for final CR cleaning and editorial work on the draft deliverables.  Working sessions of the STF are:

- W23, 06 - 09 June 2017, Berlin (done)

- W30, 24 - 28 July 2017, Göttingen (planned)

- W36, 04 - 08 September 2017, Tallinn (planned)

- W43, 23 - 27 October 2017, Budapest (planned)

Further working sessions for progressing the work on the new TTCN-3 extension “Object-oriented features” will be organized on demand.

During the first working sessions in Berlin the CRs below have been progressed (i.e., assigned to experts, partially discussed and partially resolved):

Part 01: TTCN-3 Core Language

7590	BNF for select-case is not correct

7673	dynamic_encoding parameter missing in encvalue_o and decvalue_o

7672	Compatibility of enumerated types

7561	Allow finally block or shutdown hook

7601	Misspelled word in 20.2.c

7611	Valid port lists for the procedure operations

7618	alternative event headers could allow a boolean combinators

7619	No named interleave construct available.

7603	Delete note on template restriction passing table

7599	Rules for actual parameterers with template restriction

7630	example creating empty template is wrong

7605	Logging of constructive values

7602	Three options of handling blocking multicast and broadcast calls

7610	Missing rules for return value of the reply operation

7620	Constraining of array types

7598	Invalid restriction on formal template parameters

7495	out, inout and return value should be assignable via the done/killed statement redirect

Part 04: TTCN-3 Operational Semantics

7593	Part-1, Sec.15.11: Template concatenation drops omit and type restrictions

Part 06: TTCN-3 Control Interface

7553	Invalid return type in java MatchingMechanism.getMatchingType()

7594	Wrong parameter type in C mapping of the tliRnd function

Part 09: Using XML with TTCN-3

7562	Clarification of order of XML to TTCN3 type conversion

7654	Invalid encoding instruction in the example on type substitution

7656	Invalid examples on simple content mapping

7657	Name of anyAttribute and anyElement fields are not encoded

7658	Missing support for leap seconds in mapping of XSD time types

Ext Pack: Config & Deployment Support (ES 202 781)

7626	editorial: syntactical structure parts are not properly "spaced"/"indented"

Ext Pack: Behaviour Types (ES 202 785)

7625	Harmonization: the behaviour extension package does not mention modifiers when
 	describing compatibility.

Ext Pack: Advanced Matching (ES 203 022)

7629	concatenation of arbitrary present list/string templates should be allowed

7525	allow repetition (and maybe other regular expression syntax) also for binary string types

The status of the CRs can be followed in detail in ETSI’s Mantis system at http://forge.etsi.org/mantis/view_all_bug_page.php.

For the new TTCN-3 extension “Object-oriented features”, the following topics have been discussed:

- Exception handling

- Handles

- Need of a class concept

- Kinds of objects needed and implicitly existing in TTCN-3

- Inheritance and (existing) multiple inheritance in TTCN-3

- Encapsulation (need for protected)

- Refinement (final declaration needed to avoid further refinement of objects)

- Synonyms or renaming on import (in case of long names)

- Simplification of import due to the existence of means for encapsulation

Even though the topics above have been discussed in the context of the new TTCN-3 extension “Object-oriented features”, not all topics are directly related to object-orientation (e.g., 1, 2, 8, and 9). The STF will discuss this with the TTCN-3 steering group. Some of the topics above will raise CRs which will be resolved in the context of the new TTCN-3 extension or other parts of the TTCN-3 standard series.

# Assessment of technical risk, difficulties encountered/expected, unresolved issues

Currently, the number of unresolved CRs is manageable and should not cause major problems. However, new CRs tend to be submitted before work sessions and the number of new CRs submitted in 2017 cannot be predicted. If the number of new CRs becomes big, STF533 may not be able to resolve all open CRs. The resolution of some CRs may be left for succeeding STFs. The STF will then prioritize the open CRs and resolve them in order of priority as long as possible (some high priority CRs may need long discussions, while low priority, e.g. trivial CRs may be handled quickly and thus may overtake the resolution of higher priority CRs).

The concepts and features to be implemented in the new TTCN-3 extension “Object-oriented features” have not been selected and the amount of work needed for a proper implementation cannot be predicted today. The selection will be made in agreement with TC MTS and TTCN-3 steering group. Problems regarding the development of the new TTCN-3 extension will be reported instantly to TC MTS and TTCN-3 steering group. The STF will follow the advice provided by TC MTS and TTCN-3 steering group.

The work on Task 3 “TTCN-3 language harmonization” has not started. Therefore, the amount of work needed for this task cannot be predicted. The planning will be done in agreement with TC MTS and the TTCN-3 steering group.

At this point in time no action is seen to be required from TC MTS.

# Proposed changes in the STF work plan

No proposed change.

# Resources requirements

There is no change foreseen in the STF resource requirements related to the STF’s ToR.

# Changes in the STF Team

There was no change in the STF's composition and no change is foreseen or required.

# Meetings/events attended on behalf of the STF

| Date | Place | TB/Orga | Event description | Reason to attend | Expert(s) |
| --- | --- | --- | --- | --- | --- |
| 06.04.17 | online | TTCN-3 SC | TTCN-3 steering group online meeting | Discussing STF working principles | Jens Grabowski, György Réthy |
| 31.05. – 01.06.17 | ETSI HQ | TC MTS | MTS#71 regular meeting | Online participation to report STF planning | Jens Grabowski |

# Meetings/events planned to be attended

| Date | Place | TB/Orga | Event description | Reason to attend | Expert(s) |
| --- | --- | --- | --- | --- | --- |
| Jun/Jul | online | TTCN-3 SC | TTCN-3 steering group online meeting (after 1st STF working session) | Selection/discussion of OO-concepts for TTCN-3 and language harmonization | all |
| August | online | TTCN-3 SC | TTCN-3 steering group online meeting (after 2nd STF working session) | Selection/discussion of OO-concepts for TTCN-3 and language harmonization | all |
| 26.09 – 27.09.17 | University Göttingen | TC MTS | MTS#72 regular meeting | Presentation of progress report (milestone M2) | Jens Grabowski |
| 11.10. – 13.10.17 | Berlin | TC MTS | User Conference on Advanced Automated Testing (UCAAT) | Poster presentation of STF work | Jens Grabowski |
| Jan/Feb 2018 | tba | TC MTS | MTS#73 regular meeting | Presentation of progress report (milestone M3) | Jens Grabowski |

# STF communications, presentations, promotion, inside and outside ETSI, WEB pages etc

- The STF533 webpage can be found on: https://portal.etsi.org/STF/STFs/STFHomePages/STF533

- The work of STF533 will be presented and discussed on the ETSI UCAAT conference (https://ucaat.etsi.org/2017/home) in form of a poster presentation.

- Further external communication is done via Mantis and emails.

# Technical advice required from the reference Technical Body

Technical advice from the TTCN-3 steering group is required for

- Task 2 –TTCN-3 language extension: Object-oriented features:

The steering committee shall advice the STF with respect to the contents of the new language extension.

- Task 3 –TTCN-3 language harmonization

The steering committee shall advice the STF with respect to the issues to be tackled in this task.

An online TTCN-3 steering group meeting should be organized before the next STF533 work session in September 2017.

# Status of the deliverables

TTCN-3 standards are stable documents. The way of working of TTCN-3 evolution STFs is approved by ETSI TC MTS, is based on change requests submitted to ETSI’s Mantis CR handling system. Technical resolution and proposed changes in the texts of deliverables are publically available in Mantis during the year. Agreed text of resolved CRs is implemented in drafts of deliverables at, and after the last working session of the STF. Therefore the output drafts of the deliverables are available at the end of the project.

The actual status of the CRs can be found at http://forge.etsi.org/mantis/main_page.php.

# Next report

The next report is scheduled for: TB MTS#72 regular meeting (26/27 Sept. 2017, University of Göttingen).

# Any other business

None