|  | STF 522 – Progress Report for ETSI |
| --- | --- |
|  | Presented to ETSI meeting | Author: | Philip Makedonski |
|  |  |  | Date: | 15/09/2017 |
|  |  |  | Version | 1.0 |
|  | Doc ref |  | page 1 of 6 |

| STF | 522 |  | STF leader | Philip Makedonski |
| --- | --- | --- | --- | --- |
| TB/WG | MTS |  | TB responsible | Emmanuelle Chaulot-Talmon |
|  |  |  | STF Assistant | Elodie Rouveroux |

| STF title: | A standardized mapping to facilitate the automatic generation of TTCN-3 code from TDL descriptions |
| --- | --- |

| Milestone | C |  | Status | Covers the period until (cut-off date) | 29/09/2017 |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Template |  |  |
| Objective | Progress Report approved by MTS#72 and 2nd draft of ES's for review. The draft documents must be uploaded on the MTS contributions area at least one week before the start of the meeting. |
| Achieved | Yes/No |  |
| Remarks |  |

Achieved dates

| Template | Draft report | TB approval | ETSI approval |
| --- | --- | --- | --- |
| 13/09/2017 | 15/09/2017 |  |  |

# Executive summary

This progress report covers the work of STF 522 on reaching Milestone C, done in the period between 15-May-2017 and 15-Sep-2017. This period concludes the submission of the completed deliverables defined for Milestone C.

The work was done during one working session, accompanied by coordinated homework of the experts and one technical discussion with the established steering group, which provided further technical guidance.

The STF work plan has been adapted to accommodate a delay with the start of work. No changes to the resource requirements and STF team are proposed at this point.

Promotional activities related to the public launch of the TDL open source project and promoting TDL in general have been put in place to raise awareness for TDL. The proposals by the STF members for a tutorial and a presentation at UCAAT 2017 have been accepted and are in preparation to promote and communicate the work of the STF.

# Introduction

This progress report covers the work of STF 522 on Milestone C, done in the period between 15-May-2017 and 15-Sep-2017. This period concludes with the submission of the deliverables defined for Milestone C. The work was done primarily during one working session at the University of Göttingen, accompanied by coordinated homework among the experts and one technical discussion with the established steering group.

# Contractual milestone

During the preparatory meeting the milestone planning needed to be adjusted to accommodate the delay with the start of work. Further delays with the administrative details related to the contracts required additional adjustments to the milestone planning. As a consequence, during the preparatory meeting, Milestone C was redefined to "Progress Report C approved by MTS#72 and 2nd draft of ES's for review. The draft documents must be uploaded on the MTS contributions area at least one week before the start of the meeting." All requested deliverables have been uploaded in the MTS contributions area of the ETSI portal on 15-Sep-2017.

# Progress of the work

The original work plan comprises four principal milestones. Due to delays with the start of the work, the scope of the milestones has been adjusted. As agreed during the preparatory meeting, most of the work will be done remotely in order to minimize travelling costs and overhead. The milestones are primarily prepared during individual and coordinated homework. Two working sessions (14-17-Feb-2017, 22-25-Aug-2017) have been scheduled to discuss complex technical challenges in person.

Progress on the following activities has been achieved so far:

Task 0 – Project Management

Two STF working sessions have been planned and allocated.

Progress reports for Milestones B (approved at MTS#71) and C (this document), as well as interim progress reports for the steering group have been prepared and submitted in a timely manner.

STF members participated actively in steering group and MTS meetings.

Proposals for a tutorial and a presentation at UCAAT have been prepared and submitted. Both proposals have been accepted and are currently in preparation.

Coordination and preparation of materials for the TDL open source project.

Task 1 – TDL-to-TTCN-3 language mapping (ETSI Standard)

Discussed and agreed upon fundamentals and refinements of the mapping approach.

Evaluated semantic gaps and potential constraints of the mapping (support only locally ordered behavior), exclude certain constructs (parallel behavior).

Provided basis for most mapping specifications (pending further refinement).

Complete translation of examples from Annex B of ES 203 119-1 to TTCN-3 as basis for mapping.

Set up initial prototype for validating mappings.

Task 2 – Advanced test configuration features (language evolution)

Proposal for meta-model changes integrated as Annex C of ES 203 119-1.

Changes to graphical syntax and exchange format will be added once it has been decided whether the extension becomes a separate document or whether it remains as annex or is integrated into the main meta-model.

Proposal to reclassify advanced test configuration features as a separate extension which will integrate all necessary changes in a self-contained manner (similar to ES 203 119-4).

Task 3 – Language maintenance

Refinements of new features related to the specification of collections added to the meta-model.

Refinements of new features related to the specification of procedure-based interactions added to the meta-model.

Refinements of new features related to the specification of locally ordered behavior added to the meta-model.

Further refinements related to predefined functions, time labels, and quiescence added to the meta-model.

Related changes to the graphical syntax, exchange format, and structured test-objective specification partially implemented in the corresponding documents.

Task 4 – Requirements for performance and security testing

Initial discussions with ETSI CTI to identify potential stakeholders at ETSI.

Gathered additional information regarding potential risks and next steps as basis for discussion within MTS.

# Assessment of technical risk, difficulties encountered/expected, unresolved issues

The progress of the work of the STF may be negatively affected by the following risks:

Task (inter-) dependencies may create bottlenecks for the work of the STF

Due to the parallel and distributed work on multiple deliverables across multiple experts, dependencies among individual activities may create hindrances for the progress of the STF.

Severity: Medium, Likelihood: Low

Mitigation strategies:

Limit dependencies between activities where possible.

Make dependencies explicit where these are inevitable in order to raise awareness, as well as monitor and control potential implications.

Ensure communication and collaboration among experts working on inter-dependent tasks.

Reassign experts where applicable in order to accelerate progress of delayed activities and eliminate bottlenecks in a timely manner.

Misunderstandings and communication barriers hinder progress

Misunderstandings and communication issues during discussions and individual work may negatively impact the progress of the STF work.

Severity: Medium, Likelihood: Medium

Mitigation strategies:

Moderation and awareness – recognize and differentiate between misunderstandings, where clarification is needed, and technical disagreements, where different solutions are proposed.

Emphasis on facts, substantiated and illustrated with examples, and written input and output of discussions, which describes ideas, problems, and solutions in sufficient detail, and can be referenced to in subsequent discussions.

Identify fundamental differences in alternative proposals and their impact in order to establish a baseline for discussions, rather focusing discussions on superficial and non-essential differences.

Communicate and resolve persistent issues and disagreements with the help of the steering group.

Misalignment of expectations towards the STF and the output of the STF

Due to potentially unrealistic or misaligned expectations towards the STF from different stakeholders, the output of the STF may not be able to meet these expectations.

Severity: Medium, Likelihood: Medium

Mitigation strategies:

A steering group has been established to provide technical guidance and mediate technical disagreements.

Frequent reporting and technical discussions with the steering group and TC MTS ensure that the work of the STF is aligned with its expectations. The STF has an opportunity to communicate any expectations that are perceived to be unrealistic back to the steering group and TC MTS.

Concrete examples are prepared to support technical discussions and ensure alignment of expectations

Insufficient stakeholders and/or insufficient requirements for Task 4

Due to potentially insufficient number of stakeholders interested in using TDL for security and performance testing within ETSI, or inability to gather sufficiently detailed requirements from the available stakeholders, the progress and output on Task 4 may be compromised.

Severity: Medium, Likelihood: Medium

Mitigation strategies:

A discussion within MTS shall provide guidance on how to proceed based on the current information. A decision is needed on whether further potential stakeholders shall be approached or whether the resources allocated to Task 4 shall be re-allocated to other tasks.

# Proposed changes in the STF work plan

The STF work plan has been adjusted to accommodate the delay with the start of work as follows:

| N | Task / Milestone / Deliverable | ToR Targets | Current Targets |
| --- | --- | --- | --- |
| M0 | Start of work | Sep-2016 | Jan-2017 |
| T0 | Project management | Sep-2016–Sep-2017 | Jan-2017–Jan-2018 |
| T1 | TDL-to-TTCN-3 mapping | Sep-2016–Sep-2017 | Jan-2017–Jan-2018 |
| T2 | Advanced test configuration features | Sep-2016–Apr-2017 | Jan-2017–Aug-2017 |
| T3 | Language maintenance | Sep-2016–Apr-2017 | Jan-2017–Aug-2017 |
| T4 | Requirements for security and performance testing | Mar-2017–Sep-2017 | Jun-2017–Dec-2017 |
| M1 | Informal report on planning | 16-Dec-2016 | Jan-2017 |
| M2 | 1st drafts | 28-Apr-2017 | May-2017 |
| M3 | 2nd drafts | 28-Jul-2017 | Sep-2017 |
| M4 | Final drafts for MTS review | 01-Sep-2017 | Dec-2017 |
| M5 | Final report, end of work, TB approval | 27-Sep-2017 | Jan-2018 |
| M6 | Membership vote | 27-Sep-2017 | Feb-2018 |
| M7 | Publication | 01-Dec-2017 | Apr-2018 |

# Resources requirements

No changes in the STF resource requirements are proposed at this point. Depending on the outcome of the discussions regarding Task 4 at MTS#72, some of the resources allocated for Task 4 may be redistributed to other tasks.

# Changes in the STF Team

No changes in the STF team are proposed at this point in time.

# Meetings/events attended on behalf of the STF

Planning and coordination for the work of the STF were presented and discussed during MTS#70 at Spirent in Berlin on 25-26-Jan-2017. Philip Makedonski (STF leader) attended in person, while the remaining experts attended remotely. Due to a scheduling conflict of the STF leader, Martti Käärik attended MTS#71 in person as representative of the STF while all remaining experts attended remotely.

| Date | Place | TB/Orga | Event description | Reason to attend | Expert(s) |
| --- | --- | --- | --- | --- | --- |
| 25-26-Jan-2017 | Berlin | MTS | MTS#70 | Present and discuss achievements of the STF up to that point | Philip Makedonski (in person) |
| 31-May/01-Jun-2017 | Sophia-Antipolis | MTS | MTS#71 | Present and discuss achievements of the STF up to that point | Martti Käärik (in person) |

# Meetings/events planned to be attended

| Date | Place | TB/Orga | Event description | Reason to attend | Expert(s) |
| --- | --- | --- | --- | --- | --- |
| 20-21-Sep-2017 | Göttingen | MTS | MTS#72, Technical Session on TDL | Present and discuss achievements of the STF up to that point | Philip Makedonski (in person) |
| 11-13-Oct-2017 | Berlin | MTS, ETSI, Fraunhofer FOKUS | User Conference on Advanced Automated Testing (UCAAT) and associated events. | Presentation and tutorial on TDL, host the public launch of the TDL open source project. | Philip Makedonski (in person), Gusztav Adamis (in person), Martti Käärik (in person) |
| Jan-2018 | TBA | MTS | MTS#73, Technical Session on TDL | Present and discuss achievements of the STF up to that point | TBA |

# STF communications, presentations, promotion, inside and outside ETSI, WEB pages etc

The following activities related to the communication, presentation, and promotion of the work of the STF have been considered, planned, and/or performed:

The proposals by the STF for a tutorial and a presentation on TDL and the current work of the STF at the UCAAT 2017 have been accepted and are currently in preparation. Related work on the TDL open source project is expected to culminate in a public launch of the TDL open source project during UCAAT 2017.

An article has been prepared by the STF to promote and communicate the work of the STF and the new features of TDL. The STF is currently evaluating potential publication opportunities.

A keynote on TDL by a steering group member at the ICTSS 2017 is currently in preparation in collaboration with the STF, with the possibility for a subsequent article in the SQJ.

Ongoing dissemination activities from STF members from research institutions include raising awareness and promoting TDL on their respective websites and within teaching and research activities.

A website for the STF will be published shortly upon agreement within the STF and TC MTS.

The official TDL website aggregating all resources related to TDL and its implementation is being updated and extended with new information.

A dedicated project is established on the online issue reporting portal for ETSI (“ETSI’s Bug Tracker”) where change requests for TDL can be submitted and managed in an open and transparent manner.

# Technical advice required from the reference Technical Body

A steering group has been assembled by TC MTS to provide technical guidance and expert advice during technical sessions with the STF. Up to this point, the steering group has been supporting the work of the STF very well, with technical sessions arranged between working sessions of the STF to discuss the progress of the STF and any open questions or unresolved disagreements.

# Status of the deliverables

Milestone C is comprised of the following deliverables:

A second draft of ES 203 119-1 v1.4.1, available at:	
ftp://docbox.etsi.org:21/STF/STF522_TDL_PH4/Public/drafts/es_20311901v010401p.docx

A first draft of ES 203 119-2 v1.3.1, available at:	
ftp://docbox.etsi.org:21/STF/STF522_TDL_PH4/Public/drafts/es_20311902v010301p.docx

A first draft of ES 203 119-3 v1.3.1, available at:	
ftp://docbox.etsi.org:21/STF/STF522_TDL_PH4/Public/drafts/es_20311903v010301p.docx

A first draft of ES 203 119-4 v1.3.1, available at:	
ftp://docbox.etsi.org:21/STF/STF522_TDL_PH4/Public/drafts/es_20311904v010301p.docx

A second draft of ES 203 119-6 v1.1.1, available at:	
ftp://docbox.etsi.org:21/STF/STF522_TDL_PH4/Public/drafts/es_20311906v010101p.docx

# Next report

The next report is scheduled for: 19-Dec-2017.

# Any other business

None.