|  | STF 548 – Progress Report for ETSI |
| --- | --- |
|  | Presented to ETSI meeting | Author: | Mr. Andras Kovacs |
|  |  |  | Date: | 26/04/2018 |
|  |  |  | Version | 1.0 |
|  | Doc ref |  | page 1 of 4 |

| STF | 548 |  | STF leader | Andras Kovacs |
| --- | --- | --- | --- | --- |
| TB/WG | MTS |  | TB responsible | Emmanuelle Chaulot-Talmon |
|  |  |  | STF Assistant | Elodie Rouveroux / Léa Belloulou |

| STF title: | Extension of Conformance tests for TTCN-3 tools |
| --- | --- |

| Milestone | A |  | Status | Covers the period until (cut-off date) | 24/05/2018 |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Template |  |  |
| Objective | Progress Report approved by TC MTS#74 and stable drafts of RTS's required in the ToR available for review. The draft documents must be uploaded on the MTS contributions area one week before the start of the meeting |
| Achieved | Yes | Indicate whether the objective has been achieved If the objective is not achieved, give a short explanation in the “remarks” |
| Remarks | Draft (unvalidated) new TTCN-3 test cases have been created and shall be uploaded as MTS#74 contributions. |

Achieved dates

| Template | Draft report | TB approval | ETSI approval | Sent to EC | EC approval |
| --- | --- | --- | --- | --- | --- |
| 26/04/2018 | 08/05/2018 |  |  |  |  |

The Progress Report must be produced at the time set in the STF Work Plan.  It generally corresponds to the achievement of a contractual milestone.  The approval of the Progress Report by the ETSI Director-General and the reference TB is required to authorize payment.

The purpose of the Progress Report is to provide an overview of the work performed by the STF between two milestones, the results achieved, difficulties encountered, planning, schedule, etc.

The report is addressed to the reference TB and the ETSI Secretariat, also for STFs funded by EC/EFTA.  Its content is of more technical nature than the Interim and Final Reports.  However, the Progress Reports are an important element to assess the progress of the STF.  The Progress Report may also raise warnings for difficulties that could not be foreseen when the Interim Report was produced and require action from the TB and/or the ETSI Secretariat.

The author shall be conscious that the approval of the Report embodies the authorisation to pay an amount, which may be considerable.  Moreover the correct understanding of the background information and actions requested may affect the outcome of the STF.  The STF Leader should feel responsible to provide complete explanations and give evidence to the items that must be understood by the readers.

The structure of this template is given as a guideline. Non-relevant sections may be suppressed. Paragraphs may be added as necessary.  These guidelines (in italic) must be deleted in the final document.

- Executive summary

TTCN-3 is a living language, a new version is published by ETSI each year, the latest published version is v4.9.1. The TTCN-3 conformance test suite development is in sync with the language development.

The STF 548 target is to synchronize the development of the TTCN-3 language and its conformance test suite, and reach full clause coverage of the standard. This would support that TTCN-3 test suites will also in the future compile on multiple TTCN-3 tools, by removing possible misunderstandings and ambiguities when implementing a new language feature in test tools.

- Introduction

This is the first milestone of STF 548 work, covering the ramping-up of this team’s work.

The part-1 test cases have been 90% completed (focus of work in this first phase), part-9 test cases have been 0% completed. Remaining work to be done: writing of part-9 test cases, validation of test cases by batch execution of the ATS and analysing reason for unexpected results of some test cases (including regression testing), follow-up on the resolution of raised CRs, write-up and publication of results.

- Contractual milestone

STF 548’s Terms of Reference does not specify quantitative targets for milestone A. The ongoing progress of STF 548 work fully meets the main STF target of producing by the end of this STF work an updated version of well documented TTCN-3 reference test specification.

- Progress of the work

# Add amount of resource spent.

# The following required tasks have been completed already:

- Analysis of changes in the core language between 4.8.1 and 4.9.1

- Update of PICS, test purposes, and existing conformance tests

- Partly completed: Extension of implementation conformance statement (ICS).

- Partly completed: Extension of test suite structure and test purposes - mainly for part 1 (TSS & TP).

- Partly completed: Extension of abstract test suite (ATS) and IXIT including validation on multiple tools

# The following required tasks remain to be completed in the next phase of STF548 work:

- Validation of tests on multiple tools

- Complete extension of implementation conformance statement (ICS).

- Complete extension of test suite structure and test purposes - especially for part 9 (TSS & TP).

- Complete extension of abstract test suite (ATS) and IXIT including validation on multiple tools

- Assessment of technical risk, difficulties encountered/expected, unresolved issues

As the preceding STFs have provided a sound methodological basis for this work, there have been no  technical difficulties with the STF 548 to date. One risk is the slow progress with part 9 test cases development, which causes approximately one month delay with the completion of milestone A. However, we expect to catch up during validation phase, and to complete the STF work as planned by end of September.

- Proposed changes in the STF work plan

The current STF Work Plan is confirmed. The completion of milestone A is projected by end of June, one month delayed from the originally planned schedule. We expect to complete the STF work nevertheless according to the originally planned time schedule.

- Resources requirements

No additional resources are required to complete the STF work.

The resource spending to date has been approximately the following:

- Elvior: 17 days effort (approximately 50% of total)

- BroadBit: 15 days effort (approximately 50% of total)

- Changes in the STF Team

No changes have occurred in the team.

- Meetings/events attended on behalf of the STF

Remote meeting attendance for the MTS#74 meeting.

- Meetings/events planned to be attended

| Date | Place | TB/Orga | Event description | Reason to attend | Expert(s) |
| --- | --- | --- | --- | --- | --- |
|  |  | MTS | #75 meeting | Final results presentation | Andras Kovacs |

- STF communications, presentations, promotion, inside and outside ETSI, WEB pages etc

There has been no external communication yet.

- Technical advice required from the reference Technical Body

No technical advice is currently required from MTS TB.

- Status of the deliverables

Draft (unvalidated) test cases have been uploaded onto the ETSI portal among MTS#74 meeting contributions.

- Next report

Planned date for the next report: at MTS#75 meeting (September 2018).

- Any other business