## Slide 1: MTS TDL Working Group Status Period: Jan 2021 – May 2021
11-May-2021
Andreas Ulrich WG Chairman
MTS#83

## Slide 2: WG Activities
Setup of new TTF 013 on TDL/TOP evolution and Restful API testing
  Preparatory meeting 04-Feb-2021
  Start of work in March 2021
  Final drafts until end of 2021
Open TDL/TTF meeting 10-Mar-2021
  With participation of 3 guests
  Expectations on TDL and TOP

## Slide 3: Open TDL / TTF Meeting Discussion
Skip distinction between two separate languages for Test Objectives and Test Descriptions
  Observation: People use of TDL-TO but forget about TDL core
Support for protocol specifications
  Observation: Need for native data type support in TDL to handle (i.e. “map”) protocol specs such as ASN.1 automatically
  Besides ASN.1, similar issue occurs for any interface specification language, including OpenAPI

## Slide 4: Next Activities
TDL WG / TTF Meeting on 19-May-2021
  Discussion of achievements
  Progressing on execution of TDL specs for an Open API example
Interest for a TDL TTF in 2022?

## Slide 5: TDL/TOP Roadmap
Year | TDL | TOP | Methodology
2021 | Standardise a default TDL TO/TD textual syntax (indentation based) (reqs on syntax to be discussed) | Support for tabular data values specifications in TDL specifications (to be covered also in TDL) | Elaborate a defined way to derive TDs from TOs; provide guidelines for a semi-automatic workflow
 | Extensions towards parameterizable test objectives and re-usable events in TDL-TO | TDL execution engine to support RESTful API testing | Req solicitation for testing of AI systems (self-adaptive systems)
 | Language features to better support RESTful API testing using OpenAPI – t.b.detailed (extension or base lang.) | Support of OpenAPI for data type specs in TOP | 
2022 | Besides functional tests, test specification support of further testing kinds such as stochastic tests (endurance and performance), adaptive tests (of intelligent systems), security tests (attack patterns) etc. |  | 
 | Elaborate on an execution semantics for TDL specifications to provide direct execution of TDL specifications, e.g. within a containerized architecture |  | 
 | Methodology + guideline for interoperability testing of AI systems (self-adaptive systems) |  | 
2022+ | Provide an approach, based on model transformation and meta-modelling, to map TDL specifications to arbitrary general-purpose language |  | 
 | Methodology support and tool support for reverse engineering of TDL specifications from structured data (e.g. TDL) |  | 
Covered in TTF T013

## Slide 6: BACKUP

## Slide 7: Current Standards
TDL standard series
  ETSI ES 203 119-1 V1.5.1 (2020-08): Abstract Syntax and Associated Semantics
  ETSI ES 203 119-2 V1.4.1 (2020-08): Graphical Syntax
  ETSI ES 203 119-3 V1.4.1 (2020-08): Exchange Format
  ETSI ES 203 119-4 V1.4.1 (2020-08): Structured Test Objective Specification (Extension)
  ETSI ES 203 119-5 V1.1.1 (2018-05): UML Profile for TDL
  ETSI ES 203 119-6 V1.2.1 (2020-08): Mapping to TTCN-3
  ETSI ES 203 119-7 V1.2.1 (2020-08): Extended Test Configurations
TOP description
  ETSI TR 103 119 V1.2.1 (2020-09): Reference Implementation

## Slide 8: Current WIs – Handled in TTF 013
WIs appear under MTS, but not under MTS TDL

## Slide 9: Scope of TTF T013 as stated in ToR
TDL phase 6: Enhancements + RESTful API services testing
Timeframe: Feb 2021 – Mar 2022
Requested budget: 108,600 €
Planned efforts comparable with previous STFs

## Slide 10: TTF Task 1: TDL Evolution
Standardised textual syntax for TO and TD, indentation-based
Parameterizable test objectives
Re-usable events in TDL-TO
New language features for supporting RESTful API services testing through their OpenAPI interface specification

## Slide 11: TTF Task 2: TOP Maintenance + RESTful API Services
Implement the elaborated workflow for RESTful API services testing from Task 3
Provision of a TDL-TD code generator and execution engine to support the execution of RESTful API services tests

## Slide 12: TTF Task 3: TDL Methodology
Elaborate a defined way to derive TDs from TOs; provide guidelines for a semi-automatic workflow
Elaborate a workflow to specify TOs/TDs for RESTful API services starting from an OpenAPI specification in accordance with EG 203 647
Demonstrate and describe the application of TOP for RESTful API Services testing
Solicitation of requirements for describing tests of AI systems and ML models