## Slide 1: TTF T023 conformance tests (task T2) progress/status report
25/01/2023
MTS#88
1
Axel Rennoch

## Slide 2: Overview
2
Team:
Elvior, Nokia, FOKUS
Now without Broadbit, Ericsson, Spirent
August 2022
  Completion of contracts
September 2022
  First working session (online)
October-December 2022
  Remote working / overlapping with evolution task

## Slide 3: Details on Conformance task
3
Migration of “old” SVN repository to ETSI forge
Public repository structure and contents https://forge.etsi.org/rep/mts/ttcn3-conformance-tests
Changes/Tests for 2021 edition done by previous TTF
Validation of tests done in parallel with different tools (and tool releases)
Consolidation of results from the different tools in progress
New Conformance tests “follows” evolution task (new changes for 2022 edition)
So far no technical risks BUT delay of the deliverables

## Slide 4: Summary & future steps
4
TTF task T2 is following the planning BUT milestone B is delayed
Consolidation of the tool results in progress (due to e.g. application of multiple releases of tools)
Provision of two delayed deliverables “stable drafts” (core and OO), each three parts (ICS, TSS&TP, ATS) in February, final drafts in May
Preparation of upcoming changes (from 2022 evolution)

## Slide 5
Follow us on:
Thank you for your attention

## Slide 6
Any further questions?