|  |  |
| --- | --- |
|   |  |
| **Title\*:** | **TC MTS work programme summary** as of 2023.09.22 | IntroductionThe present contribution provides a snapshot of TC MTS work programme. As of today, **29 WIs are in development**.Please use revision marks to suggest changes  |
| from **Source**\*: | ETSI |
| Contact: | Laurent Vreck  |
| input for **Committee**\***:** | MTS  |
| Submission date**\***: | 2023.09.22 |
|  |  |

# SUMMARY view of work in development

Note: hyperlinks under WI References link to detailed Work Item information on ETSI portal, the Version hyperlinks link to the latest draft file (at snapshot time).

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Reference** | **Rapporteur** | **Adoption Date** | **Current status** | **Since** | **Current Ver** | **Early Draft** | **Stable Draft** | **Final draft for approval** | **MTS Approval** | **PUB plan** | **PUB As\_v** | **Comments** |
| [(103 253) RTS/MTS-103253V181 "TTCN-3 tool conformance in using XML Schema: ICS"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=66108) | Axel RENNOCH | 2022.04.25 | Start of work | 2022.08.27 |  | 2024.01.27 | 2024.03.23 | 2024.04.28 | 2024.05.26 | 2024.07.07 | 1.8.1 |  |
| [(103 254) RTS/MTS-103254v181](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=66109) | Axel RENNOCH | 2022.04.25 | Start of work | 2022.07.7 |  | 2023.09.30 | 2024.01.26 | 2024.03.31 | 2024.04.28 | 2024.06.09 | 1.8.1 |  |
| [(103 255) RTS/MTS-103255v181](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=66110) | Axel RENNOCH | 2022.04.25 | Start of work | 2022.07.7 |  | 2023.09.30 | 2024.01.26 | 2024.03.31 | 2024.04.28 | 2024.06.09 | 1.8.1 |  |
| [(103 663-1) RTS/MTS-103663v141](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=66111) | Axel RENNOCH | 2022.04.25 | Start of work | 2023.07.7 |  | 2023.09.29 | 2024.01.26 | 2024.03.31 | 2024.04.28 | 2024.06.09 | 1.4.1 |  |
| [(103 663-2) RTS/MTS-103663-2v1.4.1](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=66112) | Axel RENNOCH | 2022.04.25 | Start of work | 2023.07.7 |  | 2023.09.29 | 2024.01.26 | 2024.03.31 | 2024.04.28 | 2024.06.09 | 1.4.1 |  |
| [(103 663-3) RTS/MTS-103663-3v141](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=66114) | Axel RENNOCH | 2022.04.25 | Start of work | 2023.07.7 |  | 2023.09.30 | 2024.01.27 | 2024.03.31 | 2024.04.21 | 2024.06.02 | 1.4.1 |  |
| [(103 910) DTR/MTS-103910](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=62502) | Juergen GROSSMANN | 2021.01.27 | Early draft | 2023.06.2 | [0.0.6](https://docbox.etsi.org/MTS/MTS/07-Drafts/001191167/MTS-103910v006.docx) | **2023.06.02** | 2023.12.15 | 2024.05.15 | 2024.05.30 | 2024.07.11 | 1.1.1 |  |
| [(103 911) DTR/MTS-1191168](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=62511) | Jens GRABOWSKI | 2021.01.27 | TB adoption of WI | 2021.01.27 |  | 2021.04.30 | 2021.11.30 | 2021.12.15 | 2022.01.31 | 2022.03.14 | 1.1.1 | No progress since Jan 2021: candidate for stopping  |
| [(104 008) DTS/MTS-6756"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=68039) | Dorian KNOBLAUCH | 2023.03.16 | Early draft | 2023.06.1 | [0.0.2](https://docbox.etsi.org/MTS/MTS/07-Drafts/006756/MTS-6756v002.docx) | **2023.06.01** | 2024.02.06 | 2024.07.15 | 2024.08.15 | 2024.09.26 | 1.1.1 | Should WI reference be updated to 104 008? |
| [(201 873-1) RES/MTS-2018731v4.16.1 "TTCN-3 Core ed4.16.1"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=68552) | Jens GRABOWSKI | 2023.05.03 | TB adoption of WI | 2023.05.3 |  | 2023.09.28 |   | 2023.12.29 | 2024.01.30 | 2024.05.11 | 4.16.1 |  |
| [(201 873-4) RES/MTS-201873-4 T3ed471 "TTCN-3 Edition 4.5.1: OS"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=50948) | Jens GRABOWSKI | 2016.11.18 | Start of work | 2022.06.15 |  |   |   | 2023.12.30 | 2024.01.29 | 2024.05.10 | 4.7.1 |  |
| [(201 873-5) RES/MTS-201873-5v4.10.1 "TTCN-3: TRI"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=64430) | Jens GRABOWSKI | 2022.04.05 | Start of work | 2022.06.15 |  |   |   | 2023.12.30 | 2024.01.27 | 2024.05.08 | 4.10.1 |  |
| [(201 873-6) RES/MTS-20187316v4.15.1 "TTCN-3 TCI V4121"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=68568) | Jens GRABOWSKI | 2023.05.03 | TB adoption of WI | 2023.05.3 |  | 2023.09.29 | 2023.11.24 | 2023.12.29 | 2024.01.30 | 2024.05.11 | 4.15.1 |  |
| [(201 873-7) RES/MTS-201873-7v4.11.1 "TTCN-3: the use of ASN.1"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=64432) | Jens GRABOWSKI | 2022.04.05 | Start of work | 2022.06.16 |  |   |   | 2023.12.30 | 2024.01.27 | 2024.05.08 | 4.11.1 |  |
| [(201 873-8) RES/MTS-2018738v491 "TTCN-3: IDL"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=63086) | Tomas URBAN | 2021.06.10 | Start of work | 2022.06.15 |  |   |   | 2023.12.31 | 2024.01.29 | 2024.05.10 | 4.9.1 |  |
| [(201 873-9) RES/MTS-201873-9v4131 "TTCN-3 XSD V4111"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=63087) | Tomas URBAN | 2021.06.10 | Start of work | 2022.06.10 |  |   |   | 2023.12.31 | 2024.01.29 | 2024.05.10 | 4.13.1 |  |
| [(201 873-10) RES/MTS-201873-10 T3ed461 "TTCN-3: T3Doc"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=41264) | Tomas URBAN | 2012.11.19 | Start of work | 2020.06.20 |  |   |   | 2023.12.30 | 2024.01.30 | 2024.05.11 | 4.6.1 |  |
| [(201 873-11) RES/MTS-20187311 "TTCN-3 ed. V4.9.1: Use of JSON"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=68569) | Jens GRABOWSKI | 2023.05.03 | TB adoption of WI | 2023.05.3 |  | 2023.09.29 | 2023.11.30 | 2023.12.30 | 2024.01.27 | 2024.05.08 | 4.11.1 |  |
| [(202 781) RES/MTS-202781v1.10.1 "TTCN-3 extension: Configuration & Deployment support"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=64433) | Jens GRABOWSKI | 2022.04.05 | Start of work | 2022.06.15 |  |   |   | 2023.12.30 | 2024.01.27 | 2024.05.08 | 1.10.1 |  |
| [(202 782) RES/MTS-202782v151 "TTCN-3 RealtPerf V131"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=64490) | Jens GRABOWSKI | 2022.04.05 | Start of work | 2022.06.15 |  |   |   | 2023.12.30 | 2024.01.27 | 2024.05.08 | 1.5.1 |  |
| [(202 784) RES/MTS-202784v1.10.1 "TTCN-3 extension: Advanced Parameterization"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=64453) | Jens GRABOWSKI | 2022.04.05 | Start of work | 2022.06.15 |  |   |   | 2023.12.30 | 2024.01.27 | 2024.05.08 | 1.11.1 |  |
| [(202 785) RES/MTS-202785v1.10.1 "TTCN-3 BehTypes V171"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=64454) | Jens GRABOWSKI | 2022.04.05 | Start of work | 2022.06.15 |  |   |   | 2023.12.30 | 2024.01.26 | 2024.05.07 | 1.11.1 |  |
| [(202 786) RES/MTS-202786v1.6.1 "TTCN-3 extension: Continuous Signal support"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=64455) | Jens GRABOWSKI | 2022.04.05 | Start of work | 2022.06.15 |  |   |   | 2023.12.29 | 2024.01.27 | 2024.05.08 | 1.6.1 |  |
| [(202 789) RES/MTS-202789v171](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=64456) | Jens GRABOWSKI | 2022.04.05 | Start of work | 2022.06.15 |  |   |   | 2023.12.30 | 2024.01.27 | 2024.05.08 | 1.7.1 |  |
| [(203 022) RES/MTS-203022v161](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=64457) | Jens GRABOWSKI | 2022.04.05 | Start of work | 2022.06.15 |  |   |   | 2023.12.30 | 2024.01.27 | 2024.05.08 | 1.6.1 |  |
| [(203 790) RES/MTS-203790v161 "TTCN3ext\_OOed111"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=64458) | Jens GRABOWSKI | 2022.04.05 | Start of work | 2022.06.15 |  | 2023.07.20 | 2023.09.29 | 2023.12.30 | 2024.01.27 | 2024.05.08 | 1.5.1 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |
| [(103 942) DTS/MTS-TST10SecTest\_IoTmodule "IoT security module testing"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=66187) | Marija JANKOVIC | 2022.05.18 | With EditHelp | 2023.09.6 | [0.1.2](https://docbox.etsi.org/MTS/TST/70-Draft/TST10SecTest_IoTmodule/MTS-TST10SecTest_IoTmodulev012.docx) |   |   |   | 2023.09.06 | 2023.10.04 | 1.1.1 | 2023.09.22 🡪 wih EditHelp |
| [(103 946) DTR/MTS-TST11Sec\_IoTconf "IoT security architecture conformity"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=66188) | Klaus-Peter HOFMANN | 2022.05.18 | With EditHelp | 2023.09.4 | [0.1.2](https://docbox.etsi.org/MTS/TST/70-Draft/TST11Sec_IoTconf/MTS-TST11Sec_IoTconfv012.docx) |   |   |   | 2023.09.04 | 2023.10.02 | 1.1.1 | 2023.09.22 🡪 wih EditHelp |
|  |  |  |  |  |  |  |  |  |  |  |  |  |
| [(203 119-1) RES/MTS-TDL2031191 "TDL Meta-Model"](http://webapp.etsi.org/WorkProgram/Report_WorkItem.asp?WKI_ID=65123) | Andreas ULRICH | 2022.04.28 | With EditHelp | 2023.07.27 | [1.7.1](https://docbox.etsi.org/MTS/TDL/70-Draft/TDL2031191/MTS-TDL2031191v171.docx) |   |   |   | 2023.07.27 | 2023.12.08 | 1.7.1 | MV scheduled to start on 25 Sept, |
|  |  |  |  |  |  |  |  |  |  |  |  |  |