STF 280 (PD2) on Preparation for endorsement of relevant 3GPP IMS Technical specifications for TISPAN_NGN Release 1 (TISPAN WG2/3 Architecture/ Protocols)

Participants

| Mr. Alain Le Roux | TISPAN Chairman | alainxavier.leroux@francetelecom.com |
| --- | --- | --- |
| Mr. Ian Spiers | TISPAN Vice Chairman | ian.spiers@marconi.com |
| Mr Christian Julien | ETSI Technical Editor | christian.julien@etsi.org |
| Mr. Alberto Berrini | STF Manager | alberto.berrini@etsi.org |

Candidates:

| Prof. Tatiana Kovacikova | University of Zilina / France Telecom | tatiana.kovacikova@frkis.utc.sk |
| --- | --- | --- |
| Prof. Pavol Segec | University of Zilina / France Telecom | pavol.segec@frkis.utc.sk |
| Mr. Scott Cadzow | Cadzow Communications | scott@cadzow.com |
| Mr. Esbjorn Engberg | Ericsson AB | esbjorn.engberg@telia.com |

On audioconference (part 2 only)

| Mr. Martin Niekus | TISPAN WG2 | mniekus@lucent.com |
| --- | --- | --- |
| Mr. Ray Forbes | TISPAN WG3 Chairman | raymond.forbes@marconi.com |
| Mr. Klaus Pulverer | TISPAN WG2 vice-Chair | klaus.pulverer@siemens.com |

Copy

| Mr. Pierre de Courcel | CFO | pierre.decourcel@etsi.org |
| --- | --- | --- |
| STF support |  | stfsupport@etsi.org |

# Introduction

The Preparatory Meeting has been held jointly with STF 281 (PD3) on Development and Verification of PSTN/ISDN emulation, proceeding first with the selection of experts for both STFs and then continue with the experts selected to plan the two STFs.

The meeting has been co-chaired by Mr. Alain Le Roux and Mr. Ian Spiers.

The participants made a short “round the table” presentation.

# Agenda:

The following agenda was approved:

Part 1: experts’ selection (8:30 – 10:00)

- Approval of the agenda

- Introduction of participants

- Short introduction to the ETSI STF concept and specific activity of STF PD2

- Personal interviews

- ETSI selection panel meeting (confidential)

- Final decision on the selection of experts and of the STF Leader

Part 2: STF planning (jointly with STF PD3) 11:00 –14:00

- Review of the STF Terms of Reference

- Identification of tasks

- Distribution of tasks

- Manpower allocation (resource and duration)

- Steering Group, liaison with the reference TB and other interested bodies

- Deliverables schedule

- Contractual milestones, reports preparation and approval

- Sessions schedule

- Travel plan

- Document exchange areas, access rights, docbox, ETSI Portal, STF presentation pages

- Administrative requirements: travel authorization, time-log, reports, role of the leader

- Information for the establishment of the contracts

- Practical information to settle in the area of Sophia Antipolis

- Reimbursement travel cost for Preparatory Meeting

- Any other business

# STF concept and funding

Alberto Berrini presented the ETSI STF concepts and practice.

The ETSI concept is that STF experts normally work together in Sophia Antipolis.  The STF must work according to the ToR approved by the Board.  The draft deliverables produced by the STF will be submitted for approval by the reference TB.  The STF will ensure that the draft they are producing will get approval in the TB, by ensuring frequent co-ordination meetings with the TB/WG.  The work within the STF is organized by the STF leader, in co-ordination with the reference TB for technical guidance and the ETSI Secretariat for the management of resources.

This STF is funded by the ETSI Members statutory contributions, under the ETSI STF budget, which is allocated by the ETSI Board.

Ian Spiers reminded that, in addition to the ETSI funding, the active participation of the ETSI Members with voluntary contribution in the TB is essential for the success of the STF.

# Personal interviews and selection of experts

The experts have been interviewed individually by the selection panel, constituted by Messrs. Alain Le Roux, Ian Spiers, Christian Julien and Alberto Berrini.

All the candidates have been found suitable for the task and have been appointed as STF experts:

- Prof. Tatiana Kovacikova

- Prof. Pavol Segec

- Mr. Scott Cadzow

- Mr. Esbjorn Engberg

Scott Cadzow will be the STF Leader.

The selection panel considered that this choice of the experts offers a fair mix of experience to cover the tasks required in the ToR.

The STF budget is 160 working days, with no allowance for travel cost.

Preliminary resources allocation is, in principle, 40 working days for each expert.  The exact distribution of resources between the experts will be refined when making the detailed plan and may require adjustments.  Moreover, if the Leaders will have to attend TB/WG meetings outside ETSI, the corresponding resources must be made available by reducing the number of working days.

The work will be done in sessions in Sophia Antipolis.  It has been agreed that Prof. Segec can spend a half of the working days as home, since he can easily co-ordinate with Prof. Tatiana Kovacikova.

Work permit (APT) is required for Prof. Tatiana Kovacikova and Prof. Pavol Segec.

# Review of Terms of Reference

The ToRs have been reviewed, with particular regard to the time scale and the milestones in §3.10.

# STF sessions plan

The initial sessions plan is in the attached EXCEL sheet.  The STF will complete the sessions plan during their session from 21 to 25 March.

The initial sessions plan will be transferred by the ETSI Secretariat into the Time Allocation Management WEB application (TAM) and will constitute the reference plan for the STF working sessions.  Changes must be agreed between the experts, the Leader and the STF Manager, before being recorded in TAM.

# Initial contracts

As a result of the initial planning that took place during the meeting and proposed for agreement in these minutes the initial contracts shall be as follows

- Scott Cadzow	26 working days	from 07/02 to 30/09

- Tatiana Kovacicova	24 working days	from 28/02 to 30/09

- Esbjorn Engberg	19 working days	from 21/02 to 30/09

- Pavol Segec	29 working days	from 21/02 to 30/09

The initial contracts cover the whole duration of the STF, which must provide the final deliverables before end September.  Extension of resources, within this period, will be provided when the sessions plan will be completed.

# STF reporting, milestones and deliverables schedule

The following milestones have been agreed and will be included in the experts’ LoE:

- Milestone A: Progress Report, with the description of the base architecture and the identification of the 3GPP IMS-base specifications to be addressed, to be presented to TISPAN#5bis meeting for review, ready on 4 March 2005.

- Milestone B: Progress Report, with the identification of potential issues in the base IMS specifications, for review by TISPAN#6 (9-13 May), ready on 29 April 2005.

- Milestone C: Progress Report, with the resolution of issues identified in Milestone B and by TISPAN and preliminary DTR/03032-NGN-R1 draft, including at least ToC, scope, structure, for review by TISPAN#7 11-16 July, ready on 1 July 2005.

- Milestone D: Progress Report, with the final version of the draft DTR/03032-NGN-R1, for review and approval at TISPAN#8 (12-16 September 2005), ready on 2 September 2005.

- Milestone E: Final Report and DTR/03032-NGN-R1 ready for publication after inclusion of comments, on 30 September 2005.

The STF will provide the deliverable DTR/03032-NGN-R1 ready for publication by 30 September 2005.

The ETSI template for the Progress Report, the Interim Report and the Final Report can be found on the ETSI Portal.

Two weeks before the date the report is due by the STF Leader, the ETSI Secretariat will send a template, initialized with the information relevant to the milestone to the STF Leader.

# Travel plan

There is no travel budget for this STF.  The STF sessions are scheduled jointly with the TISPAN meetings, to save travel cost.  However, TISPAN#8 will be in Lubiana.  If required to fund the travel of the leader to present the result, 2-3 days of the manpower budget will be converted into travel cost.

# Support from the ETSI Secretariat

STF folders on “docbox”

A folder has been created on the ETSI Server (docbox) to exchange documents, at the following address: http://portal.etsi.org/docbox/STF/STF280_TISPAN_3GPP_IMS/ .  This folder contains a “Public” area, accessible to all ETSI-on-Line users and a “STFworkarea”, with access restricted to the STF experts, the Technical Officer, the TB Chairman, the STF Manager and the STF support team).  These people can include additional users, as required, using the ETSI Access Rights Management (ARM) application: http://webapp.etsi.org/ARM/ .

Initially, access to STF docbox restricted area will be granted to the following people:

- The experts of both STF 280 and 281

- Mr. Alain Le Roux	TISPAN Chairman

- Mr. Martin Niekus	TISPAN WG2

- Mr. Ray Forbes	TISPAN WG3 Chairman

- Mr. Klaus Pulverer	TISPAN WG2 vice-Chairman

- Mr. Christian Julien	TISPAN support officer

- Mrs. Aline Luther	TISPAN support assistant

- Mr. Alberto Berrini	STF support

- STFLINK	STF support

STF folders in the internal ETSI NW (H and P drives)

The STF will also have two folders in the internal ETSI network, a “Private” area (called H:\STF280) and a “Public area (called P:\STF280).  The write access to these areas is restricted to the STF experts only.  The “P” area is accessible “read only” to all users in the internal ETSI network.

Creating a mixed access or a common area for both STF is possible but may create difficulties for the internal ETSI IT management.  It is recommended that, in the beginning, the two STFs are assigned separate areas and that the “P” area is used by to share documents between the two STFs.  If this appears to be impractical, the opportunity to create a common area will be considered between the leaders, the STF Manager and the IT service.

Mailing list

Christian Julien will create a mailing list for the STF.

STF presentation page on the ETSI Portal

A presentation page for the STF will be created on the ETSI Portal.  This page can be used as a “hook” to advertise the STF results and share documents for discussion inside and outside ETSI.  The page is accessible from the STF information boxes on the Portal however, its URL can be referred from other WEB pages.   Ms. Fabienne Chastanet (fabienne.chastanet@etsi.org) will create an initial page for the STF and can provide help to improve and publish this page, based upon the information provided by the Leader and the TB.  Support can also be provided for the including organization of events, design of leaflets and WEB pages.  An example is: http://portal.etsi.org/STFs/ESI/STF263.asp

STFLINK

If you do not know the person who deals with a particular topic, you can address your requests regarding STFs to “STFLINK” (STFLINK@etsi.org, tel. +33 4 9294 4950).  They will dispatch take your requests to the relevant services.

# Attachments:

The following documents are integral part of these minutes:

ToR STF280, revised during the Preparatory Meeting (attached to e-mail)

Initial Sessions Plan (attached to e-mail)

Annex A: Reference information on STF process (useful addresses)

Annex A:  Reference Information on STF process (useful addresses)

The reference information and contact persons concerning the STF management process and requirements can be found at the following addresses:

| ETSI WEB site | http://www.etsi.org/ |
| --- | --- |
| ETSI Portal | http://portal.etsi.org/ |
| STF reference Information | http://portal.etsi.org/Portal_STF/FullSearch.asp?Param |
| STF management process | http://portal.etsi.org/stfs/process/home.asp |
| STF working conditions | http://portal.etsi.org/stfs/process/item6_STFwork/item6_A_STFWork.asp |
| STF “contractual” conditions | http://portal.etsi.org/stfs/process/item5_Contr&Invoice/item5_A_LoEconditions.asp |
| STF Travel application | http://webapp.etsi.org/travel/ |
| Time Allocation Management (TAM) | http://webapp.etsi.org/STF_TAM/ |
| STFLINK (STF support) | mailto:STFLINK@etsi.org tel: +33 4 9294 4950 |
| EditHelp (standards drafting support) | http://portal.etsi.org/edithelp/home.asp mailto:edithelp@etsi.org |
| HelpDesk (IT support) | http://portal.etsi.org/helpdesk/home.asp tel: +33 4 9294 4900 |
| Protocol and Testing Competence Centre (PTCC) | http://www.etsi.org/technicalfocus/home.htm |
| Mr. Alberto Berrini (STF Manager) | mailto:alberto.berrini@etsi.org tel: +33 4 9294 4264 |
| Mrs. Pascale Georges (LoE) | mailto:pascale.georges@etsi.org tel: +33 4 9294 4348 |
| Ms. Fabienne Chastanet (WEB pages, reports, planning) | mailto:fabienne.chastanet@etsi.org tel: +33 4 9294 4345 |
| Ms. Marithé Carlier (Invoicing and travel) | mailto:marithe.carlier@etsi.org tel: +33 4 9294 4325 |
| Mrs. Christine Voulgre (Work Permit) | mailto:christine.voulgre@etsi.org tel: +33 4 9294 4269 |
| Ms. Lucy Navas (Trainee) | mailto:lucy.navas@etsi.org tel: +33 4 9294 4268 |