## STFs 280&281 Sessions 05
STFs 280 and 281 - Sessions plan Year 2005
|  |  | STF 280 | [7 empty] | STF281
from | to | week | SC |  | TK |  | EE |  | Pavol |  | Pietro |  | SC |  | Peter |  | SR |  | EE |  | Milestones STF280 | Milestones STF281
2005-01-31 | 2005-02-04 | 5 | [18 empty] | Prep. Meet 3/2/05 | Prep. Meet 3/2/05
2005-02-07 | 2005-02-11 | 6 | H | 2 | [6 empty] | H | 2
2005-02-14 | 2005-02-18 | 7 | H | 2 | [6 empty] | H | 2
2005-02-21 | 2005-02-25 | 8 | E | 2.5 |  |  | E | 3 | E | 5 | E | 5 | E | 2 |  |  |  |  | E | 2
2005-02-28 | 2005-03-04 | 9 | E | 2 | E | 5 | E | 3 | E | 5 | E | 5 | E | 2.5 |  |  | E | 5 | E | 2 | Prog. Rep#1 Base architecture (Milestone A) TISPAN#5bis | Prog. Rep#1 Milestone A TISPAN#5bis
2005-03-07 | 2005-03-11 | 10
2005-03-14 | 2005-03-18 | 11
2005-03-21 | 2005-03-25 | 12 | E | 3 | E | 4 | E | 2 | H | 4 | E | 4 | E | 1 | E | 4 | H | 2 | E | 2 | Friday off - Update session plan | Friday off - Update session plan
2005-03-28 | 2005-04-01 | 13 | [18 empty] | Easter week
2005-04-04 | 2005-04-08 | 14
2005-04-11 | 2005-04-15 | 15
2005-04-18 | 2005-04-22 | 16
2005-04-25 | 2005-04-29 | 17 | E | 2.5 | E | 5 | E | 3 | E | 5 | E | 5 | E | 2.5 | E | 5 | E | 3 | E | 2 | Prog. Rep#2 Identify potential issues in basic IMS specs (Milestone B) | Prog. Rep#2 Milestone B
2005-05-02 | 2005-05-06 | 18
2005-05-09 | 2005-05-13 | 19 | E | 1.5 | [6 empty] | E | 2 | E | 1.5 | [6 empty] | TISPAN#6 | TISPAN#6
2005-05-16 | 2005-05-20 | 20
2005-05-23 | 2005-05-27 | 21
2005-05-30 | 2005-06-03 | 22
2005-06-06 | 2005-06-10 | 23
2005-06-13 | 2005-06-17 | 24
2005-06-20 | 2005-06-24 | 25
2005-06-27 | 2005-07-01 | 26 | E | 2.5 | E | 5 | E | 3 | H | 5 | E | 5 | E | 2.5 | E | 5 | E | 5 | E | 2 | Prog. Rep#3 Milestone C | Prog. Rep#3 Milestone C
2005-07-04 | 2005-07-08 | 27
2005-07-11 | 2005-07-15 | 28 | E | 1.5 | [6 empty] | E | 2 | E | 1.5 | [6 empty] | TISPAN#7 | TISPAN#7
2005-07-18 | 2005-07-22 | 29
2005-07-25 | 2005-07-29 | 30
2005-08-01 | 2005-08-05 | 31
2005-08-08 | 2005-08-12 | 32
2005-08-15 | 2005-08-19 | 33
2005-08-22 | 2005-08-26 | 34
2005-08-29 | 2005-09-02 | 35 | E | 5 | E | 5 | E | 5 | E | 5 | E | 5 |  |  | E | 5 | E | 5 |  |  | Prog. Rep.#4 Milestone D | Prog. Rep.#4 Milestone D
2005-09-05 | 2005-09-09 | 36
2005-09-12 | 2005-09-16 | 37 | M | 1 | [6 empty] | M | 1 | [8 empty] | TISPAN#8 Lubiana | TISPAN#8 Lubiana
2005-09-19 | 2005-09-23 | 38 | [18 empty] | Inclusion of comments | Inclusion of comments
2005-09-26 | 2005-09-30 | 39 | [18 empty] | Final Report (TR ready for publication) Milestone E | Final Report (TR ready for publication) Milestone E
2005-10-03 | 2005-10-07 | 40
2005-10-10 | 2005-10-14 | 41
2005-10-17 | 2005-10-21 | 42
2005-10-24 | 2005-10-28 | 43
2005-10-31 | 2005-11-04 | 44
2005-11-07 | 2005-11-11 | 45
2005-11-14 | 2005-11-18 | 46
2005-11-21 | 2005-11-25 | 47
2005-11-28 | 2005-12-02 | 48
2005-12-05 | 2005-12-09 | 49
2005-12-12 | 2005-12-16 | 50
2005-12-19 | 2005-12-23 | 51
2005-12-26 | 2005-12-30 | 52
|  | days | 25.5 |  | 24 |  | 19 |  | 29 |  | 38 |  | 13.5 |  | 19 |  | 20 |  | 10 |  | 97.5 | 100.5
|  | ETSI |  | 20.5 |  | 24 |  | 19 |  | 20 |  | 33 |  | 13.5 |  | 19 |  | 18 |  | 10 | 83.5 days in ETSI | 93.5 days in ETSI
Total per expert |  |  |  | 39 |  | 24 |  | 29 |  | 29 |  | 38 |  |  |  | 19 |  | 20 |  |  | 21.09% | 38.02%
[19 empty] | Ex. |  | Codes: 1 letter for the location 1 figure for the number of days (e.g. E5 = 5days in ETSI) | Codes: 1 letter for the location 1 figure for the number of days (e.g. E5 = 5days in ETSI)
[19 empty] | E | 5 | E = work in an ETSI session | E = work in an ETSI session
[19 empty] | C | 3 | C = work in STF co-ordination meetng (sessions) outside ETSI | C = work in STF co-ordination meetng (sessions) outside ETSI
[19 empty] | H | 0,5 | H = work at home (with ETSI autorisation) | H = work at home (with ETSI autorisation)
[19 empty] | M | 2 | M = mission travel (with ETSI autorisation) | M = mission travel (with ETSI autorisation)
Note on F6: Alberto Berrini: Off 14/2
Note on Q6: Alberto Berrini: 14/02
Note on S6: Alberto Berrini: Excl. Monday morning
Note on O7: Alberto Berrini: Half-Monday off
Note on S16: Alberto Berrini: Wen-Thu-Fri
Note on O18: Alberto Berrini: tbd
Note on M18: Alberto Berrini: tbd
Note on M27: Alberto Berrini: tbd
Note on O27: Alberto Berrini: tbd
Note on O8: Alberto Berrini: -0.5 Monday