STF287 (PF1) TB HF - User-oriented handling of multicultural issues in broadband and narrowband multimedia communications

Participants

| Mr. Stephen Furner | TC HF Chairman | stephen.furner@bt.com |
| --- | --- | --- |
| Mr. Alberto Berrini | STF Manager | alberto.berrini@etsi.org |

Candidates:

| Mr. Michael Andrew Pluke | Castle Consulting Ltd / BT Group Plc | mike.pluke@castle-consult.com |
| --- | --- | --- |
| Mr. Derek Pollard | Parity Ressources / BT Group Plc | derek@dpol.co.uk |
| Ms. Françoise Petersen | Apica IT / Tieto Enator Technical Cons. | francoise.petersen@apica.com |
| Miss Bianca Szalai | CAS Software AG / SIEMENS AG | bianca.szalai@cas.de |

Copy

| Mr. Pierre de Courcel | CFO | pierre.decourcel@etsi.org |
| --- | --- | --- |
| Mr. Ted Laverack | ETSI HF Support Officer | ted.laverack@etsi.org |
| STF support |  | stfsupport@etsi.org |
| Mr. Gavin Craik | EC/EFTA Mandate Officer | Gavin.craik@etsi.org |

# Introduction

The HF Chairman, Mr. Stephen Furner chaired the meeting.  Participants made a short “round the table” presentation.

# Agenda:

The following agenda was approved:

- Approval of the agenda

- Introduction of participants

- STF concepts and funding

- EC/EFTA contract requirements

- Performance indicators –responsibility to prepare the report, content guidelines, examples

- Accounting for expenditure under EC/EFTA contribution: TAM time sheets and travel cost

- Accounting for ETSI “in –kind” contribution (meetings, office use in ETSI)

- Review of the STF Terms of Reference

- Identification of tasks

- Interview and selection of experts and nomination of the STF Leader

- Distribution of tasks and manpower allocation (resource share and duration)

- Steering Group, liaison with the reference TB and other interested bodies

- Contractual milestones, reports preparation and approval, deliverables schedule

- Sessions schedule (min. 125 working days in ETSI)

- Travel plan

- Document exchange areas, access rights, docbox, ETSI Portal, STF presentation pages

- Administrative requirements: travel authorization, time-log, reports, role of the leader

- Information for the establishment of the contracts and Social Security certificates

- Practical information to settle in the area of Sophia Antipolis

- Reimbursement travel cost for Preparatory Meeting

- Any other business

# STF concept

The ETSI concept is that STF experts normally work together in Sophia Antipolis.  The STF must work according to the ToR approved by the Board.  The draft deliverables produced by the STF will be submitted for approval by the reference TB.  The work within the STF is organized by the STF leader, in co-ordination with the reference TB for technical guidance and the ETSI Secretariat for the management of resources.

# STF funding

The STFs may be funded either from the ETSI budget, the EC/EFTA or from voluntary contribution of Members.  This STF is funded by EC/EFTA.

A. Berrini gave a detailed description of the requirements related to the EC/EFTA funding for this STF funding (see also Annex B).

Total resources of 137 000 EUR are available from EC/EFTA to perform the STF work:

- Manpower: 117 000 EUR, corresponding to 195 working days, to be recorded by the experts in the ETSI Time Allocation Management (TAM) WEB application.

- Travels and stakeholder consultation: 20 000 EUR.   Travels must be authorized by ETSI with a Travel Order (using Travel Management WEB application).  Travel budget is to attend the following type of meetings: 5 HF plenary (STF Leader), input collection, liaison activities and result dissemination, Interviews with individual specialists and relevant companies (particular members of the Localization Industry Standards Association (LISA).  The participation in ETSI TB meetings on behalf of the STF will be recorded in the minutes.  For travels to workshops, events and/or meetings other than ETSI TBs, the expert must provide a report indicating the scope of his contribution, stakeholders attending, value for the STF work.

# ETSI co-funding contribution

In addition to the EC/EFTA funding, ETSI is engaged to provide a contribution in-kind for an equivalent amount of 58 800 EUR, split as follows:

- in-kind contribution: 45 000 EUR for 75 days attendance of delegates to meetings, corresponding to a total of 25 delegates*meetings (e.g. 5 delegates attending 5 meetings of 1 day duration + 1 day preparation + 1 day review).  This requires attendance lists signed on paper, to be collected by the Leader.  If the Leader does not attend, he/she must ensure that this task is properly delegated (e.g. the ETSI TO attending the meeting).

- In kind contribution of 13 800 EUR (23 man-days), for consultation of the Advisory Group, consisting of relevant technical, localization, human factors and other experts to guide the technical work of the STF

In addition, a minimum of 125 days must be spent by the experts working in ETSI premises, representing a hosting cost for ETSI of 25 000 EUR.  The minimum number of days to be spent in ETSI will be a contractual obligation for the experts.

The management of the ETSI contribution is the responsibility of the TB and the STF leader.  The ETSI Secretariat can provide support to administer this element.  The administrative provisions for the management of the ETSI contribution are provided in Annex C.

# Review of Terms of Reference

The Terms of Reference are based upon the ETSI Technical Proposal and are part of the contract with EC/EFTA.  The ToRs have been discussed and did require only minor updates.

# Planned working period and deliverables schedule

The STF will work from 11 April 2005 to end December 2006 and will provide the following deliverables:

- ETSI deliverable DEG/HF-00054: User-oriented handling of language issues in broadband multimedia communications: handling of language issues in broadband multimedia communications

- EC/EFTA deliverables: 	Interim Report in November 2005
	Final Report in December 2006

# Allocation of resources and contracts

All candidates have been found well qualified for this STF.  The four contracts will be made for the same period, from 11 April  2005 to 31 December 2006.  The resources allocation has been agreed as follows:

- Mr. Michael Andrew Pluke (STF Leader)	55 days	(min 24 days in ETSI)

- Mr. Derek Pollard	40 days	(min 22 days in ETSI)

- Ms. Françoise Petersen	40 days	(min 37 days in ETSI)

- Miss Bianca Szalai	40 days	(min 30 days in ETSI)

- Contingency	20 days	(min 12 days in ETSI)

- Total	195 days	(min 125 days in ETSI)

Miss Bianca Szalai has a Romanian passport.  Christine Voulgre explained that she will need a Work Permit, even is she is spending less than 89 days in ETSI.

The following milestones will be included in the experts’ LoE:

- Milestone A: Progress Report#1 referring of Table of Content & Scope of ETSI Guide completed, submitted to HF#37 (13-17 June) for review.  The Report will be prepared by the STF Leader, uploaded in the HF meeting documents and sent to STFLINK, two weeks before the meeting (27 May).

- Milestone B: Progress Report#2 referring of Initial Draft of ETSI Guide submitted to HF#38 (10-14 October 2005)* for review.  The Report will be prepared by the STF Leader, uploaded in the HF meeting documents and sent to STFLINK, two weeks before the meeting (23 September).

*Note, if the meeting is re-scheduled, the dates for this milestone will be shifted accordingly.

- Milestone C: Interim Report for EC/EFTA.  The Report will be prepared by the STF Leader and sent to STFLINK in November 2005.  The ETSI Secretariat will get confirmation of acceptance by EC/EFTA.  The process may require up to 60 days from reception of the Report.

- Milestone D: Progress Report#3 referring of Stable Draft ETSI Guide submitted to HF#39 (provisionally scheduled 6-10 February 2006)* for review.  The Report will be prepared by the STF Leader, uploaded in the HF meeting documents and sent to STFLINK, two weeks before the meeting (20 January).  *Note, the dates for this milestone may be shifted according to the actual meeting schedule.

- Milestone E: Progress Report#4 referring of approval of the final draft ETSI Guide by HF#41 (provisionally scheduled 16-20 October 2006).  The Report will be prepared by the STF Leader, uploaded in the HF meeting documents together with the draft EG for approval and sent to STFLINK, two weeks before the meeting (29 September).  *Note, the dates for this milestone may be shifted according to the actual meeting schedule.  Payment on Milestone E will be limited to 90% of the total contractual amount for the STF Leader.  The balance will be paid upon successful completion of the project, i.e. achievement of Milestone F.

- Milestone F: Final Report for EC/EFTA, referring of publication of ETSI Guide   The Report will be prepared by the STF Leader and sent to STFLINK in November 2006.  The ETSI Secretariat will get confirmation of acceptance by EC/EFTA.  The process may require up to 60 days from reception of the Report.

The ETSI template for the Progress Report, the Interim Report and the Final Report can be found on the ETSI Portal.

Two weeks before the date the report is due by the STF Leader, the ETSI Secretariat will send a template, initialized with the information relevant to the milestone to the STF Leader.

# STF sessions plan

The initial sessions plan is in the attached EXCEL sheet.  This initial sessions plan will be transferred by the ETSI Secretariat into the Time Allocation Management WEB application (TAM) and will constitute the reference plan for the STF working sessions.  Any changes must be agreed between the experts, the Leader and the STF Manager, before being recorded in TAM.  The experts will record the time spent at the end of each month (before the 7th of the following month).  The STF Leader will “validate” the time sheets before the 14th.

# Travel plan

The travel budget can be used to reimburse travel cost for the experts to attend the TB meetings and other meetings indicated in the ToR.

The travels will be entered by the STF Leader in the Travel Management WEB application (Travel Plan).  The expert concerned will prepare a Travel Order for ETSI approval before the travel.  The approval of the Travel Order is done through the TM application, without exchange of signed paper.  The expert will receive a confirmation code by automatic mail, which must be referenced in the reimbursement claim.

# Support from the ETSI Secretariat

STF folder on “docbox”

A folder has been created on the ETSI Server (docbox) to exchange documents, at the following address: http://portal.etsi.org/docbox/STF/STF287_HF_Multicultural/  .  This folder contains a “Public” area, accessible to all ETSI-on-Line users and a “STFworkarea”, with access restricted to the STF experts, the Technical Officer the AT Chairman, the STF Manager and his Assistant).  These people can include additional users, as required, using the ETSI Access Rights Management (ARM) application: http://webapp.etsi.org/ARM/ .

STF folders in the internal ETSI NW (H and P drives)

The STF will also have two folders in the internal ETSI network, a “Private” area (called H:\STF287) and a “Public area (called P:\STF287).  The write access to these areas is restricted to the STF experts only.  The “P” area is accessible “read only” to all users in the internal ETSI network.  The “P” area is used by to share documents with other STFs.

STF presentation page on the ETSI Portal

A presentation page for the STF will be created on the ETSI Portal.  This page can be used as a “hook” to advertise the STF results and share documents for discussion inside and outside ETSI.  The page is accessible from the STF information boxes on the Portal however, its URL can be referred from other WEB pages.   Ms. Fabienne Chastanet (fabienne.chastanet@etsi.org) will create an initial page for the STF and can provide help to improve and publish this page, based upon the information provided by the Leader and the TB.  Support can also be provided for the including organization of events, design of leaflets and WEB pages.  An example is: http://portal.etsi.org/STFs/ESI/STF263.asp

STFLINK

If you do not know the person who deals with a particular topic, you can address your requests regarding STFs to “STFLINK” (STFLINK@etsi.org, tel. +33 4 9294 4950).  They will dispatch take your requests to the relevant services.

# Attachments:

The following documents are integral part of these minutes:

ToR STF284, revised during the Preparatory Meeting (attached to e-mail)

Initial Sessions Plan (attached to e-mail)

Annex A: Reference information on STF process (useful addresses)

Annex B: EC/EFTA funding management

Annex C: ETSI co-funding element accounting

Annex A:  Reference Information on STF process (useful addresses)

The reference information and contact persons concerning the STF management process and requirements can be found at the following addresses:

| ETSI WEB site | http://www.etsi.org/ |
| --- | --- |
| ETSI Portal | http://portal.etsi.org/ |
| STF reference Information | http://portal.etsi.org/Portal_STF/FullSearch.asp?Param |
| STF management process | http://portal.etsi.org/stfs/process/home.asp |
| STF working conditions | http://portal.etsi.org/stfs/process/item6_STFwork/item6_A_STFWork.asp |
| STF “contractual” conditions | http://portal.etsi.org/stfs/process/item5_Contr&Invoice/item5_A_LoEconditions.asp |
| STF Travel application | http://webapp.etsi.org/travel/ |
| Time Allocation Management (TAM) | http://webapp.etsi.org/STF_TAM/ |
| STFLINK (STF support) | mailto:STFLINK@etsi.org tel: +33 4 9294 4950 |
| EditHelp (standards drafting support) | http://portal.etsi.org/edithelp/home.asp mailto:edithelp@etsi.org |
| HelpDesk (IT support) | http://portal.etsi.org/helpdesk/home.asp tel: +33 4 9294 4900 |
| Protocol and Testing Competence Centre (PTCC) | http://www.etsi.org/technicalfocus/home.htm |
| Mr. Alberto Berrini (STF Manager) | mailto:alberto.berrini@etsi.org tel: +33 4 9294 4264 |
| Mrs. Pascale Georges (LoE) | mailto:pascale.georges@etsi.org tel: +33 4 9294 4348 |
| Ms. Fabienne Chastanet (WEB pages, reports, planning) | mailto:fabienne.chastanet@etsi.org tel: +33 4 9294 4345 |
| Ms. Marithé Carlier (Invoicing and travel) | mailto:marithe.carlier@etsi.org tel: +33 4 9294 4325 |
| Mrs. Christine Voulgre (Work Permit) | mailto:christine.voulgre@etsi.org tel: +33 4 9294 4269 |
| Ms. Lucy Navas (Trainee) | mailto:lucy.navas@etsi.org tel: +33 4 9294 4268 |

Annex B:  EC/EFTA funding principles

This STF is funded by an EC/EFTA eEurope contract.  The total cost of the action includes the EC/EFTA funding plus a contribution from ETSI as the partner, along with an in-kind contribution based on the days to be spent by ETSI members in reviewing the work at meetings.

The full EC/EFTA funding share will be paid to ETSI on condition that the level of voluntary contribution defined in the contract is achieved.  ETSI will take the responsibility to engage in contracts with the experts and make payments in anticipation of the availability of the in-kind contribution promised by the Members.

The EC/EFTA will pay ETSI against the achievement of the contractual milestones of their contract with ETSI. To a certain extent, ETSI will anticipate payments on the experts’ LoEs, however, ETSI will reserve the right to submit the achievement of some milestones (e.g. Interim and Final Report) to the verification of acceptance by the EC/EFTA.

The contract between the EC/EFTA and ETSI also defines the scope of the action, the activity to be performed and the deliverables to be provided, which include an interim and a final report.  The EC/EFTA only owns the reports, not the deliverables. The reports must show how the work has been carried out, how the resources have been spent, and give evidence for voluntary contributions.

The responsibility for the execution of the contract is shared between the Technical Body, the ETSI Secretariat and the STF. In order for the action to be effective, strict co-ordination between the parties involved is required.

The Terms of Reference define the scope of the STF activity, the deliverables to be provided and the amount of funding available for the experts’ contracts and travels.  However, in view of the complexity of this contract, the STF experts must not limit to the simple execution of the piece of work defined in the ToR but must feel responsible to ensure that their contribution fits the overall objective of the action.  The STF and the TB shall not change the number or type of deliverables, nor make significant changes in the scope, without the explicit agreement of the EC/EFTA, to be confirmed by the EC/EFTA contract manager.

The ETSI Secretariat will co-ordinate the actions for the execution of the contract and is responsible for the management of this contract.  The reference TB is responsible for the technical guidance of the activity and the approval of the technical content of the output.  In order for the action to be effective, strict co-ordination between the parties involved is required.

The performance indicators include statistical information, for example how many people have seen the drafts.  The Final Report will provide the assessment of the performance indicators, against the benchmarks required by the EC/EFTA contract.

Annex C:  ETSI co-funding element accounting

The following guidelines apply for the management and accounting of the ETSI co-funding element:

- Attendance of delegates to TB/WG meetings

The participation of a delegate to a physical meeting can be accounted as two working days for preparation and review after the meeting plus the duration of the meeting itself (with the “granularity” of half-a-day).  The participation must be proven by signed attendance sheet, to be collected by the STF leader during the meeting and provided to the ETSI Secretariat (STFLINK).  The STF experts, the ETSI Secretariat staff and delegates participating on behalf of projects funded by EC/EFTA are not eligible for this purpose.  This STF Leader is responsible to collect attendance lists during the meeting.  If the Leader does not attend, he/she must ensure that this task is delegated (e.g. the ETSI Technical Officer or the Chairman).

The attendance sheets header must include the title, date and place of the meeting, the STF code, the EC/EFTA contract code.  The attendance list must include the name of the delegate, the Organization/TB/Project they are representing, the e-mail address and the signature.

The ETSI Secretariat (STFLINK) will provide the attendance sheet template.

Delegates may also join the meeting by audio-conference however, for these delegates, only the time actually spent on the phone conference can be accounted (either as half-a-day or full day) and not the time for preparation and review..  Physical signatures will be collected only for the persons actually attending the meeting.  The responsible for the meeting will complete the list of participants with the attendees in audio-conference, sign on their behalf and note their participation in the minutes.  Additional information concerning the audio-conference shall also be provided in the attendance list (e.g. the telephone number of the audio-bridge).

- Attendance of delegates to workshops/events and/or collection of requirements

The same principles apply as for the attendance of delegates to TB/WG meeting; however, it is assumed that the attendance is only for the duration of the workshop and/or the collection of requirements.  If the delegates have been asked to prepare contributions and/or give feedback on results the corresponding additional days can be accounted but this must be mentioned in the signed document.

- Voluntary contribution from experts providing work free of charge in the STF

The contribution must be documented with time sheets recorded with the same process as the remunerated work (i.e. through TAM).

- Voluntary contribution from external experts (not working as STF experts)

Contribution of experts from external Companies must be documented with a time sheets declaration on head-letter signed by a representative, indicating which experts have worked which days and other cost incurred.

- Cost to organize workshops/events

The cost must be documented with real cost justification (e.g. invoices for room rental, etc.) and/or a declaration of the cost for services, if these are provided by the host (e.g. support staff, security, etc.).

- Support of working sessions in ETSI: XX days x 200 EUR = XX 000 EUR.  The hosting cost for the experts is represented by the number of days spent in the ETSI premises of Sophia Antipolis, as it results from the time-log records. The work plan shall have a provision for this number of days spent in ETSI, as a minimum.  The minimum number of working days to be performed in the ETSI premises will be specified in the individual LoEs for the experts.  In the course of the activity, it will be possible to swap working days between experts; however, the total number of days spent in the ETSI premises must be achieved.