## Tabelle1
Phase 1 (2004) |  | FT | HA | Tid | Mes
Travelling
Task | Subtask |  |  |  |  | MD | Priority (1+2) | Place | AT ETSI | Contrib (days) | Cost € | Contrib. € |  | Kind of Contribution
1. Transmission network simulation | VoIP metric experts | FT |  | Tid | Mes | 30 | 24+6 |  | 12 days | 6 days | 18000 | 15800 | 3900
|  |  | HA | [5 empty] | 35% | 25%
1.1 | Evaluation of simulation methodologies and tools |  |  |  |  | 4 | 1 | Expert |  |  | 2400
|  | 3 | 1
1.2 | Setup of simulation environment in a lab |  |  | 12 |  | 12 | 1 | Expert | 9 at ETSI | 3 | 7200 | 1800 |  | 3 MD * 600
1.,3 | Validation of the simulation environment |  |  | 5 |  | 5 | 1 | Expert |  | 3 | 3000 | 1800 |  | 3 MD * 600
1.4 | Steering comittee meeting |  |  |  |  | 6 | 2 | ETSI | 21 at Expert |  | 3600 | 6600
| 1 mid term meeting is planned to attend, 2 Experts and 3 steering committee members will attend 1 day) |  |  | 6 |  |  |  |  | 30% at ETSI |  | 0 |  |  | Contribution: 6 x 200 € from ETSI for STF member; 3 x 600 € plus 6 x 600 € (preparation/ de-briefing)
1.5 | (1 meeting is planned to attend, one mid term meeting, one at the end of task 1, 1 Expert will attend) |  |  | 3 |  | 3 | 1 | ETSI |  |  | 1800 | 600 |  | Contribution: 3*200 € from ETSI for STF member
| About 0.7 month of network test setup and test tools use which equals to about | [10 empty] | 5000
| Travelling costs | [11 empty] | 3900
2. Database for transmission networks and conditions evaluation/ simulation | VoIP metric experts |  |  |  |  | 21 | 17+4 |  | 8 days | 7 days | 12600 | 10300
[9 empty] | 40% | 35%
2.1 | Definition of the different network scenarios and conditions to be recorded | 2 | 1 |  |  | 3 | 1 | Expert | 8 at ETSI | 1 | 1800 | 600
2.2 | Preparation of the network simulation recordings |  |  | 10 |  | 10 | 1 | Expert | 13 at Expert | 2 | 6000 | 1200
2.3 | Editing and preparing the data base (for Plugtest compatible format etc.) |  |  | 4 |  | 4 | 2 | ETSI |  | 2 | 2400 | 2000 |  | Contribution: 4*200 € from ETSI for STF member + 2 MD
2.4 | Description of the network simulation data base (STQ document) |  |  | 4 |  | 4 | 1 | ETSI | 40% at ETSI | 2 | 2400 | 2000 |  | Contribution: 4*200 € from ETSI for STF member + 2 MD
| About 0.7 month of network test setup and tools use which equals to about | [10 empty] | 4500
3. Subjective tests | Independent Testlab or Accoustic experts |  |  |  |  | 71 | 38+33 |  | 17 days |  | 42600 | 40500 | 2600
16%
3.1 | Preparation of the test material | 2.5 |  |  | 2.5 | 5 | 1 | Expert | 11 at ETSI |  | 3000
3.2 | Conducting experts test (2 languages) | 10 |  |  | 10 | 20 | 1 | Expert | 60 at Expert |  | 12000
3.3 | Evaluation of the experts test results | 2.5 |  |  | 2.5 | 5 | 1 | Expert |  |  | 3000
3.4 | Preparing test material for naïve listeners tests | 2.5 |  |  | 2.5 | 5 | 2 | Expert | 16% at ETSI |  | 3000
3.5 | Conducting naïve listeners tests (2 languages) | 5 |  |  | 5 | 10 | 2 | Expert |  |  | 6000
3.6 | Evaluation of the results | 5 |  |  |  | 5 | 2 | Expert |  |  | 3000
3.7 | Statistical analysis | 10 |  |  |  | 10 | 2 | Expert |  |  | 6000
3.8 | Description of the test results (STQ document) | 3 |  |  | 2 | 5 | 1 | ETSI |  |  | 3000 | 1000 |  | Contribution: 5*200 € from ETSI for STF member
3.9 | Steering comittee meeting |  |  |  |  | 3 | 2 | ETSI |  |  | 1800 | 6000
| 1 mid term meeting is planned to attend, 1 Expert and 3 steering committee members will attend 1 day) | 3 | [11 empty] | Contribution: 3 x 200 € from ETSI for STF member; 3 x 600 € plus 6 x 600 € (preparation/ de-briefing)
3.10 | STQ meeting 1 meeting is planned to attend at the end of task 1 Expert and 10 delegates will attend 1day) |  |  |  | 3 | 3 | 1 | ETSI |  |  | 1800 | 6000 |  | Contribution: 10 x 600 € (Delegates participation)
| About 10 weeks of test facility use which equals to about | [10 empty] | 27500
| Travelling costs | [11 empty] | 2600
TOTAL Phase 1 |  | 48.5 | 2 | 44 | 27.5 | 122 |  |  |  |  | 88500 | 8100 | 6500
Phase 2 (2005)
4. Objective method for background noise evaluation | Accoustic experts |  |  |  |  | 126 | 123+3 |  | 22 days |  | 75600 | 14000 | 2600
17%
4.1 | Adaptation of existing methods/ programming new methods |  | 88 |  |  | 88 | 1 | Expert | 22 at ETSI |  | 52800
4.2 | Optimization of the method(s) |  | 22 |  |  | 22 | 1 | Expert | 110 at Expert |  | 13200
4.3 | Description of the method(s) (STQ document) |  | 10 |  |  | 10 | 1 | ETSI |  |  | 13200 | 2000 |  | Contribution: 10*200 € from ETSI for STF member
4.4 | Steering comittee meeting |  |  |  |  | 3 | 2 | ETSI |  |  | 1800 | 6000
| 1 mid term meeting is planned to attend, 1 Expert and 3 steering committee members will attend 1 day) |  | 3 | [5 empty] | 17 % at ETSI |  |  |  |  | Contribution: 3 x 200 € from ETSI for STF member; 3 x 600 € plus 6 x 600 € (preparation/ de-briefing)
4.5 | STQ meeting 1 meeting is planned to attend at the end of task 1 Expert and 10 delegates will attend 1day) |  | 3 |  |  | 3 | 1 | ETSI |  |  | 1800 | 6000 |  | Contribution: 10 x 600 € (Delegates participation)
| Travelling costs | [11 empty] | 2600
5. Validation of the new method | Independent Testlab or Accoustic experts |  |  |  |  | 24 | 21+3 |  | 12 days |  | 14400 | 15200 | 1300
45%
5.1 | Preparation of the test files | 1 | 1 | 1 |  | 3 | 1 | Expert |  |  | 1800
5.2 | Processing of the data (validation against unknown databases) |  |  | 6 |  | 6 | 1 | Expert | 12 at ETSI |  | 3600
5.3 | Statistical analysis |  |  | 6 |  | 6 | 1 | Expert |  |  | 3600
5.4 | Drafting document on results (STQ document) |  |  | 6 |  | 6 | 1 | ETSI | 15 at Expert |  | 3600 | 1200 |  | Contribution: 6*200 € from ETSI for STF member
5.5 | Steering comittee meeting |  |  |  |  | 3 | 2 | ETSI |  |  | 1800 | 6000
| 1 meeting is planned to attend, 1 Expert and 3 steering committee members will attend 1 day) |  | 3 | [5 empty] | 45 % at ETSI |  |  |  |  | Contribution: 3 x 200 € from ETSI for STF member; 3 x 600 € plus 6 x 600 € (preparation/ de-briefing)
| About 15 days of test facility use which equals to about | [10 empty] | 8000
| Travelling costs | [11 empty] | 1300
6. Standardization of the background noise evaluation methodology | VoIP metric experts & Accoustic experts |  |  |  |  | 36 | 30+6 |  |  |  | 21600 | 35000 | 5200
6.1 | Drafting and refining STQ EG 201 377 -x: | 3 | 6 | 3 | 2 | 14 | 1 | ETSI |  |  | 8400 | 2800 |  | Contribution: 14*200 € from ETSI for STF member
6.2 | Preparation and realization of an STQ workshop |  |  |  |  | 10 | 1 | ETSI/ |  |  | 6000 | 300 |  | Contribution: 10*200 € from ETSI for STF member; 1400 Workshop
[5 empty] | 10 |  |  | Expert
6.3 | Steering comittee meeting |  |  |  |  | 6 | 2 | ETSI |  |  | 3600 | 6600
| 1 mid term meeting is planned to attend, 2 Experts and 3 steering committee members will attend 1 day) |  | 6 | [10 empty] | Contribution: 6 x 200 € from ETSI for STF member; 3 x 600 € plus 6 x 600 € (preparation/ de-briefing)
6.4 | STQ meeting 1 meeting is planned to attend at the end of task 2 Experts and 10 delegates will attend 1day) |  | 3 | 3 |  | 6 | 1 | ETSI |  |  | 3600 | 6000 |  | Contribution: 10 x 600 € (Delegates participation)
| Travelling costs | [11 empty] | 5200
TOTAL Phase 2 |  | 4 | 145 | 25 | 12 | 186 |  |  |  |  | 200400 | 95200 | 9100
*As stated in the section “3.8.3 Estimated costs of voluntary contributions” of the original STF proposal, beside budgeted 22 MD there will be needed additional 8 MD for the setup and validation works which would be donated. Hence, those 8 days were introduced in the Addendum II | Laboratory owning the Simulator
* As stated in the section 3.8.3 Estimated costs of voluntary contributions of the original STF proposal, Beside budgeted 22 MD there will be needed additional 8 MD for the setup and validation works which would be donated. Hence, those 8 days were introduced in the Addendum II | Laboratoriy(ies) in charge of Subjective tests
Laboratory implementing the New Model
Team including at least one expert of Subj. Tests, Voice Quality, Simulator to be used
The experts involved in the relevant task (at least a part of it is the STF Leader)
May be done by Subjective test experts or by a third party
To be done by a "third party"
May be a specific task