STF 302 (PY) TISPAN on Incorporating Universal Communications Identifier (UCI) support into the specification of Next Generation Networks (NGN)

Participants

| Mr. Rainer Münch | TISPAN Chairman | r.muench@alcatel.de |
| --- | --- | --- |
| Mr. Ian Spiers | TISPAN vice-Chairman | ian.spiers@marconi.com |
| Mr. Tony Holmes | TISPAN WG4 Chairman | tony.ar.holmes@bt.com |
| Mr. Christian Julien | ETSI Technical Officer | christian.julien@etsi.org |
| Mr. Alberto Berrini | STF Manager | alberto.berrini@etsi.org |

Candidates:

| Mr. Francisco J. Cano | Telefonica | fjcs@tid.es |
| --- | --- | --- |
| Mr. Michael Pluke | Castle Consulting Ltd./ÖFEG | Mike.Pluke@CASTLE-CONSULT.COM |
| Mr. Scott Cadzow | Cadzow Comm.Consult. Ltd. | scott@cadzow.com |

Excused

| Ms.Tatiana Kovacikova | Univ. Of Zilina/F.Telec. | tatiana.kovacikova@kis.fri.utc.sk |
| --- | --- | --- |

Copy

| Mr. Pierre de Courcel | CFO | pierre.decourcel@etsi.org |
| --- | --- | --- |
| Mr. Gavin Craik | EC/EFTA Mandate Officer | Gavin.craik@etsi.org |
| STF support |  | stfsupport@etsi.org |

# Agenda:

The following agenda was approved:

1.	Approval of the agenda

2.	Introduction of participants

3.	STF concepts

4.	EC/EFTA contract requirements

5.	EC/EFTA funding and STF resources

6.	ETSI co-funding contribution

7.	Accounting for STF expenditure under EC/EFTA contribution

8.	Accounting for ETSI co-funding contribution

9.	Performance indicators

10.	Interview of candidates

11.	Final decision on the selection of the experts and of the STF Leader

12.	Review of the STF Terms of Reference

13.	Organization of Phases and Tasks

14.	Steering Group, liaison with TB and other interested bodies

15.	STF deliverables schedule

16.	STF reporting and milestones schedule

17.	Allocation of tasks

18.	Work plan and contracts

19.	Sessions plan

20.	Travel plan

21.	Support from the ETSI Secretariat

Document exchange areas, access rights, docbox, ETSI Portal, STF presentation pages

Administrative requirements: travel authorization, time-log, reports

Establishment of the Letter of Engagement, work permit, Social Security certificates

Practical information to settle in the area of Sophia Antipolis

Reimbursement travel cost for Preparatory Meeting

22.	Any other business

# Introduction

The TISPAN Chairman, Mr Rainer Münch delegated Mr. Ian Spiers, TISPAN STF coordinator to chair the meeting.  The meeting was opened at 9:30 and lasted until 15:30.  The agenda was approved.  The participants made a short “round the table” presentation.

Mrs. Tatiana Kovacicova could not attend the meeting, due to an unexpected conflicting engagement requested by EC/EFTA in one of their project.

# STF concept

The ETSI concept is that STF experts normally work together in Sophia Antipolis.  The STF must work according to the ToR approved by the Board.  The draft deliverables produced by the STF will be submitted for approval by the reference TB.  The work within the STF is organized by the STF leader, in co-ordination with the reference TB for technical guidance and the ETSI Secretariat for the management of resources.  More details on the STF working methods can be found on the ETSI Portal: http://portal.etsi.org/stfs/process/home.asp

# STF funding and EC/EFTA contract requirements

This STF is funded from EC/EFTA, under eEurope contract.  Alberto Berrini explained the principles of the contract between EC/EFTA and ETSI and the obligations that derive from it (more information on the funding principles is available on the ETSI Portal).

The STF must produce the ETSI Guide DEG/TISPAN-04004-UCI: “TISPAN; Incorporating Universal Communications Identifier (UCI) support into the specification of Next Generation Networks NGN”.

The EC/EFTA contract requires the following deliverables:

- the Interim Report, due before August 2006

- the Final Report, due before September 2007 and after publication of the ETSI Guide and including the assessment of the “performance indicators”.

It should be agreed with the EC/EFTA whether the period between the publication of the ETSI Guide and the delivery of the Final Report may be used for the dissemination of results, using travel budget.

# STF resources

The total resources funded by EC/EFTA are 53 000 EUR: split as follows:

- Manpower: 45 000 EUR, corresponding to 75 working-days

- Travels: 8 000 EUR.

A minimum of 60 working days out of 75 (80%) must be performed in the ETSI premises.

# ETSI co-funding contribution

In addition to the EC/EFTA funding, ETSI is engaged to provide a co-funding contribution for an equivalent of 37 200 EUR.

The ETSI co-funding contribution consists of two elements: in-kind contribution from ETSI Members and the cost of hosting STF experts’ sessions in ETSI premises.

- The amount of the in-kind contribution is 25 200 EUR, equivalent to 42 delegate-days attendance to TB/WG meetings (mainly TISPAN and AT).

- The equivalent cost for hosting experts’ sessions in ETSI offices is 12 000 EUR (60 days spent in by the experts working in ETSI).

The management of the ETSI contribution is the responsibility of the TB and the STF leader.  The ETSI Secretariat can provide support to administer this element.  Failure to provide the required amount of ETSI co-funding contribution would lead to an equivalent reduction of the EC/EFTA contribution.

# Review of Terms of Reference

Some changes in the STF environment have occurred since the original WG4 Technical Proposal was submitted to EC/EFTA, one year ago.  Some issues in the Technical Proposal have already been addressed within TISPAN and would represent a duplication of work already done.

Thanks to this progress on the background aspects and service definition for UCI, the focus has moved from the “wish-list” to the early implementation of UCI functions using the existing protocols.  The outcome of work performed on UCI, ENUM within WG4 and SIP within WG3 must be taken into account and integrated in the STF ToR.

Definitely, WG4 is not interested in another assessment of benefits that could be realized with UCI.

Experts should look at the UCI concept, potentially recognize and look at what ENUM could provide now.  Expertise ENUM, UCI, SIP is required.

The provisions in the Terms of Reference are part of the contract with EC/EFTA, in the form of a Technical Proposal Annex.  Corrections and/or redirection of activities must be preliminarily agreed with EC/EFTA.  As soon as possible, we should get in contact with the EC/EFTA services, through Gavin Craik, to investigate their views on the possible revision of the Technical Proposal.  Once obtained their agreement in principle, the formal approval will be requested with the Interim Report.

The ToR have been reviewed to take into account the revised time scale.

According to the proposed time scale, the Interim Report will be provided by October 2006, instead of August.  The Interim Report will include the proposed review of these ToR, as indicated above, seeking for the formal approval by EC/EFTA.

The ETSI Guide will be published in April 2007.

The STF will perform the dissemination activities after the publication of the EG and provide the Final Report before the EC/EFTA contractual date of 21 September 2007, obviously including the outcome of the dissemination activities in the performance indicators.

# Interview of candidates

The experts have been interviewed individually.  A selection panel was formed by Rainer Münch,

Ian Spiers, Tony Holmes, Christian Julien and Alberto Berrini.

Experts have been asked about their knowledge in particular in ENUM, UCI, SIP and their views on the objectives of this STF, particularly with regard to the standardization aspects.

Scott Cadzow and Mike Pluke have been selected.  Scott Cadzow will be the STF Leader.

The qualification of Mr. Francisco Cano has been appreciated, however, it was recognized that his specific knowledge of the standardization aspects still to be strengthened before he can participate in an STF, particularly in relation to the limited resources available in this contract.  We recommend that Telefonica could allow Mr. Cano and other experts in his team to attend the TISPAN meetings on a voluntary basis, in order to get the experience required.

Considering the interesting qualification of Mrs. Tatiana Kovacicova for this STF, it has been decided to keep a reserve in the resources allocation, in order to further consider her participation, in a separate interview. Note: Mrs. Kovacicova has been interviewed besides the Preparatory Meeting for STF303, on the following day.  Her participation to STF302 has been confirmed.

# Steering Group and relevant TB meetings schedule

A Steering Group will be set-up.  TISPAN WG3 is invited to support the STF work with SIP expertise.

# Contracts

The initial Letters of Engagement (LoEs) will be established as follows:

Total	Min days	From	To

Days	in ETSI

- Mr. Scott Cadzow	20	16	13 Mar 06	31 Dec 06

- Mr. Mike Pluke	15	12	13 Mar 06	31 Dec 06

- Mrs. Tatiana Kovacicova	15	12	13 Mar 06	31 Dec 06

Initial plan 2006	50	40

Remaining to be allocated	25	20

Total STF budget	75	60

# STF reporting and milestones schedule

The following milestones will be included in the experts’ LoE:

- Milestone A: Progress Report#1 approved by the Steering Group during TISPAN#11 (12-16 June 2006) and the ETSI Director-General.  The draft Report will be prepared by the STF Leader, before 2 June 2006.  The following level of development of the EG should have been achieved: Table of Content & Scope completed.

- Milestone B1: Progress Report#2 approved by the Steering Group during TISPAN#11-bis (11-15 September 2006) and the ETSI Director-General.  The draft Report will be prepared by the STF Leader, before 1st September 2006.  The achievement of Milestone B1 is linked to the approval of the Interim Report by EC/EFTA (Milestone B2).

- Milestone B2: Interim Report accepted by EC/EFTA.  The Report will be prepared by the STF Leader in October 2006, for Steering Group review during TISPAN#11-bis and sent to the ETSI Secretariat (STFLINK).

- Milestone C: Progress Report#3 approved by the Steering Group during TISPAN#12-bis (11-15 December 2006) and the ETSI Director-General and TISPAN/WG4 endorsement of the EG for TB approval during TISPAN#13 (January 2007)..  The draft Report and the draft EG will be provided by the STF Leader, before 1st December 2006.

- Milestone D: Progress Report#4 approved by the Steering Group during TISPAN#13 (January 2007) and the ETSI Director-General and TISPAN approval of the EG for Members’ Vote. The Progress Report will contain the main elements of the Final Report that will be provided to the EC/EFTA.  Payment on this Milestone will be limited to 90% of the contractual amount for the STF Leader.  The balance will be paid upon acceptance of the Final Report by EC/EFTA

- Milestone E: Final Report accepted by EC/EFTA, to be provided to the ETSI Secretariat one month in advance of the date for the delivery to EC/EFTA, which is 21 September 2007.

The STF leader will send the Report and the draft deliverables associated to STFLINK and upload a copy in the “docbox” area as input documents to the TB meeting (if applicable).

The STF Manager will review the Progress Reports (on behalf of the ETSI Director-General), in parallel of the TB approval process.  This review may take a maximum of two weeks.  The milestone is achieved when the report is approved by the TB and the STF Manager, triggering the payment of invoices for the work done to achieve this milestone.

The ETSI Secretariat will review the Interim and Final Reports before sending to the EC/EFTA services.  The ETSI Secretariat review should take no more than 2 weeks from reception of the complete report and publication of deliverables for the Final Report.  The EC/EFTA acceptance confirmation process may require up to 45 days from the reception of the Report by their services.

The ETSI template for the Progress Report, the Interim Report and the Final Report can be found on the ETSI Portal.

# Accounting for STF expenditure under EC/EFTA contribution

- Time sheets are recorded by the experts and validated by the STF Leader using the ETSI Time Allocation Management (TAM) WEB application.

- Travels are authorized by ETSI with a Travel Order, to be agreed in advance between the STF Leader and the STF Manager.  (Travel Management WEB application).  Travel budget is to attend TB meetings and of its WGs and for liaison with other interested Bodies and stakeholders, as specified in the ToR.  For travels to workshops, events and/or meetings other than ETSI TBs, the request must be accompanied by a motivation indicating the scope of the contribution and value for the STF.  Upon his/her return, the expert must provide a report and a signed list of delegates and stakeholders attending. The preliminary authorization of the EC/EFTA must be obtained by the ETSI Secretariat for mission travels not explicitly listed in the ToR categories and, in any case, for mission travels costing more than 1 500 EUR.  The request for all travels must be made reasonably in advance, to allow for the approval process.

# Accounting for ETSI co-funding contribution

The ETSI co-funding contribution must be properly documented, as required by the EC/EFTA financial services, according to the nature of the contribution:

- Attendance of delegates to TB/WG meetings, workshops/events and/or collection of requirements: signed attendance lists

- Cost for hosting experts in the ETSI premises of Sophia Antipolis: time sheets record in TAM.

# Performance indicators

The EC/EFTA contract requires ETSI to provide information that will serve as performance indicators against this activity.  This information will be included in the Final Report and may include quantitatively defined “benchmarks”, as defined in the ToR.  The following indicators will be used to assess the performance of the project:

- Effectiveness

- Stakeholders engagement

- Dissemination of results

- Impact

# Support from the ETSI Secretariat

STF folder on “docbox”

A folder has been created on the ETSI Server (docbox) to exchange documents, at the following address: http://portal.etsi.org/docbox/STF/STF302_TISPAN_EC_NGN_UCI/  .  This folder contains a “Public” area, accessible to all ETSI-on-Line users and a “STFworkarea”, with access restricted to the STF experts, the Technical Officer the AT Chairman, the STF Manager and his Assistant).  These people can include additional users, as required, using the ETSI Access Rights Management (ARM) application: http://webapp.etsi.org/ARM/ .

STF folders in the internal ETSI NW (H and P drives)

The STF will also have two folders in the internal ETSI network, a “Private” area (called H:\STF302) and a “Public area (called P:\STF302).  The write access to these areas is restricted to the STF experts only.  The “P” area is accessible “read only” to all users in the internal ETSI network.  The “P” area is used by to share documents with other STFs.

STF presentation page on the ETSI Portal

A presentation page for the STF will be created on the ETSI Portal.  This page can be used as a “hook” to advertise the STF results and share documents for discussion inside and outside ETSI.  The page is accessible from the STF information boxes on the Portal however, its URL can be referred from other WEB pages.   Ms. Fabienne Chastanet (fabienne.chastanet@etsi.org) will create an initial page for the STF and can provide help to improve and publish this page, based upon the information provided by the Leader and the TB.  Support can also be provided for the including organization of events, design of leaflets and WEB pages.  An example is: http://portal.etsi.org/STFs/ESI/STF263.asp

STFLINK

If you do not know the person who deals with a particular topic, you can address your requests regarding STFs to “STFLINK” (STFLINK@etsi.org, tel. +33 4 9294 4950).  They will dispatch take your requests to the relevant services.

# Attachments:

The following documents are integral part of these minutes:

ToR STF302, revised during the Preparatory Meeting (attached to e-mail)

Initial Sessions Plan (attached to e-mail)

Annex A: Reference information on STF process (useful addresses)

Annex A:  Reference Information on STF process (useful addresses)

The reference information and contact persons concerning the STF management process and requirements can be found at the following addresses:

| ETSI WEB site | http://www.etsi.org/ |
| --- | --- |
| ETSI Portal | http://portal.etsi.org/ |
| STF reference Information | http://portal.etsi.org/Portal_STF/FullSearch.asp?Param |
| STF management process | http://portal.etsi.org/stfs/process/home.asp |
| STF working conditions | http://portal.etsi.org/stfs/process/item6_STFwork/item6_A_STFWork.asp |
| STF “contractual” conditions | http://portal.etsi.org/stfs/process/item5_Contr&Invoice/item5_A_LoEconditions.asp |
| STF Travel application | http://webapp.etsi.org/travel/ |
| Time Allocation Management (TAM) | http://webapp.etsi.org/STF_TAM/ |
| STFLINK (STF support) | mailto:STFLINK@etsi.org tel: +33 4 9294 4950 |
| EditHelp (standards drafting support) | http://portal.etsi.org/edithelp/home.asp http://portal.etsi.org/edithelp/ETSI_Packs/Deliverables_pack/index.asp mailto:edithelp@etsi.org |
| HelpDesk (IT support) | http://portal.etsi.org/helpdesk/home.asp tel: +33 4 9294 4900 |
| Protocol and Testing Competence Centre (PTCC) | http://www.etsi.org/technicalfocus/home.htm |
| Mr. Alberto Berrini (STF Manager) | mailto:alberto.berrini@etsi.org tel: +33 4 9294 4264 |
| Mrs. Pascale Georges (LoE) | mailto:pascale.georges@etsi.org tel: +33 4 9294 4348 |
| Ms. Fabienne Chastanet (WEB pages, reports, planning) | mailto:fabienne.chastanet@etsi.org tel: +33 4 9294 4345 |
| Ms. Marithé Carlier (Invoicing and travel) | mailto:marithe.carlier@etsi.org tel: +33 4 9294 4325 |
| Mrs. Christine Voulgre (Work Permit) | mailto:christine.voulgre@etsi.org tel: +33 4 9294 4269 |