## Sessions 06
STF302 - Sessions plan Year 2006
from | to | week | SC |  | MP |  | other |  | Notes
2006-02-06 | 2006-02-10 | 6 | [6 empty] | Preparatory Meeting
2006-02-13 | 2006-02-17 | 7
2006-02-20 | 2006-02-24 | 8
2006-02-27 | 2006-03-03 | 9
2006-03-06 | 2006-03-10 | 10
2006-03-13 | 2006-03-17 | 11 | E | 3 |  |  |  |  | Start work
2006-03-20 | 2006-03-24 | 12
2006-03-27 | 2006-03-31 | 13 | [6 empty] | ToC&scope
2006-04-03 | 2006-04-07 | 14 | [6 empty] | TISPAN#10-bis
2006-04-10 | 2006-04-14 | 15
2006-04-17 | 2006-04-21 | 16
2006-04-24 | 2006-04-28 | 17
2006-05-01 | 2006-05-05 | 18
2006-05-08 | 2006-05-12 | 19
2006-05-15 | 2006-05-19 | 20
2006-05-22 | 2006-05-26 | 21
2006-05-29 | 2006-06-02 | 22 | [6 empty] | Initial draft EG, draft Progress Report #1
2006-06-05 | 2006-06-09 | 23
2006-06-12 | 2006-06-16 | 24 | [6 empty] | TISPAN#11, SG meeting
2006-06-19 | 2006-06-23 | 25 | [6 empty] | SG approved Progress Report #1
2006-06-26 | 2006-06-30 | 26
2006-07-03 | 2006-07-07 | 27
2006-07-10 | 2006-07-14 | 28
2006-07-17 | 2006-07-21 | 29
2006-07-24 | 2006-07-28 | 30
2006-07-31 | 2006-08-04 | 31
2006-08-07 | 2006-08-11 | 32
2006-08-14 | 2006-08-18 | 33
2006-08-21 | 2006-08-25 | 34
2006-08-28 | 2006-09-01 | 35 | [6 empty] | Initial draft EG, draft Progress Report #2
2006-09-04 | 2006-09-08 | 36
2006-09-11 | 2006-09-15 | 37 | [6 empty] | TISPAN#11-bis, SG meeting
2006-09-18 | 2006-09-22 | 38 | [6 empty] | SG approved Progress Report #2
2006-09-25 | 2006-09-29 | 39
2006-10-02 | 2006-10-06 | 40
2006-10-09 | 2006-10-13 | 41 | [6 empty] | Stable draft EG, draft Interim Report
2006-10-16 | 2006-10-20 | 42 | [6 empty] | TISPAN#12
2006-10-23 | 2006-10-27 | 43
2006-10-30 | 2006-11-03 | 44
2006-11-06 | 2006-11-10 | 45
2006-11-13 | 2006-11-17 | 46
2006-11-20 | 2006-11-24 | 47
2006-11-27 | 2006-12-01 | 48 | [6 empty] | Final draft EG, draft Progress Report #3
2006-12-04 | 2006-12-08 | 49
2006-12-11 | 2006-12-15 | 50 | [6 empty] | TISPAN#12-bis (WG approval), SG meeting
2006-12-18 | 2006-12-22 | 51 | [6 empty] | SG approved Progress Report #3
2006-12-25 | 2006-12-29 | 52
|  | days | 3 |  | 0 |  | 0 |  | 3
|  | ETSI |  | 3 |  | 0 |  | 0 | 3 days in ETSI
100%
Codes: 1 letter for the location 1 figure for the number of days (e.g. E5 = 5days in ETSI)
[7 empty] | E | 5 | E = work in an ETSI session
[7 empty] | C | 3 | C = work in STF co-ordination meetng (sessions) outside ETSI
[7 empty] | H | 0,5 | H = work at home (with ETSI autorisation)
[7 empty] | M | 2 | M = mission travel (with ETSI autorisation)

## Sessions 07
STF302 - Sessions plan Year 2007
from | to | week | SC |  | MP |  | other |  | Notes
2007-01-01 | 2007-01-05 | 1
2007-01-08 | 2007-01-12 | 2 | [6 empty] | Draft Progress Report #4 (preparation of Final Report)
2007-01-15 | 2007-01-19 | 3
2007-01-22 | 2007-01-26 | 4 | [6 empty] | TISPAN#13 date tbd (TB approval), SG meeting
2007-01-29 | 2007-02-02 | 5 | [6 empty] | EG approved for MV, SG approved Progress Report #4
2007-02-05 | 2007-02-09 | 6
2007-02-12 | 2007-02-16 | 7
2007-02-19 | 2007-02-23 | 8
2007-02-26 | 2007-03-02 | 9
2007-03-05 | 2007-03-09 | 10
2007-03-12 | 2007-03-16 | 11
2007-03-19 | 2007-03-23 | 12
2007-03-26 | 2007-03-30 | 13 | [6 empty] | end Members' vote
2007-04-02 | 2007-04-06 | 14
2007-04-09 | 2007-04-13 | 15
2007-04-16 | 2007-04-20 | 16
2007-04-23 | 2007-04-27 | 17 | [6 empty] | Publication
2007-04-30 | 2007-05-04 | 18
2007-05-07 | 2007-05-11 | 19
2007-05-14 | 2007-05-18 | 20
2007-05-21 | 2007-05-25 | 21
2007-05-28 | 2007-06-01 | 22
2007-06-04 | 2007-06-08 | 23
2007-06-11 | 2007-06-15 | 24
2007-06-18 | 2007-06-22 | 25
2007-06-25 | 2007-06-29 | 26
2007-07-02 | 2007-07-06 | 27
2007-07-09 | 2007-07-13 | 28
2007-07-16 | 2007-07-20 | 29
2007-07-23 | 2007-07-27 | 30
2007-07-30 | 2007-08-03 | 31
2007-08-06 | 2007-08-10 | 32
2007-08-13 | 2007-08-17 | 33
2007-08-20 | 2007-08-24 | 34
2007-08-27 | 2007-08-31 | 35
2007-09-03 | 2007-09-07 | 36
2007-09-10 | 2007-09-14 | 37
2007-09-17 | 2007-09-21 | 38 | [6 empty] | Final Report
2007-09-24 | 2007-09-28 | 39
2007-10-01 | 2007-10-05 | 40
2007-10-08 | 2007-10-12 | 41
2007-10-15 | 2007-10-19 | 42
2007-10-22 | 2007-10-26 | 43
2007-10-29 | 2007-11-02 | 44
2007-11-05 | 2007-11-09 | 45
2007-11-12 | 2007-11-16 | 46
2007-11-19 | 2007-11-23 | 47
2007-11-26 | 2007-11-30 | 48
2007-12-03 | 2007-12-07 | 49
2007-12-10 | 2007-12-14 | 50
2007-12-17 | 2007-12-21 | 51
2007-12-24 | 2007-12-28 | 52
|  | days | 0 |  | 0 |  | 0 |  | 0
|  | ETSI |  | 0 |  | 0 |  | 0 | 0 days in ETSI
#DIV/0!
Codes: 1 letter for the location 1 figure for the number of days (e.g. E5 = 5days in ETSI)
[7 empty] | E | 5 | E = work in an ETSI session
[7 empty] | C | 3 | C = work in STF co-ordination meetng (sessions) outside ETSI
[7 empty] | H | 0,5 | H = work at home (with ETSI autorisation)
[7 empty] | M | 2 | M = mission travel (with ETSI autorisation)