STF 386 Phase 3 - ERM / TG17 WP3 - PMSE Cognitive Radio 
“Methods, parameters and test procedures for cognitive interference mitigation techniques for use by PMSE devices (Programme Making and Special Events)

Participants

TB/Secretariat representatives:

| Brian Copsey | ERM TG17 Chairman | bc@copsey-comms.com |
| --- | --- | --- |
| Alberto Berrini | STF Support Unit Director | alberto.berrini@etsi.org |
| Marithé Carlier | STF Support Assistant | marithe.carlier@etsi.org |

Candidates:

| Clemens Kunert | IRT | kunert@irt.de |
| --- | --- | --- |
| Axel Schmidt | Sennheiser Electronic GmbH | schmidtax@sennheiser.com |
| Andreas Wilzeck | wiseSense GmbH Project Leader C-PMSE | andreas.wilzeck@wisesense.net |
| Sven Dortmund | RUB | sven.dortmund@rub.de |
| Johannes Brendel | Friedrich-Alex-Universität | brendel@lte.eei.uni-erlangen.de |

Candidates via GoTo Meeting

| Edgar Reihl | SHURE Europe GmbH | Reihl_Edgar@shure.com |
| --- | --- | --- |

Copy

| Gabrielle Owen | TC ERM Chairman | gabrielle.owen@agentschaptelecom.nl |
| --- | --- | --- |
| Frank Ernst | TG17 Secretary | frank.ernst@de.bosch.com |
| Wolfgang Bilz | SHURE Europe GmbH | Bilz_Wolfgang@shure.de |
| Maria Dolores Perez-Guirao | Leibniz Universität Hannover | dolores.perez@wiseSense.net |
| Georg Fischer | Friedrich-Alex-Universität | fischer@lte.eei.uni-erlangen.de |
| Igor Minaev | Technical Officer | igor.minaev@etsi.org |

Table of content

1	Introduction	2

2	STF concept	2

3	STF funding	2

Experts manpower	2

4	STF deliverables	2

5	Review of Terms of Reference	3

6	Steering Group	3

7	Organization of the work and co-ordination requirements	3

8	Selection of experts and STF leader	3

9	Allocation of tasks and resources	3

10	STF reporting and milestones schedule	4

11	Electronic working tools	4

11.1	STF folder on “docbox”	4

11.2	e-mail	4

11.3	STF presentation page on the ETSI Portal	5

11.4	Access rights	5

12	Organization of the work	5

12.1	Establishment of Contracts	5

12.2	Social Security and Work Permit	5

12.3	Session plan	6

12.4	Declaration of time spent	6

12.5	Travels	6

12.6	Milestones and reporting	7

12.7	Invoicing	7

12.8	Presentation in conferences and articles	8

12.9	Practical information to settle in the area of Sophia Antipolis	9

12.10	STFLINK	9

13	Reimbursement of travel cost for this meeting	9

14	Attachments:	9

Annex A:  Reference Information on STF process (useful addresses)	9

# Introduction

The meeting was opened at 9:00.  Participants made a short presentation. The agenda was approved.

Brian Copsey chaired the meeting.

# STF concept

Alberto Berrini made a short presentation of the STF concepts.  More details on the STF working methods can be found on the ETSI Portal: http://portal.etsi.org/stfs/process/home.asp

# STF funding

This STF is funded from the ETSI budget.

### Experts manpower

The total resources available are 65 working days (55 remunerated + 10 voluntary = 33 000 € and up to 3 000 € for travels (Steering Group, TC-ERM or CEPT meetings).

Days free of charge that will be shared between the experts following the guidelines in the voluntary contribution allocation criteria.

# STF deliverables

The STF will provide the following ETSI deliverable:

DTR/ERM-TG17WG3-013 TR 102 801

Test reports from technology demonstrator implementing TS 102 800 on protocols for spectrum access and sound quality control systems for PMSE using cognitive interference mitigation techniques.”

Scope: to specify input test scenarios for a technology demonstrator implementing TS 102 800 on protocols for spectrum access and sound quality control systems for Programme Making and Special Events (PMSE) applications using cognitive interference mitigation techniques.

Schedule revised to take into account start in December 2012:

# Review of Terms of Reference

During Phase 3, the STF will:

Specify input test scenarios for a demonstrator for the TS developed under (3) and test its compliance.

Deliver an ETSI Technical Report of the defined RF compliance tests, carried out under (0), for the selected spectrum access mechanism defined in (3)  STF386 will propose the type of compliance required, which will be different from the current EN 300 422 specifications.

It should be noted that, although the technology demonstrator will concentrate on one particular PMSE application and frequency band, the theory will be applicable to all PMSE applications.

Edgar should provide the latest draft of IEEE 802.22.1.

# Steering Group

TC ERM TG17 WP3 will monitor the progress through a steering committee that will consist of the ERM Chairman, the ERM TG17 Chairman, a representative from a regulatory authority (could be covered by the current ERM Chairman) and a representative of the PMSE industry and users.

# Organization of the work and co-ordination requirements

The first face-to-face meeting of STF386 Phase 3 will be held in January 2013.

Secretariat will set up a Doodle to select a date from 15 to 31 January.

Location: in one of the Universities in Germany (Hannover).

STF work plan and synchronization with CPMSE will be decided during the first face-to-face meeting.

# Selection of experts and STF leader

As in Phase 2, Leadership will be shared between Wolfgang Bilz and Georg.

Georg will take care of the administrative tasks.

# Allocation of tasks and resources

The responsibility for the STF tasks has been allocated as follows, with the following preliminary resources allocation:

| Expert(s) | Company | Tasks | Days remun. | Days volunt. |
| --- | --- | --- | --- | --- |
| Clemens Kunert | IRT |  |  | 10 |
| Axel Schmidt | Sennheiser Electronic GmbH |  |  | 10 |
| Andreas Wilzeck | wiseSense GmbH | Project Leader C-PMSE |  | 10 |
| Edgar Reihl | SHURE Europe GmbH |  |  | 10 |
| Wolfgang Bilz | SHURE Europe GmbH | Joint Leader |  | 10 |
| Sven Dortmund | RUB |  | 13 |  |
| Johannes Brendel | Friedrich-Alex-Universität |  | 13 |  |
| Maria Dolores Perez-Guirao | Leibniz Universität Hannover |  | 13 |  |
| Georg Fischer | Friedrich-Alex-Universität, | Joint Leader (admin. resp.) | 16 |  |
|  |  |  | 55 | 50 |

Contracts from 1 Jan 2013 to 31 December 2014.

# STF reporting and milestones schedule

The following milestones will be included in the experts’ LoE:

| Mil | Description | Target date milestone achieved |
| --- | --- | --- |
| A | Progress Report#1 for information to ERM#49 (18-22 Mar). | 28 Feb 2013 |
| B | Progress Report#2 with the STF work plan defined after conclusion of CPMSE Phase 2 and preliminary ToC of the TR, to be contributed to ERM#50 (24-28 June). | 31 May 2013 |
| C | Progress Report#3 and preliminary early draft with consolidated ToC and some content, to be contributed to ERM#51 (18-22 Nov). | 31 Oct 2013 |
| D | Progress Report#3 and early draft TR uploaded on ERM Portal | 31 Dec 2013 |
| 2014 | Progress Reports to each ERM meeting and current draft TR uploaded on ERM Portal | tbd |
| Final ETSI | Final Report and TR approved by TG17 and TC ERM plenary and accepted by ETSI Secretariat for publication. The Final Report and the draft TR must be uploaded by the STF Leader on the ERM contributions area at least two weeks before the ERM plenary. | tbd |

# Electronic working tools

## STF folder on “docbox”

The STF will use the current folder http://docbox.etsi.org/STF/STF386_ERM17WG3_PMSE_CognRadio/STFworkarea/

Administrative rights are granted to all STF experts and to the TG17 Chair, Brian Copsey.

The subfolder contains a “Public” area, accessible to all ETSI-on-Line users and a “STFworkarea”, with access restricted to the following users.

| Gabrielle Owen | TC ERM Chairman | gabrielle.owen@agentschaptelecom.nl |
| --- | --- | --- |
| Brian Copsey | WG17 Chairman | bc@copsey-comms.com |
| Frank Ernst | TG17 Secretary | frank.ernst@de.bosch.com |
| Wolfgang Bilz | STF Leader | Bilz_Wolfgang@shure.de |
| Georg Fischer | STF Leader | fischer@lte.eei.uni-erlangen.de |
| Clemens Kunert | Expert | kunert@irt.de |
| Axel Schmidt | Expert | schmidtax@sennheiser.com |
| Andreas Wilzeck | Expert | andreas.wilzeck@wisesense.net |
| Sven Dortmund | Expert | sven.dortmund@rub.de |
| Johannes Brendel | Expert | brendel@lte.eei.uni-erlangen.de |
| Edgar Reihl | Expert | Reihl_Edgar@shure.com |
| Maria Dolores Perez-Guirao | Expert | dolores.perez@wiseSense.net |
| Igor Minaev | Technical Officer | igor.minaev@etsi.org |

If necessary, users may be added using the ETSI Access Rights Management (ARM) application: http://webapp.etsi.org/ARM/ .

## e-mail

Experts will use their own e-mail account to exchange information within the STF.

An e-mail list will be created, with archive, for the day-to-day work, at the following address: STF386_ERM_PMSE@list.etsi.org, with the following users:

| Gabrielle Owen | TC ERM Chairman | gabrielle.owen@agentschaptelecom.nl |
| --- | --- | --- |
| Brian Copsey | WG17 Chairman | bc@copsey-comms.com |
| Frank Ernst | TG17 Secretary | frank.ernst@de.bosch.com |
| Wolfgang Bilz | STF Leader | Bilz_Wolfgang@shure.de |
| Georg Fischer | STF Leader | fischer@lte.eei.uni-erlangen.de |
| Clemens Kunert | Expert | kunert@irt.de |
| Axel Schmidt | Expert | schmidtax@sennheiser.com |
| Andreas Wilzeck | Expert | andreas.wilzeck@wisesense.net |
| Sven Dortmund | Expert | sven.dortmund@rub.de |
| Johannes Brendel | Expert | brendel@lte.eei.uni-erlangen.de |
| Edgar Reihl | Expert | Reihl_Edgar@shure.com |
| Maria Dolores Perez-Guirao | Expert | dolores.perez@wiseSense.net |
| Igor Minaev | Technical Officer | igor.minaev@etsi.org |

The ETSI Secretariat will be the owner and can extend access rights to other participants upon request of the STF Leader.  The list and is restricted to ETSI Members.  If access to non-ETSI Members is required, the authorization must be requested to the STF Support Unit Director.

## STF presentation page on the ETSI Portal

A presentation page for the STF will be created on the ETSI Portal.  This page can be used to advertise the STF results and share documents for discussion inside and outside ETSI.  The URL can be referred from other WEB pages or by e-mail.  The ETSI Secretariat will create an initial page for the STF and can provide help to improve and publish this page, based upon the information provided by the Leader and the TB.

An example is http://portal.etsi.org/stfs/STF_HomePages/STF397/STF397_Ph2.asp

## Access rights

During the period in which they work for the STF, experts will be granted the same access rights as the full ETSI Members, even if their Company is not an ETSI Member.  Access to the STF IT services and, in particular, Members access rights will be granted after the experts’ contract is signed by both parties and will be removed one month after the STF work is finished or the expert contract expires.

# Organization of the work

## Establishment of Contracts

Contracts (LoE) will be made according to the conditions agreed in this Preparatory Meeting.  In order to draft the LoE, the ETSI Secretariat must receive the administrative information that has been requested with the invitation to the Preparatory Meeting.

The ETSI Secretariat will send a “pdf” file to the contact person of the expert’s Company indicated in the administrative information form.

The contact person should print out and send two signed copies to the ETSI Secretariat, at the postal address STFLINK, 650 route des Lucioles, F-06921 Sophia Antipolis Cedex, France.  One original of the LoE will be returned to the contact person, countersigned by the ETSI Director-General.

The expert is not be entitled to come to work in the ETSI premises nor to be granted access to the IT services nor to charge working time before the LoE is signed by both parties.

## Social Security and Work Permit

Experts attending sessions in the ETSI premises must provide a certificate to prove that their Company has paid the Social Security contributions for the period of activity in the STF.

Experts from Companies based in an “EU area” country (EU + Iceland, Norway, Liechtenstein, and Switzerland) must provide a "A1" certificate.  Experts from Companies based in France must provide a copy of the Social Security card for an employee or URSSAF declaration for self-employed consultants

The Social Security certificate must be requested as soon as possible to the competent authorities.  If the certificate cannot be delivered on time for the first session of the STF in ETSI, then the expert must provide a copy of the request.

Experts from countries outside the “EU area” must obtain a Work Permit before they can join an STF session in ETSI.  This procedure requires a minimum of 8 weeks.

## Session plan

The initial session plan is in the attached EXCEL sheet.  The initial plan will be recorded by the ETSI Secretariat in the Time Allocation Management (TAM) WEB application.  Request for new sessions and/or changes of the current plan will be done directly by the experts or by the STF Leader using the TAM interface.

The process is as follows:

1)	the expert or the Leader requests a new session or to change a session (status REQUESTED)

2)	ETSI Secretariat (STF Support) confirms the session (status PLANNED)

The expert concerned and the Leader are informed by automatic e-mail of all changes of the session plan, when they are requested and when they are confirmed by the ETSI Secretariat.

The same process applies for sessions in ETSI and for work at home.  However, request for sessions in ETSI should be submitted with reasonable advance, to allow planning of office allocation.

## Declaration of time spent

After the end of each month each expert will confirm the time actually spent in TAM. The STF Leader will validate the experts’ declaration, to confirm that the effort claimed corresponds to the result achieved. STF Support will then accept the time sheets, after checking the contractual conditions.

The process is as follows:

3)	if the expert has worked according to the plan, he/she confirms the time spent (status DONE)

3a)	if the actual working time is different than planned (typically for home work), the expert will update the time sheet and submit to STF Support, as for an updated “session plan”.  After STF Support has confirmed the change, the expert can confirm the time spent, as in 3)

4)	The STF LEADER validates the time spent (status VALIDATED)

5)	STF Support accepts the registration and the related invoice can be paid (status ACCEPTED)

The declaration of the time spent should be done by each expert after the last session of the current month and before the 7th of the month that follows, based upon the agreed session plan (status “PLANNED”).  When the expert submits the time sheet, status will be changed to “DONE”.  The STF Leader should validate the experts’ time sheets in status “DONE”, before the 14th of the following month (status will be changed to “VALIDATED”).  When the Secretariat confirms acceptance of the time declaration (status “ACCEPTED”), the corresponding working days are “credited” to the contract for the payment of the next invoice.

## Travels

The travel cost to attend the STF working sessions (in ETSI or in any other location) is included in the contractual remuneration.

The STF travel budget can be used to reimburse cost for the experts to attend the TB meetings and other meetings outside the STF working sessions.  These travels must be preliminarily authorized by the ETSI Secretariat, and are limited to the subjects explicitly mentioned in the ToR.

Travel approval is managed with the Travel Management WEB application:

1)	The STF Leader requests as soon as possible a Travel Plan, indicating the general information about reason, duration, number of experts, location, expected cost, etc.

2)	The ETSI Secretariat endorses the travel plan (status “ETSI”)

3)	The expert prepares a Travel Order (TO) with all the details of the proposed travel organization and cost.  The Travel Order must be based upon an approved Travel Plan.

4)	The ETSI Secretariat endorses the proposed travel organization.  The experts receives a confirmation by e-mail with a TO number (e.g. STF/2011/NNNN), which represents the confirmation of the approval and that he/she will refer in the reimbursement claim (status “AGREED”).

5)	The travel cost will be reimbursed on the basis of the travel organization agreed in the TO and within the limits set by the ETSI Travel rules.

ETSI will reimburse the travel and subsistence cost according to the ETSI travel reimbursement rules, with justification bills and for the minimum period necessary to attend the meeting.  Reimbursement will be made according to the minimum cost and duration necessary to present the STF contribution to the meeting.  It is recommended that, if there is the need for special travel arrangement and/or extended duration, the expert provides this information in the Travel Order, so that STF Support can confirm the preliminary agreement.  If this information is not provided in the Travel Order, the reimbursement will be determined by ETSI according to the information available at the time the reimbursement will be requested.  Unexpected extra-cost must be justified in the travel reimbursement claim.

The Travel Expenses Reimbursement form can be sent to STFLINK, with an invoice from the Company and copies of the bills and boarding cards attached.

Reimbursement claims should be submitted to ETSI no later than one month after the travel.  If this is not possible, the expert shall inform ETSI of the amount that will be claimed.

Experts travelling to meetings other than those of ETSI TBs must produce an executive report of their attendance.  The report should provide the necessary information to assess the benefit for the STF from the attendance.  The Mission Report template provides an example of “bullet-points” structure.

If required, the in-kind contribution signatures must be sent to STFLINK before submitting the reimbursement claim.

## Milestones and reporting

The achievement of milestones is normally related to the approval of STF Reports.  In order to ensure liaison with the reference TB, the reporting schedule is linked to the TB/WG meeting calendar.  The objectives to be achieved for each milestone and the target date are indicated in §13 of these minutes and reproduced in the LoE.

If a milestone is not achieved or delayed, payment of invoices may be suspended until the cause and responsibility for the failure is identified.  If the experts are not responsible for the failure, their will work will be normally remunerated, however, the ETSI Secretariat will take the necessary corrective actions to ensure the efficient use of the remaining resources.

Unless differently specified, draft of Progress Reports and intermediate deliverables should be made available by the STF Leader to the ETSI Secretariat (STFLINK) and the TB at least two weeks before the target date for the milestone.  Final draft deliverables for TB approval must be made available by the STF Leader to the TB at least 30 days before the start of the meeting.

The Report and the related documents must be uploaded on the TB contributions area of the ETSI Portal with source “STF 386”.  The Leader will inform STF Support (STFLINK) by e-mail when the documents have been uploaded.  The milestone will be considered as achieved when all the documents referred will be in status “Accepted” in the TB contribution area.  The STF Leader will inform STF Support (STFLINK) by e-mail when this is achieved.

The ETSI template for the Progress Report, and the Final Report can be found on the ETSI Portal.

## Invoicing

Invoices for the time spent can be sent after the relevant milestone is achieved.  The amount to be invoiced corresponds to the number of working days actually spent until the target date for the Milestone indicated in the LoE and as it results from the time sheets accepted by the ETSI Secretariat.

When the milestone is achieved, STF Support will send to the contact person of the LoE (copy to the expert) an e-mail with the amount that can be invoiced.

In order to comply with the French regulations and the ETSI accounting rules, the invoice must fulfil the following requirements:

be an original document, preferably on head letter of the Company

contain the term "INVOICE" or the equivalent term in the national language in the header of the document

and provide the following information:

Date of issue

Invoice number (a sequential number, based on one or more series, which uniquely identifies the invoice)

Full name, legal address and registration number of your Company

Company VAT number (the VAT identification number under which your company supplied the services)

Customer name and address (ETSI, 650 route des Lucioles, F-06921 Sophia Antipolis, cedex France)

ETSI VAT identification number (FR 14 348 623 562), for companies based in an EU country

Quantity and nature of the services rendered and, in particular:

Expert name

LoE code * or Travel Order number

Milestone(s) code, as referenced in Annex 2 of the LoE **

Number of working days claimed and daily rate

Reference period for the work claimed or date of the travel

Net amount due (in EUR, exclusive of tax)

VAT rate amount (VAT must be charged only by Companies based in France) ***

Total amount of the invoice (in EUR, inclusive of tax)

Notes - 
*  The invoice must refer to a single LoE or Travel Order: if the expert works on different STFs, separate invoices are required

** The invoice must correspond to the amount of work performed to achieve the milestone(s), i.e. not exceeding the total accepted time sheets at the milestone achievement date (delivery date) indicated in the LoE.

*** Application of VAT on travel reimbursement invoices for Companies based in France

Payment will be made within 30 days upon reception of the invoice by ETSI and confirmation of the achievement of the relevant milestone. If the milestone is delayed, the invoice must be kept on hold until the achievement is confirmed.  The final invoice must be sent not later than two months after the conclusion of the contract

## Presentation in conferences and articles

ETSI welcome the widest possible dissemination of the standardization achievement in articles conferences and other publications, on condition that the copyright and confidentiality requirements are fulfilled and that the role of ETSI and its brand identity are duly evidenced and acknowledged.

Therefore, reference to ETSI, the TB, the STF and the funding sources, if different from the ETSI budget (e.g. EC/EFTA, Members), must be explicitly quoted.

In order to avoid confusion, the activity and results achieved on behalf of ETSI must be clearly identified and must appear as distinct from the objectives of any other related initiatives, either commercial or not for profit.

Moreover, it must be considered that the documentation which is being processed by the STF is, by its nature, draft material not yet approved by the ETSI Membership.  Therefore, whenever this material is presented in another context than the STF reference TB, particular care must be taken to ensure that the audience understands that this represents the provisional point of view of the STF and/or the reference TB and that this may not be interpreted as a firm official ETSI position.

More information can be found in the STF site on the ETSI Portal.

## Practical information to settle in the area of Sophia Antipolis

The ETSI Secretariat has negotiated preferential rates for housing, transports and other services in the area of Sophia Antipolis.  More information can be found in the STF site on the ETSI Portal.

## STFLINK

If you do not know the person who deals with a particular topic, you can address your requests regarding STFs to “STFLINK” (STFLINK@etsi.org), postal address STFLINK, 650 route des Lucioles, F-06921 Sophia Antipolis Cedex, France.  They will dispatch take your requests to the relevant services.

# Reimbursement of travel cost for this meeting

ETSI will reimburse the travel and subsistence cost for the participation to this Preparatory Meeting according to the ETSI travel reimbursement rules i.e. cheapest ticket, 3 star hotel in Sophia Antipolis, 35 EUR per meal, airport bus shuttle (unless taxi required, due to arrival/departure time), with justification bills and for the minimum period necessary to attend the meeting.  The Travel Expenses Reimbursement form can be sent to STFLINK, either with an invoice from the Company and copies of the bills or as direct reimbursement to the experts, with the original bills attached.

# Attachments:

- ToR STF386 v3.4 revised during the Preparatory Meeting

Annex A:  Reference Information on STF process (useful addresses)

The reference information and contact persons concerning the STF management process and requirements can be found at the following addresses:

| ETSI WEB site | http://www.etsi.org/ |
| --- | --- |
| ETSI Portal | http://portal.etsi.org/ |
| STF reference Information | http://portal.etsi.org/Portal_STF/FullSearch.asp?Param |
| STF management process | http://portal.etsi.org/stfs/process/home.asp |
| STF working conditions | http://portal.etsi.org/stfs/process/item6_STFwork/item6_A_STFWork.asp |
| STF “contractual” conditions | http://portal.etsi.org/stfs/process/item5_Contr&Invoice/item5_A_LoEconditions.asp |
| STF Travel application | http://webapp.etsi.org/travel/ |
| Time Allocation Management (TAM) | http://webapp.etsi.org/STF_TAM/ |
| Mailing lists server | http://list.etsi.org/ |
| EditHelp (standards drafting support) | http://portal.etsi.org/edithelp/home.asp http://portal.etsi.org/edithelp/ETSI_Packs/Deliverables_pack/index.asp mailto:edithelp@etsi.org |
| CTI (Conformance Testing and Interoperability Competence Centre) | http://www.etsi.org/technicalfocus/home.htm |
| Helpdesk (IT support) | http://portal.etsi.org/helpdesk/home.asp +33 4 9294 4900 |
| STFLINK (STF support) | mailto:STFLINK@etsi.org |
| STF Support Unit Director Alberto Berrini | alberto.berrini@etsi.org +33 4 9294 4264 |
| STF Support Assistants Marithé Carlier | marithe.carlier@etsi.org +33 4 9294 4325 |