STF 458 Rationalised Framework for electronic signatures standards; activities related to Signature Creation and Validation and Trusted Service Providers (TSP) supporting eSignatures SA/ETSI/ENTR/460/2012-09 Phase 2c, part A

TB/Secretariat representatives:

| Riccardo Genghini | ETSI TC ESI Chairman | riccardo.genghini@sng.it |
| --- | --- | --- |
| Dominique Lescribaa | CEN TC224 Chairman | dominique-lescribaa@cartes-bancaires.com |
| Caroline De Condé | CEN TC224 Secretary | caroline.deconde@afnor.org |
| Alain Dechamps | CEN/CENELEC Management Centre | adechamps@cencenelec.eu |
| Sonia Compans | ETSI ESI Technical Officer | sonia.compans@etsi.org |
| Laurent Velez | ETSI CTI Technical Officer | laurent.velez@etsi.org |
| Gavin Craik | ETSI EC/EFTA Mandate Officer | gavin.craik@etsi.org |
| Alberto Berrini | STF Support Unit Director | alberto.berrini@etsi.org |
| Marithé Carlier | STF Support Assistant | marithe.carlier@etsi.org |
| Expert | eMail | Company |
| Nick Pope | nick.pope@thales-esecurity.com | Thales |
| Alexander Funk | af@bos-bremen.de | bremen online |
| Andrea Caccia | andrea.caccia@studiocaccia.com | Knowl. works / UNINFO |
| Andrea Röck | andrea.rock@CRYPTOLOG.COM | Cryptolog |
| Arne Tauber | Arne.Tauber@iaik.tugraz.at | Stiftung / FTW |
| Arno Fiedler | arno.fiedler@nimbus-berlin.com | Nimbus |
| Frank Leroy | franck.leroy@certinomis.fr | Certinomis / CEN |
| Ijaz Khan | ijaz.khan@gemalto.com | GEMALTO |
| Inigo Barreira | inigo_barreira@hotmail.com | I3S / AENOR |
| Jon Olnes | jon.olnes@unibridge.no | UniBridge / Norway auth. |
| Juan Carlos Cruellas | cruellas@ac.upc.edu | DAC-UPC |
| Leonard Rosenthol (voluntary) | lrosenth@adobe.com | Adobe |
| Luigi Rizzo | luigi.rizzo@infocert.it | InfoCert |
| Moez Ben Mbarka (voluntary) | moez.benmbarka@cryptolog.com | Cryptolog |
| Olivier Delos | olivier.delos@sealed.be | SEALED sprl |
| Paloma LLaneza | pll@palomallaneza.com | LLaneza A+A / AENOR |
| Peter Lipp | peter.lipp@iaik.tugraz.at | Stiftung / FTW |
| Stefan Santesson | stefan@aaa-sec.com | 3xA Security |
| Sylvie Lacroix | sylvie.lacroix@sealed.be | SEALED sprl |

Table of content

1	STF funding	2

2	In-kind contribution	2

3	Travel plan	2

4	STF deliverables	4

5	STF reporting and milestones schedule (T0 = 1 January 2013)	5

6	Contracts	7

7	Allocation of tasks	8

8	Time recording	8

8.1	Remunerated work	8

8.2	Voluntary work	8

8.3	Practical instructions	8

9	Electronic working tools	9

9.1	STF folder on “docbox”	9

9.2	e-mail	9

9.3	WEB page	9

10	Attachments:	9

Annex A:  Reference Information on STF process (useful addresses)	10

# STF funding

This STF is funded under EC/EFTA Mandate M460, Grant Agreement SA/ETSI/ENTR/460/2012-09 Phase 2c, part A.  The available resources are summarized in the following table:

| EC - ETSI Contributions |
| --- |
|  | Expert | CTI | Total days | Total € | % |
| EC/EFTA | 611 X 600 | 0 | 611 | 366 600 |  |
| Travel |  |  |  | 35 600 |  |
| Total EC Contribution |  |  |  | 402 200 | 59,83 |
| Contributions in-kind | 450 x 600 |  | 450 | 270 000 |  |
| Total ETSI Contribution |  |  |  | 270 000 | 40,17 |
| TOTAL |  |  |  | 672 200 | 100 |

# In-kind contribution

An in-kind contribution amounting to 270 000 € (the equivalent of 450 man-days) will be provided as an element of the co-financing of this action. These man-days will be justified by signatures for specifically designed attendance sheets by participants in the planned activity. Signatures at TB and reference body meetings (ETSI) will be valued at three times the one day signed for. Signatures from other standards body meetings, workshops, consultations, etc. will be solely for the eligible day or half-day.  The total cost of funding via in kind contribution is 270 000 € (40,17% of the total action cost).

# Travel plan

Table 7a: Travels – Year 1

| Concept | Number of Travels | Number of travellers | Cost per travel | Total Cost |
| --- | --- | --- | --- | --- |
| travels of the leader to CEN-ETSI eSignature Coordination Group meetings | 3 | 1 | 800 | 2 400 |
| Travels of the leader to the ETSI ESI meetings | 4 | 1 | 800 | 3 200 |
| Travels of the leader to the open workshop | 1 | 1 | 800 | 800 |
| travels to disseminate the work to non-European conferences/for a | 1 | 1 | 1 800 | 1 800 |
| Liaison meetings with stakeholders (EU projects, Bodies, Associations, conferences) | 10 | 1 | 800 | 8 000 |
| Total Y1 |  |  |  | 16 200 |

Table 7b: Travels – Year 2

| Concept | Number of Travels | Number of travellers | Cost per travel | Total Cost |
| --- | --- | --- | --- | --- |
| travels of the leader to CEN-ETSI eSignature Coordination Group meeting | 3 | 1 | 800 | 2 400 |
| Travels of the leader to the ETSI ESI meetings | 4 | 1 | 800 | 3 200 |
| travels to disseminate the work to non-European conferences/for a | 1 | 1 | 1 800 | 1 800 |
| Liaison meetings with stakeholders (EU projects, Bodies, Associations, conference) | 8 | 1 | 800 | 6 400 |
| Total Y2 |  |  |  | 13 800 |

Table 7c: Travels – Year 3

| Concept | Number of Travels | Number of travellers | Cost per travel | Total Cost |
| --- | --- | --- | --- | --- |
| travels of the leader to CEN-ETSI eSignature Coordination Group meeting | 3 | 1 | 800 | 2 400 |
| Travels of the leader to the ETSI ESI meetings | 4 | 1 | 800 | 3 200 |
| Total Y3 |  |  |  | 5 600 |

Total travel budget is estimated at 35 600 EUR over 3 years.

# STF deliverables

| Area | Task | Deliv code | Deliverable | Subject | Num exp | Y1 | Y2 | Y3 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 0 | 1.0 |  | Area 1 Leader | 1 | 10 | 10 | 10 | 30 |
| 1 | 1 | 1.1 | EN 319 102 | Procedures for Signature Creation and Validation | 4-5 | 32 | 18 | 10 | 60 |
| 1 | 2 | 2.1 | EN 319 122 | CMS Advanced Electronic Signature Formats (CAdES) | 4-5 | 80 | 40 | 30 | 150 |
| 1 | 2 | 2.2 | EN 319 132 | XML Advanced Electronic Signature Formats (XAdES) |  |  |  |  |  |
| 1 | 2 | 2.3 | EN 319 142 | PDF Advanced Electronic Signature Formats (PAdES) |  |  |  |  |  |
| 1 | 2 | 2.4 | EN 319 162 | Associated Signature Containers (ASiC) |  |  |  |  |  |
| 1 | 3 | 3 | EN 319 152 | Advanced Electronic Signatures in Mobile environments | 4-5 | 20 | 10 | 10 | 40 |
| 1 | 4 | 4 | EN 319 172 | Signature Policies | 4-5 | 45 | 20 | 10 | 75 |
| 2 | 0 | 2.0 |  | Area 2 Leader | 1 | 10 | 10 | 10 | 30 |
| 2 | 1 | 1.1 | EN 319 411-2 | Policy requirements for CAs issuing Qualified Certificates | 2 | 15 | 8 | 7 | 30 |
| 2 | 1 | 1.2 | EN 319 411-3 | Policy requirements for CAs issuing public key certificates |  |  |  |  |  |
| 2 | 2 | 2 | EN 319 411-4 | Policy requirements for CAs issuing TLS/SSL Certificates | 2 | 11 | 7 | 7 | 25 |
| 2 | 3 | 3 | EN 319 411-5 | Policy requirements for CAs issuing attribute Certificates | 1 | 7 | 5 | 5 | 17 |
| 2 | 4 | 4 | EN 319 421-2 | Policy Requirements for TSPs providing Time-Stamping | 1 | 7 | 5 | 5 | 17 |
| 2 | 5 | 5 | EN 319 412 | Profiles for TSPs issuing Certificates | 3 | 20 | 10 | 9 | 39 |
| 2 |  | 5.1 | Part 1 | Part 1: Overview |  |  |  |  | 0 |
| 2 |  | 5.2 | Part 2 | voluntary from TS 102 280 |  |  |  |  | 0 |
| 2 |  | 5.3 | Part 3 | Part 3: Certificate profile for certificates issued to legal persons |  |  |  |  | 0 |
| 2 |  | 5.4 | Part 4 | Part 4: Profiles for SSL/TSL certificates issued to organisation |  |  |  |  | 0 |
| 2 | 6 | 6 | EN 319 422 | Profile for Trust Service Providers providing Time-Stamping | 1 | 7 | 5 | 5 | 17 |
| 2 | 7 | 7 | EN 319 403 | Requirements and guidance Conformity TSPs supporting ES | 3 | 23 | 10 | 9 | 42 |
| 2 | 8 | 8 | EN 319 413 | Conformity for TSPs Issuing Certificates | 1 | 3 | 14 | 5 | 22 |
| 2 | 9 | 9 | EN 319 423 | Conformity for TSPs providing Time-Stamping Services |  | 2 | 10 | 5 | 17 |
| Total |  |  |  |  |  | 292 | 182 | 137 | 611 |

# STF reporting and milestones schedule (T0 = 1 January 2013)

Coordination and reporting:

| T0 M01 to T0 M11 | Quarterly report on Coordination Activities approved by TC ESI M6 includes Interim Report, M11 includes Final Report (see below) | End of each Quarter from Q2 (may be aligned with ESI meetings) |
| --- | --- | --- |
| T0.M6 | Interim Report approved by EC/EFTA. The draft Interim Report must be delivered by the STF Leader to the ETSI Secretariat before 1 July 2014. The deadline for delivery to EC/EFTA by the ETSI Secretariat is 31 July 2014. EC/EFTA approval is expected not later than 45 days after delivery. | 1 July 2014 (Draft) 31 July 2014 (EC/EFTA) |
| T0.M11 | Final Report approved by EC/EFTA. The draft Final Report must be delivered by the STF Leader to the ETSI Secretariat before 1 December 2015. The deadline for delivery to EC/EFTA by the ETSI Secretariat is 31 December 2015. All ETSI deliverables required in the ToR must have been published. EC/EFTA approval is expected not later than 45 days after delivery. | 1 Dec 2015 (Draft) 31 Dec 2015 (EC/EFTA) |

Signature Creation and Validation Area

| Milestone | Description | Due Date |
| --- | --- | --- |
| T1.M1 | Stable Draft for Public Review of 319 102 | T0 + 11 |
| T1.M2 | Final Draft for TC approval of 319 102 | T0 + 16 |
| T1.M3 | Draft EN 319 102 submitted to EN approval procedure | T0 + 19 |
| T1.M4 | EN 319 102 published | T0 + 34 |
| T2.x.M1 | Stable Drafts for Public Review of 319 122, 319 132, 319 142, and 319 162 | T0 + 11 |
| T2.x.M2 | Final Drafts for TC approval of 319 122, 319 132, 319 142, and 319 162 | T0 + 16 |
| T2.x.M3 | Draft EN 319 122, 319 132, 319 142, 319 162 submitted to EN approval procedure | T0 + 19 |
| T2.x.M4 | EN 319 122, 319 132, 319 142, 319 162 published | T0 + 34 |
| T3.M1 | Stable Draft for Public Review of 319 152 | T0 + 11 |
| T3.M2 | Final Drafts for TC approval of 319 152 | T0 + 16 |
| T3.M3 | Draft EN 319 152 submitted to EN approval procedure | T0 + 19 |
| T4.M4 | EN 319 152 published | T0 + 34 |
| T4.M1 | Stable Draft for Public Review of 319 172 | T0 + 11 |
| T4.M2 | Final Drafts for TC approval of 319 172 | T0 + 16 |
| T4.M3 | Draft EN 319 172 submitted to EN approval procedure | T0 + 19 |
| T4.M4 | EN 319 172 published | T0 + 34 |

TSPs Supporting Electronic Signatures Area

| Milestone | Description | Due Date |
| --- | --- | --- |
| T1.1,1.2 M1 | Check List Annex on Policy Requirements for CA issuing Certificates - Draft for public review | T0+11 |
| T1.1,1.2 M2 | Check List Annex on Policy Requirements for CA issuing Certificates - Draft for TC approval | T0+16 |
| T1.1,1.2 M3 | Check List Annex on Policy Requirements for CA issuing Certificates - Draft for EN approval procedure | T0+19 |
| T1.1, 1.2 M4 | Check List Annex on Policy Requirements for CA issuing Certificates - ENs published | T0 +34 |
| T2M1 | Additional Parts of Policy Requirements for CA issuing SSL Certificates - Draft for public review | T0+11 |
| T2M2 | Additional Parts of Policy Requirements for CA issuing SSL Certificates - Draft for TC approval | T0+16 |
| T2M3 | Additional Parts of Policy Requirements for CA issuing SSL Certificates - Draft for EN approval procedure | T0+19 |
| T2M4 | Additional Parts of Policy Requirements for CA issuing SSL Certificates - EN published | T0 +34 |
| T3M1 | Additional Parts of Policy Requirements for CA’s Issuing Attribute Certificates - Draft for public review | T0+11 |
| T3M2 | Additional Parts of Policy Requirements for CA’s Issuing Attribute Certificates - Draft for TC approval | T0+16 |
| T3M3 | Additional Parts of Policy Requirements for CA’s Issuing Attribute Certificates - Draft for EN approval procedure | T0+19 |
| T3M4 | Additional Parts of Policy Requirements for CA’s Issuing Attribute Certificates - EN published | T0 + 34 |
| T4M1 | Policy Requirements for TSPs issuing time-stamps - Draft for public review | T0+11 |
| T4M2 | Policy Requirements for TSPs issuing time-stamps - Draft for TC approval | T0+16 |
| T4M3 | Policy Requirements for TSPs issuing time-stamps - Draft for EN approval procedure | T0+19 |
| T4M4 | Policy Requirements for TSPs issuing time-stamps – En published | T0+34 |
| T5M1 | Additional Profiles for TSPs Issuing certificates - Draft for public review | T0+9 |
| T5M2 | Additional Profiles for TSPs Issuing certificates - Draft for TC approval | T0+14 |
| T5M3 | Additional Profiles for TSPs Issuing certificates - Draft for EN approval procedure | T0+17 |
| T5 M4 | Additional Profiles for TSPs Issuing certificates – ENs published | T0+32 |
| T6M1 | Profiles for Time-stamping - Draft for EN approval procedure | T0+9 |
| T6M2 | Profiles for Time-stamping - Draft for TC approval | T0+14 |
| T6M3 | Profiles for Time-stamping - Draft for EN approval procedure | T0+17 |
| T6 M4 | Profiles for Time-stamping - EN published | T0 +32 |
| T7M1 | TSP conformity assessment general requirements - Draft for public review | T0+9 |
| T7M2 | TSP conformity assessment general requirements - Draft for TC approval | T0+14 |
| T7M3 | TSP conformity assessment general requirements - Draft for EN approval procedure | T0+17 |
| T7M4 | TSP conformity assessment general requirements – EN published | T0 + 32 |
| T8M1 | Conformity assessment for TSPs issuing certificates - Draft for public review | T0+14 |
| T8M2 | Conformity assessment for TSPs issuing certificates - Draft for TC approval | T0+19 |
| T8M3 | Conformity assessment for TSPs issuing certificates - Draft for EN approval procedure | T0+22 |
| T8 M4 | Conformity assessment for TSPs issuing certificates – EN published | T0 + 35 |
| T9M1 | Conformity assessment for TSPs providing time-stamping services - Draft for public review | T0+14 |
| T9M2 | Conformity assessment for TSPs providing time-stamping services - Draft for TC approval | T0+19 |
| T9M3 | Conformity assessment for TSPs providing time-stamping services - Draft for EN approval procedure | T0+22 |
| T9M4 | Conformity assessment for TSPs providing time-stamping services – EN published | T0 + 35 |

# Contracts

|  | Initial contract | Possible extension |
| --- | --- | --- |
| Expert | Days | From | To | Days | Total |
| Juan Carlos Cruellas | 46 | 01/04/2013 | 31/03/2014 | 46 | 92 |
| Peter Lipp | 18 | 01/04/2013 | 31/03/2014 | 11 | 29 |
| Andrea Röck | 21 | 01/04/2013 | 31/03/2014 | 20 | 41 |
| Luigi Rizzo | 14 | 01/04/2013 | 31/03/2014 | 12 | 26 |
| Alexander Funk | 14 | 01/04/2013 | 31/03/2014 | 12 | 26 |
| Jon Olnes | 19 | 01/04/2013 | 31/03/2014 | 14 | 33 |
| Ijaz Khan | 5 | 01/04/2013 | 31/03/2014 | 2 | 7 |
| Arne Tauber | 5 | 01/04/2013 | 31/03/2014 | 2 | 7 |
| Andrea Caccia | 21 | 01/04/2013 | 31/03/2014 | 22 | 43 |
| Nick Pope | 40 | 01/04/2013 | 31/03/2014 | 64 | 104 |
| Paloma LLaneza | 10 | 01/04/2013 | 31/03/2014 | 18 | 28 |
| Stefan Santesson | 13 | 01/04/2013 | 31/03/2014 | 15 | 28 |
| Sylvie Lacroix | 19 | 01/04/2013 | 31/03/2014 | 15 | 34 |
| Frank Leroy | 11 | 01/04/2013 | 31/03/2014 | 25 | 36 |
| Inigo Barreira | 12 | 01/04/2013 | 31/03/2014 | 14 | 26 |
| Arno Fiedler | 12 | 01/04/2013 | 31/03/2014 | 11 | 23 |
| Olivier Delos | 16 | 01/04/2013 | 31/03/2014 | 12 | 28 |
| Leonard Rosenthol | Volunt. | 01/04/2013 | 31/03/2014 |  |  |
| Moez Ben Mbarka | Volunt. | 01/04/2013 | 31/03/2014 |  |  |
| Total contracted | 296 |  |  | 306 | 611 |

Initial contracts will be extended according the actual progress of the STF work.

The possible extension represents a preliminary estimate of the resources allocation and does not guarantee the actual amount that it will granted to each expert.

# Allocation of tasks

The EXCEL sheet contains the details of the allocation of tasks and resources to the experts and the milestones.

# Time recording

## Remunerated work

Time sheets will be recorded separately for each area:

A1 Creation & Valid.(budget 346 working days, including «Area 1 Leader» work)

A2 TSP Policy/Format (budget 247 working days, including «Area 2 Leader» work)

STF Leader (budget 18 working days)

## Voluntary work

If experts under remunerated contract work more days than contracted, time sheets exceeding the contract allocation will be charged on a separate line “Extra work contract”, independently of the deliverable/task.  This time will be reported as Performance Indicator but is not eligible for the “In-kind contribution”.

Experts who only contribute on a voluntary basis will charge their time sheets on a separate line “Volunt contrib. (IK)”.  This time is eligible to be accounted as “In-kind contribution”

## Practical instructions

Time sheets will be recorded on the WEB application Time Allocation Management (TAM), at the following address: http://webapp.etsi.org/STF_TAM/Frames.asp

To create your first time sheet, select the STF, your name and the month you want to declare in both “From” and “To” boxes and select the area on which you have worked.  If you worked on different areas, you must create a separate time sheet for each area.

# Electronic working tools

## STF folder on “docbox”

A folder will be created on the ETSI Server (docbox) to exchange documents, at the following address: http://portal.etsi.org/docbox/STF (subfolder “STF458_ESI_M460”).

The predefined docbox structure contains the following folders:

- Inbox: read/write access to ETSI Members with an EoL account – used to upload new documents from outside the STF

- PrepMeet: readonly access to ETSI Members with an EoL account – information from Prep. Meet. (EXCEL sheet, ToR, etc.)

- Public: readonly access to ETSI Members with an EoL account – used to make STF documents available for consultation WITHIN ETSI

- STFworkarea read/write restricted to STF experts + TB Officials and Secretariat – used to store working documents before they can be made public

## e-mail

An e-mail list with archive will be created at the following address: STF458@list.etsi.org for the communication to all STF and four lists, one for each area:

- STF457_A1@list.etsi.org,

- STF457_A2@list.etsi.org

The archive can be accessed from the list management page: http://list.etsi.org/.

The ETSI Secretariat will be the owner and can extend access rights to other participants upon request of the STF Leader.  The list and is restricted to ETSI Members.  If access to non-ETSI Members is required, the authorization must be requested to the STF Support Unit Director.

## WEB page

The ETSI Secretariat will create and maintain a WEB page for each STF that can be used to present the STF but also to disseminate information and upload the drafts for public review, to collect comments in-between releases.  The drafts can be referenced with hyperlinks in the page.  The STF Leader can send the URL to stakeholders.  The ETSI Secretariat can set-up a mailbox to collect the answers.  ex. http://portal.etsi.org/stfs/STF_HomePages/STF425/STF425.asp

# Attachments:

- ToR STF458 v0.1 directly derived from the Technical Annex to the EC/EFTA contract.

Annex A:  Reference Information on STF process (useful addresses)

The reference information and contact persons concerning the STF management process and requirements can be found at the following addresses:

| ETSI WEB site | http://www.etsi.org/ |
| --- | --- |
| ETSI Portal | http://portal.etsi.org/ |
| STF reference Information | http://portal.etsi.org/Portal_STF/FullSearch.asp?Param |
| STF management process | http://portal.etsi.org/stfs/process/home.asp |
| STF working conditions | http://portal.etsi.org/stfs/process/item6_STFwork/item6_A_STFWork.asp |
| STF “contractual” conditions | http://portal.etsi.org/stfs/process/item5_Contr&Invoice/item5_A_LoEconditions.asp |
| STF Travel application | http://webapp.etsi.org/travel/ |
| Time Allocation Management (TAM) | http://webapp.etsi.org/STF_TAM/ |
| Mailing lists server | http://list.etsi.org/ |
| EditHelp (standards drafting support) | http://portal.etsi.org/edithelp/home.asp http://portal.etsi.org/edithelp/ETSI_Packs/Deliverables_pack/index.asp mailto:edithelp@etsi.org |
| CTI (Conformance Testing and Interoperability Competence Centre) | http://www.etsi.org/technicalfocus/home.htm |
| Helpdesk (IT support) | http://portal.etsi.org/helpdesk/home.asp +33 4 9294 4900 |
| STFLINK (STF support) | mailto:STFLINK@etsi.org |
| STF Support Unit Director Alberto Berrini | alberto.berrini@etsi.org +33 6 30 67 93 61 |
| STF Support Assistants Marithé Carlier | marithe.carlier@etsi.org +33 4 9294 4325 |