## Task matrix STF473
| Company | Berioli consult. | Rammer consult. | CNIT | Manpower |  |  | Duration
| Support | DLR | HUGHES | Member | Days |  |  | (T0 + months) |  | Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| Expert | Matteo Berioli | Josef Rammer | Sara Jayousi | Alloc. | Required | Conting. | Start | End |  | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Start | End | Objective
Phase 1 | Protocol definition and preliminary design |  |  |  | 0 |  | 0 |  |  | Phase 1 | [18 empty] | 2013-12-01 |  | Start date of EC/EFTA contract
1.1 | State of Art of existing alerting protocols | 3 | 4 | 3 | 10 | 10 | 0 | 2 | 3 | 1.1 | 0 | 5.001 | 5.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME?
1.2 | Operational Scenario, Integration in Existing Telecommunication and Navigation Systems | 3 | 9 | 8 | 20 | 20 | 0 | 2 | 3 | 1.2 | 0 | 10.001 | 10.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | Progress Report. validation of tasks 1.1 and 1.2 + draft table of content TR & TS
1.3 | Protocol Requirements | 6 | 24 | 30 | 60 | 60 | 0 | 4 | 6 | 1.3 | 0 | 0 | 0 | 20.001 | 20.001 | 20.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | Progress Report. validation of tasks 1.3
1.4 | MAMES Messages Definition | 5 | 35 | 52 | 92 | 92 | 0 | 7 | 11 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 18.401 | 18.401 | 18.401 | 18.401 | 18.401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME?
1.5 | Supporting Studies for Transport/Message Enhancers (TR draft) | 5 | 25 | 35 | 65 | 65 | 0 | 7 | 11 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 13.001 | 13.001 | 13.001 | 13.001 | 13.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME?
IR | Interim Report to the EC | 6 | 1 | 1 | 8 | 8 | 0 | 11 | 12 | IR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.001 | 4.001 | 0 | 0 | 0 | 0 | 0 | 0 | #NAME? | #NAME? | Interim report delivered to EC. Validation of tasks 1.4 and 1.5
| Sub-total Phase 1 | 28 | 98 | 129 | 255 | 255 | 0
Phase 2 | Protocol detailed design, TS/TR prod. | [8 empty] | Phase 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | MAMES Specification | 6 | 19 | 46 | 71 | 71 | 0 | 10 | 15 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.8343 | 11.8343 | 11.8343 | 11.8343 | 11.8343 | 11.8343 | 0 | 0 | 0 | #NAME? | #NAME?
2.2 | MAMES Integration Guidelines | 8 | 3 | 10 | 21 | 21 | 0 | 12 | 15 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.251 | 5.251 | 5.251 | 5.251 | 0 | 0 | 0 | #NAME? | #NAME?
2.3 | TS/TR Production and Dissemination | 6 | 19 | 35 | 60 | 60 | 0 | 14 | 16 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.001 | 20.001 | 20.001 | 0 | 0 | #NAME? | #NAME? | Progress Report. statement of tasks 2.1. 2.2 & 2.3. draft for Final report
| TC SES approval |  |  |  | 0 |  |  | 17 | 17 | TC appr. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0 | #NAME? | #NAME?
| Final Report to the EC | 6 | 1 | 1 | 8 | 8 | 0 | 17 | 18 | FR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.001 | 4.001 | #NAME? | #NAME? | Final report delivered to EC and publication
| Sub-total Phase 2 | 26 | 42 | 92 | 160 | 160 | 0 | bar: Sep to May
| Total planned | 54 | 140 | 221 | 415 | 415 | 0 |  |  | days/mo | 0 | 15.002 | 15.002 | 20.001 | 20.001 | 20.001 | 31.402 | 31.402 | 31.402 | 43.2363 | 47.2373 | 21.0863 | 17.0853 | 37.0863 | 37.0863 | 20.001 | 4.002 | 4.001
Initial contracts to be extended after SatEC#26 (11-12 Sep) |  | 27 | 89 | 119 | 235 | 415 | 180 |  |  |  | 7.5% | 7.5% | 3.75% | 8.75% | 13.75% | 18.75% | 26.6% | 34.45% | 42.3% | 53.11% | 64.92% | 70.19% | 74.46% | 83.73% | 93% | 98% | 99% | 100%
| Covers tasks until end-Sep | [27 empty] | SatEC#24 9-10 April 2014 (1st mile stone validation) | bar: Apr
SatEC#25 3 July 2014 (2nd milestone) | bar: Jul
SatEC#26 11-12 september 2014 (work plan for phase 2) | bar: Sep
SatEC#27 29th of October (Validation of the interim report) | bar: Oct
[10 empty] | MIL A | Dec: KO+4; Jan: Progress Report. validation of tasks 1.1 and 1.2 + draft table of content TR & TS
[10 empty] | MIL B | Dec: KO+7; Jan: Progress Report. validation of tasks 1.3
[10 empty] | MIL C | Dec: KO+12; Jan: Interim report for EC
[10 empty] | MIL D | Dec: KO+15; Jan: Progress Report. statement of tasks 2.1. 2.2 & 2.3. draft for Final report
[10 empty] | MIL E | Dec: KO+18; Jan: Final report for EC

## Orig Work plan (ToR)
Phase 1 - Protocol definition and preliminary design |  |  | Month | To+2 | To+4 | To+6 | To+8 | To+10 | To+12 INTERIM REPORT |  | To+16 | To+18 FINAL REPORT
Task 1.1 | State of Art of existing alerting protocols | 10 | [7 empty] | To+14
Task 1.2 | Operational Scenario and Integration in Existing Telecommunication and Navigation Systems | 20
Task 1.3 | Protocol Requirements | 98 | Task
Task 1.4 | MAMES Messages Definition | 65 | 0
Task 1.5 | Supporting Studies for Transport/Message Enhancers (TR draft) | 70 | 1.1
Total days Phase 1 |  | 263 | 1.2
Phase 2 - Protocol detailed design and TS/TR production |  |  | 1.3
Task 2.1 | MAMES Specification | 71 | 1.4
Task 2.2 | MAMES Integration Guidelines | 21 | 1.5
Task 2.3 | TS/TR Production | 60 | 2.1
Total days Phase 2 |  | 152 | 2.2
| Total man-days | 415 | 2.3
Profile A
· Experience and qualifications in satellite telecommunication engineering
· An understanding of the available protocols for Satellite communication (e.g. DVB family)
· Experience in protocol modelling
· Additionally, qualifications related to public safety communications, Machine-to Machine (M2M), commercial satellite broadcast, message services or navigation systems would be very beneficial.
Profile B
· Experience and qualifications in satellite telecommunication engineering
· Strong background on technical and engineering aspects of GNSS positioning system
· Additionally, knowledge of strategic market impacts of GNSS applications, eventual participation and/or relationship with European GNSS Agency (GSA)

## Table for ToR
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Phase 1
1.1 | 0 | 5.001 | 5.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 0 | 10.001 | 10.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | 0 | 0 | 0 | 20.001 | 20.001 | 20.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 18.401 | 18.401 | 18.401 | 18.401 | 18.401 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 13.001 | 13.001 | 13.001 | 13.001 | 13.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.001 | 4.001 | 0 | 0 | 0 | 0 | 0 | 0
Phase 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.8343 | 11.8343 | 11.8343 | 11.8343 | 11.8343 | 11.8343 | 0 | 0 | 0
2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.251 | 5.251 | 5.251 | 5.251 | 0 | 0 | 0
2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.001 | 20.001 | 20.001 | 0 | 0
TC appr. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.001 | 0
FR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.001 | 4.001
days/ month | 0 | 15.002 | 15.002 | 20.001 | 20.001 | 20.001 | 31.402 | 31.402 | 31.402 | 43.2363 | 47.2373 | 21.0863 | 17.0853 | 37.0863 | 37.0863 | 20.001 | 4.002 | 4.001
Cumul | 7.5% | 7.5% | 3.75% | 8.75% | 13.75% | 18.75% | 26.6% | 34.45% | 42.3% | 53.11% | 64.92% | 70.19% | 74.46% | 83.73% | 93% | 98% | 99% | 100%
MIL A | Dec: KO+4; Jan: Progress Report. validation of tasks 1.1 and 1.2 + draft table of content TR & TS
MIL B | Dec: KO+7; Jan: Progress Report. validation of tasks 1.3
MIL C | Dec: KO+12; Jan: Interim report for EC
MIL D | Dec: KO+15; Jan: Progress Report. statement of tasks 2.1. 2.2 & 2.3. draft for Final report
MIL E | Dec: KO+18; Jan: Final report for EC